## 2023.01.17 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (1) [on 2022.12.17 project was added.] | 1800 S. Knik Goose Bay Road Structures Removal | Wasilla | 2022-12-01 | Z524640000A | Z524640000A | 525016 | Vadim Belozertsev | (907)269-0879 | This federally funded contract includes the removal and disposal or salvage of all buildings, structures, and any other obstructions and improvements at 1800 S. Knik Goose Bay Road, located in Wasilla, Alaska. This project includes hazardous materials handling. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (1) [on 2022.12.17 the ANTADVDT changed to December 2022.] | (2) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | 1800 S. Knik Goose Bay Road Structures Removal | Wasilla | 2022-12-01 | Z524640000-A | Z524640000-A | N/A | Vadim Belozertsev | (907)269-0879 | This federally funded contract includes the removal and disposal or salvage of all buildings, fences, structures, abandoned utilities and any other obstructions and improvements at 1800 S. Knik Goose Bay Road, located in Wasilla, Alaska: |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (1) [on 2022.12.17 the ANTADVDT changed to December 2022.] | (6) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 FEDNUM changed.]; [on 2022.08.14 LOCATION changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | HSIP:CR Guardrail Inventory and Upgrade (North) | Matanuska-Susitna Borough | 2022-12-01 | CFHWY00939 | CFHWY00939 | 1746 | Chris L Bentz | (907)269-0652 | Prepare inventory by evaluating existing guardrail segments, end terminals, and associated hardware along several routes in Central Region for damage and adherence to current AKDOT&PF and FHWA standards. Use results of inventory to design and construct installation or updates to guardrail segments found in non-conformance with State and Federal standards. | This construction contract will be for the installation of guardrail upgrades in the Mat-Su area of Central Region following inventory and assessment efforts. Additional work may include; shoulder widening, slope flattening, bridge rail, signing, and other work associated or necessary for guardrail replacement. | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.10.20 the ANTADVDT changed to January 2023.] | (2) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to January 2023.] | STERLING SAFETY CORRIDOR IMPROVEMENTS MP 82.5 TO 94 DESIGN BUILD | Sterling | 2023-01-01 | CFHWY00130 | CFHWY00130 | 0A33026 | Kelly L Summers | (907)269-0546 | The Department anticipates issuing an RFP for a federally funded Design-Build contract to provide the necessary engineering, labor, equipment, and materials to design, construct, and warranty a four lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed project will improve safety and reduce congestion within this existing safety corridor. The department’s solicitation is contingent on federal authority to proceed with construction. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $60,000,000 and $70,000,000
Central Region | ADDED |  |  |  |  | 1360 E. Fairview Loop Structures Removal | Wasilla | 2023-01-01 | Z560200000A | Z560200000A | N/A | Vadim Belozertsev | (907)269-0879 | This State funded contract includes the removal and disposal or salvage of all buildings, structures, and any other obstructions and improvements at 1360 E. Fairview Loop, located in Wasilla, Alaska. |  | Less than $200,000
Central Region | ADDED |  |  |  |  | Mt. Edgecumbe High School Building 1331 Gymnasium Restroom Renovation | Central Region | 2023-01-01 | 25RC053605A | 25RC053605A | N/A | Christopher S Hodgin | (907)269-7484 | Renovation of the Building 1331 Gymnasium first floor and second floor restrooms. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | (1) [on 2022.02.22 the project was removed.] | COHOE LOOP RD MP 0-9.7 PAVEMENT PRESERVATION | Kasilof | 2023-02-01 | CFHWY00490 | CFHWY00490 | 1645 | Steven J Rzepka | (907)269-0592 | This federally funded pavement preservation project will resurface Cohoe Loop Road. In addition to resurfacing the road, the project will also include improvements to drainage and roadside hardware. | Project will advertise with CFHWY00493: Funny River Road Pavement Preservation. <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00490/00490_Plans.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | Mat-Su High Tower Repairs | Matanuska-Susitna Borough | 2023-02-01 | 23-25-1-001 | 23-25-1-001 | CFHWY00972 | Vernon S Vreeland | (907)269-0778 | The Contractor shall provide labor, equipment, materials, components, tools, traffic control, mobilization, demobilization and all other incidentals necessary to replace damaged components on high towers and to retrofit lighting to LED as shown in Appendixes and the specifications. Work includes lowering and raising high towers. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  |  | Mt. Edgecumbe High School Upper Campus ADA Upgrades | Central Region | 2023-02-01 | 25RC053614A | 25RC053614A | N/A | Christopher S Hodgin | (907)269-7484 | Construction of new ADA ramp entrance and canopy at breeezeway between Mt. Edgecumbe Buildings 292 (Boys Dorm) and Building 290 (Cafeteria). Installation of new stair lift in breezeway, ADA door actuators, and exterior power and lights at canopy. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  | (1) [on 2022.11.17 the ANTADVDT changed to July 2023.] | (5) [on 2022.04.15 project was added.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.] | AMATS: EAGLE RIVER LOOP RD - EAGLE RIVER RD TO OLD GLENN HWY | Eagle River | 2023-12-01 | CFHWY00731 | CFHWY00731 | 1694 | Julia R Hanson | (907)269-0753 | Pavement preservation, which may include improvements to roadside hardware, drainage, intersections, automated traffic recorders, pedestrian facilities, striping, signs, and utilities. | Project will be combined with CFHWY00621 North Eagle River Access Road Pavement Preservation | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  | (1) [on 2022.11.17 the ANTADVDT changed to July 2023.] | (3) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.] | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | Eagle River | 2023-12-01 | CFHWY00621 | CFHWY00621 | 1692 | Julia R Hanson | (907)269-0753 | This preventative maintenance project will resurface North Eagle River Access Road and may include as necessary; signing and striping, guardrail and other roadside hardware, signalization, lighting, drainage work, dig-outs, bridge repair, curb ramps, automated traffic recorders, and utility relocation. | Project will be combined with CFHWY00731 AMATS: Eagle River Loop Road Pavement Preservation. | Between $1,000,000 and $2,500,000
Central Region | ADDLINFO | <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00493/00493_Plans.pdf">Preliminary Plans (~14 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Project will advertise with CFHWY00490: Cohoe Loop Road MP 0-9.7 Pavement Preservation. <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00493/00493_Plans.pdf">Preliminary Plans (~14 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (4) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.] | (8) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 DESCRIPTION changed.] | FUNNY RIVER RD PAVEMENT PRESERVATION | Kenai | 2023-02-01 | CFHWY00493
Central Region | ANTADVDT | 2022-12-01 | 2023-01-01 | (3) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | (7) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 REGION changed.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 FEDNUM changed.] | Cold Bay Airport Structure Removal | Cold Bay | 2023-01-01 | SFAPT00399
Central Region | ANTADVDT | 2022-12-01 | 2023-01-01 | (1) [on 2022.12.17 the ANTADVDT changed to December 2022.] | (5) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 LOCATION changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | HSIP:CR Guardrail Inventory and Upgrade (South) | Kenai Peninsula | 2023-01-01 | CFHWY00938
Central Region | ANTADVDT | 2022-12-01 | 2023-01-01 | (3) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | (7) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 REGION changed.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 FEDNUM changed.] | Kodiak Airport Structure Removal | Kodiak | 2023-01-01 | SFAPT00398
Central Region | ANTADVDT | 2022-12-01 | 2023-02-01 | (3) [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.] | (4) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2023-02-01 | 25RC053613
Central Region | ANTADVDT | 2023-01-01 | 2023-02-01 |  | (1) [on 2022.11.17 project was added.] | 500 Hollywood Drive Structures Removal | Central Region | 2023-02-01 | z537350000
Central Region | ANTADVDT | 2023-01-01 | 2023-02-01 |  | (1) [on 2022.11.17 project was added.] | CHIGNIK AIRPORT SREB REHAB | Chignik | 2023-02-01 | SFAPT00368
Central Region | ANTADVDT | 2023-01-01 | 2023-02-01 | (4) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.] | (8) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 DESCRIPTION changed.] | FUNNY RIVER RD PAVEMENT PRESERVATION | Kenai | 2023-02-01 | CFHWY00493
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (4) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.] | (9) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2023-03-01 | CSAPT00931
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (1) [on 2022.12.17 the ANTADVDT changed to February 2023.] | (2) [on 2022.10.20 project was added.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2023-03-01 | CFAPT00983
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (3) [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | (8) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.07.12 ENGEST changed.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2023-03-01 | CFAPT00855
Central Region | ANTADVDT | 2023-02-01 | 2023-08-01 | (4) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.] | (7) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2023-08-01 | CFHWY00260
Central Region | ANTADVDT | 2023-02-01 | 2023-04-01 | (4) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.] | (6) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2023-04-01 | CFHWY00395
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (4) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | (10) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2023-03-01 | CFAPT00882
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (3) [on 2022.02.22 PHONENUM changed.]; [on 2022.03.15 ENGEST changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.] | Colleen Street Intersection and Frontage Road | Palmer | 2023-04-01 | CFHWY00006
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (2) [on 2022.02.22 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.] | Glenn Hwy: Parks Hwy to S. Inner Springer Lp. (Phase II) | Palmer | 2023-04-01 | CFHWY00431
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (2) [on 2022.02.22 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.] | Glenn Hwy: Parks to S. Inner Springer Lp. Pathway (Phase II) | Palmer | 2023-04-01 | CFHWY00432
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (2) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.09.13 the ANTADVDT changed to March 2023.] | (6) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.]; [on 2022.10.20 ADDLINFO changed.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2023-04-01 | CFHWY00253
Central Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $2,500,000 and $5,000,000 | (4) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | (10) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2023-03-01 | CFAPT00882
Central Region | ENGEST |  | Between $2,500,000 and $5,000,000 |  | (1) [on 2022.09.13 project was added.] | KENAI PENINSULA BRIDGE DECK REHABILITATIONS FY2023 | Kenai Peninsula | 2023-04-01 | CFHWY00946
Central Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 |  | (1) [on 2022.12.17 project was added.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-05-01 | CFAPT00993
Central Region | FEDNUM | N/A | 3-02-0016-XXX-2023 | (3) [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | (8) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.07.12 ENGEST changed.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2023-03-01 | CFAPT00855
Central Region | PHONENUM | (907)266-2171 | None | (7) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | (7) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | Mchugh RWIS Tower Upgrade | Municipality Of Anchorage | 2023-02-01 | CFHWY00428
Northern Region | (DELETED) |  |  |  | (1) [on 2022.12.17 project was added.] | Purple Heart Trail Signs FY2023 | Statewide | 2022-01-01 | 25O2532027 | 25O2532027 | N/A | Daniel S Adamczak | (907)451-2294 | This project consists of placing signs for the State of Alaska Purple Heart Trail, and to install interpretive waysides to provide further information and to extend the trail to include State traveled waterways. Existing signs will be updated. |  | Between $200,000 and $500,000
Northern Region | (DELETED) |  |  | (1) [on 2022.11.17 the ANTADVDT changed to December 2022.] | (2) [on 2022.08.14 project was added.]; [on 2022.11.17 the ANTADVDT changed to December 2022.] | Aurora Drive Noyes Slough Bridge #0209 Replacement | Fairbanks | 2022-12-01 | NFHWY00124 | NFHWY00124 | 629001 | Lauren M Little | (907)378-5911 | Replace the Noyes Slough Bridge #0209 on Aurora Drive in Fairbanks. Project work includes bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements and utility work. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  |  | RICHARDSON HWY MP 82-115 RESURFACING (CONST MP 97-115) | Valdez | 2023-12-01 | NFHWY00218 | NFHWY00218 | 712035 | Russell M Johnson | (907)451-5059 | Resurface the Richardson Highway from MP 97 - 115. Improvements include bridge work, drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Northern Region | ANTADVDT | 2023-01-01 | 2023-02-01 | (2) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.] | (4) [on 2022.05.16 project was added.]; [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.11.17 FEDNUM changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.] | Northern Region ADA Improvements - Fairbanks: College Road | Fairbanks | 2023-02-01 | NFHWY00591
Northern Region | ANTADVDT | 2023-02-01 | 2023-03-01 |  | (1) [on 2022.05.16 project was added.] | ELLIOTT HWY MP 51-63 REHABILITATION | Livengood | 2023-03-01 | NFHWY00420
Northern Region | ANTADVDT | 2023-02-01 | 2023-04-01 |  | (3) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.] | HSIP: Old Steese Highway Shoulder Widening | Fox | 2023-04-01 | NFHWY00527
Northern Region | ANTADVDT | 2023-03-01 | 2023-12-01 | (2) [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to March 2023.] | (4) [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.08.14 the ANTADVDT changed to March 2023.] | Nome Port Road Reconstruction | Nome | 2023-12-01 | Z621230000
Northern Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 |  | (3) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.] | HSIP: Old Steese Highway Shoulder Widening | Fox | 2023-04-01 | NFHWY00527
Northern Region | FEDNUM | N/A | Pending | (2) [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.12.17 the ANTADVDT changed to April 2023.] | (5) [on 2022.03.15 project was added.]; [on 2022.06.15 ADDLINFO changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.12.17 the ANTADVDT changed to April 2023.] | FAST AREA SURFACE UPGRADES FFY2023 | Fairbanks North Star Borough | 2023-04-01 | NFHWY00633
Northern Region | FEDNUM | N/A | 3-02-0363-___-____ |  | (1) [on 2022.08.14 project was added.] | Marshall Airport Improvements | Marshall | 2023-05-01 | NFAPT00371
Northern Region | PROJNAME | RICHARDSON HWY MILEPOST 233 BEAR CREEK BRIDGE #0593 REPLMNT | Richardson Highway Milepost 233 Bear Creek Bridge #0593 Replacement |  | (1) [on 2022.10.20 project was added.] | Richardson Highway Milepost 233 Bear Creek Bridge #0593 Replacement | Delta Junction | 2023-04-01 | NFHWY00278
Northern Region | PROJNAME | MARSHALL AIRPORT IMPROVEMENTS | Marshall Airport Improvements |  | (1) [on 2022.08.14 project was added.] | Marshall Airport Improvements | Marshall | 2023-05-01 | NFAPT00371
Southcoast Region | (DELETED) |  |  |  | (6) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2023-09-01 | SFAPT00227 | SFAPT00227 | N/A | David A Pyeatt | (907)465-4490 | ADQ airport ARFF Access improvements and Rehabilitation of Taxiway C, D and F. Project includes the non-private portion of the Apron. | PFAS Investigation may cause delay depending on results and how to manage waste material | Between $50,000,000 and $60,000,000
Southcoast Region | ADDED |  |  |  |  | SE District Hwy Painting FFY23 - NHS | Regionwide | 2023-02-01 | SFHWY00463 | SFHWY00463 | N/A | David B Epstein | (907)465-4483 | SCOPE: Development of NHS & Non-NHS preservation maintenance projects. These projects consist of pavement preservation on highways, catch basins, culverts, pavement markings, luminary replacement, bridge preservation, drainage preservation, gravel surface preservation, & vegetation management on various NHS & Non-NHS routes in the Southcoast Region. Design work will be accomplished under this program, and separate projects will be established for the construction phase for each federal fiscal years program. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  |  |  | SR Airport Pavement Markings FFY23 | Regionwide | 2023-02-01 | SFAPT00289-1 | SFAPT00289-1 | 3-02-0000-027-2020 | David B Epstein | (907)465-4483 | Perform SPM at various primary and non-primary airports in SR. Planned maintenance activities include: maintaining pavement markings on runways, taxiways, and aprons at Ketchikan, Petersburg, Wrangell, and Yakutat. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | FFY23 HNS AP SPM PAVEMENT MARKINGS | Haines | 2023-03-01 | SFAPT00421 | SFAPT00421 | N/A | David B Epstein | (907)465-4483 | Repaint pavement markings on the runway, taxiway, and apron
Southcoast Region | ADDED |  |  |  | (5) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2023-12-01 | SFAPT00178 | SFAPT00178 | N/A | Gregory K Lockwood | (907)465-2393 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
Southcoast Region | ANTADVDT | 2022-12-01 | 2023-01-01 | (4) [on 2022.01.18 the ANTADVDT changed to July 2022.]; [on 2022.02.22 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | (8) [on 2022.01.18 the ANTADVDT changed to July 2022.]; [on 2022.02.22 the ANTADVDT changed to August 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.09.13 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | JNU EGAN YANDUKIN INTERSECTION IMPROVEMENTS HSIP | Juneau | 2023-01-01 | SFHWY00307
Southcoast Region | ANTADVDT | 2022-12-01 | 2023-01-01 | (3) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | (4) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2023-01-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2022-12-01 | 2023-04-01 |  | (1) [on 2022.11.17 project was added.] | Lemon Creek Correctional Center Structural Repairs CM/GC | Juneau | 2023-04-01 | 25C2023065
Southcoast Region | ANTADVDT | 2023-02-01 | 2023-06-01 | (3) [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.08.14 the ANTADVDT changed to February 2023.] | (6) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.06.15 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to February 2023.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-06-01 | SFHWY00058-3
Southcoast Region | ANTADVDT | 2023-09-01 | 2023-11-01 | (4) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.] | (12) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-11-01 | SFHWY00359
Southcoast Region | PHONENUM | (907)465-8189 | (907)465-4812 |  | (1) [on 2022.09.13 project was added.] | HYG - HYDABURG SEAPLANE FACILITY REFURBISHMENT | Hydaburg | 2023-08-01 | SFAPT00328
Southcoast Region | PHONENUM | (907)465-8189 | (907)465-4483 |  | (3) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.] | KING SALMON AIRPORT PERIMETER FENCING UPGRADES | King Salmon | 2023-08-01 | SFAPT00124
Southcoast Region | PROJMAN | Loren K Gehring | David H Lowell |  | (1) [on 2022.09.13 project was added.] | HYG - HYDABURG SEAPLANE FACILITY REFURBISHMENT | Hydaburg | 2023-08-01 | SFAPT00328
Southcoast Region | PROJMAN | Loren K Gehring | David B Epstein |  | (3) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.] | KING SALMON AIRPORT PERIMETER FENCING UPGRADES | King Salmon | 2023-08-01 | SFAPT00124