## 2023.03.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (2) [on 2022.02.22 the project was removed.]; [on 2023.01.17 project was added.] | COHOE LOOP RD MP 0-9.7 PAVEMENT PRESERVATION | Kasilof | 2023-02-01 | CFHWY00490 | CFHWY00490 | 1645 | Steven J Rzepka | (907)269-0592 | This federally funded pavement preservation project will resurface Cohoe Loop Road. In addition to resurfacing the road, the project will also include improvements to drainage and roadside hardware. | Project will advertise with CFHWY00493: Funny River Road Pavement Preservation. <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00490/00490_Plans.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (5) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.01.17 the ANTADVDT changed to February 2023.] | (10) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2023.01.17 ADDLINFO changed.]; [on 2023.01.17 the ANTADVDT changed to February 2023.] | FUNNY RIVER RD PAVEMENT PRESERVATION | Kenai | 2023-02-01 | CFHWY00493 | CFHWY00493 | 485002 | Steven J Rzepka | (907)269-0592 | This federally funded pavement preservation project will resurface Funny River Road. In addition to resurfacing the road, the project will also include improvements to drainage, roadside hardware, and the roadway structural section in select locations. | Project will advertise with CFHWY00490: Cohoe Loop Road MP 0-9.7 Pavement Preservation. <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00493/00493_Plans.pdf">Preliminary Plans (~14 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2023.01.17 project was added.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.02.24 LOCATION changed.] | Mt. Edgecumbe High School Upper Campus ADA Upgrades | Sitka | 2023-02-01 | 25RC053614A | 25RC053614A | N/A | Christopher S Hodgin | (907)269-7484 | Construction of new stairs and ADA ramp entrance and canopy at breeezeway between Mt. Edgecumbe Buildings 292 (Boys Dorm) and Building 290 (Cafeteria). Installation of new stair lift in breezeway, ADA door actuators, and exterior power and lights at canopy. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.12.17 the ANTADVDT changed to March 2023.] | (7) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.11.17 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.] | ANC RON 3 AND 4 REHABILITATION | Anchorage | 2023-03-01 | CSAPT00754 | CSAPT00754 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate concrete joints and panels. | Rehabilitate concrete joints and panels. | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  |  | (1) [on 2023.02.24 project was added.] | Napakiak Airport Surface Preservation Maintenance | Napakiak | 2023-03-01 | CFAPT01049 | CFAPT01049 | AIP 3-02-0188-XXX-2023 | Jeremy R Thompson | (907)269-0767 | This Federally Funded contract will provide all resources required to regrade the existing surfaces, and provide aggregate surface course on the runway, taxiway, and apron at the Napakiak Airport.
Central Region | (DELETED) |  |  |  | (1) [on 2023.02.24 project was added.] | SEWARD HIGHWAY MILE POINT 97.5 - 117 ( MILE POST 98.5-118) B | Anchorage | 2024-01-01 | Z566310000 | Z566310000 | 0A31034 | Tom J Schmid | (907)269-0543 | Construct safety and traffic flow improvements to the Seward Highway in the vicinity of Windy Corner and Rainbow Point. Project will address safety concerns due to wildlife viewing at Windy Corner. Scope includes highway improvements fromMP 105 to MP 109.5; the railroad will be relocated as necessary.Scope Revised 12/16: The project will provide improvements in the Windy Corner area of the Seward Highway to include highway realignment, auxiliary lanes,safety improvements, wildlife viewing turnouts, and railroad relocation as needed. Formerly named: Seward Hwy: MP 105-107, Windy Corner | The project will provide improvements in the Windy Corner area of the Seward Highway to include highway realignment, auxiliary lanes, safety improvements, wildlife viewing turnouts, and railroad relocation as needed. | Greater than $100,000,000
Central Region | ADDED |  |  |  |  | Juneau State Office Building Boiler Upgrades | City & Borough Of Juneau | 2023-03-01 | SPFAC00431 | SPFAC00431 | N/A | Christopher S Hodgin | (907)269-7484 | State funded project includes repairs and upgrades to the existing heating plant at the Juneau State Office Building. New installed work includes replacement of leaking sections of Boiler #1 and complete section replacement of Boiler #3, new burner installation, a new housekeeping pad and all supportive work as required. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | ANC UNDERGROUND UST REPLACEMENT GENERATORS AT NT, ST, & ARFF | Anchorage | 2023-04-01 | CSAPT00935 | CSAPT00935 | N/A | Jennifer C Pepin | (907)266-2549 | Replace the Underground Storage Tanks (USTs) for the emergency/standby generators at the North Terminal, South Terminal, and the Airport Fire and Police building that were all installed in 1998. The USTs will be replaced with Aboveground Storage Tanks (ASTs).
Central Region | ADDED |  |  |  |  | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2023-08-01 | CFHWY01083 | CFHWY01083 | N/A | Tom J Schmid | (907)269-0543 | Culvert replacement, drainage improvements, ditch grading, guardrail, signage, utility relocations, clearing and grubbing. This Child Project will construct the first phase of improvements included in the Parent Project CFHWY00592. . | Replacing 10 critical culverts along the Parks Highway. | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  | (2) [on 2022.05.16 project was added.]; [on 2022.07.12 the project was removed.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2024-02-01 | CFHWY00394 | CFHWY00394 | 0A15039 | Kristina H Busch | (907)269-0567 | Resurface the Glenn Highway from Kings River bridge to Cascade. Additional improvements may include bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities as necessary. Project construction may be phased. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | Big Lake | 2024-02-01 | CFHWY00392 | CFHWY00392 | 1686 | Alex L Read | (907)269-0641 | Pavement preservation, roadside hardware, structural improvement in limited areas, minor drainage and/or safety improvements, utility adjustment/relocation, signing and striping. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  | (2) [on 2022.05.16 project was added.]; [on 2022.08.14 the project was removed.] | HSIP: 5TH AVE: CONCRETE ST TO KARLUK ST PEDESTRIAN IMPROVMNT | Anchorage | 2024-02-01 | CFHWY00856 | CFHWY00856 | 421102 | Cynthia L Ferguson | (907)269-0693 | This HSIP project will construct a median barrier on 5th Avenue between Concrete Street and the couplet of 5th and 6th Avenues (Karluk Street). Work may include roadside hardware, drainage, improvements, and utilities.
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (5) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.11.17 the ANTADVDT changed to February 2023.] | (5) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.11.17 the ANTADVDT changed to February 2023.] | AMATS: HILAND RD MP 0 TO MP 3.2 PAVEMENT PRESERVATION | Eagle River | 2023-03-01 | CFHWY00568
Central Region | ANTADVDT | 2023-02-01 | 2023-04-01 |  | (1) [on 2022.11.17 project was added.] | ANC NORTH TERMINAL BAGGAGE HANDLING SYSTEM IMPROVEMENTS | Anchorage | 2023-04-01 | CSAPT00932
Central Region | ANTADVDT | 2023-02-01 | 2023-04-01 | (5) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to February 2023.] | (9) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 REGION changed.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 FEDNUM changed.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to February 2023.] | Cold Bay Airport Structure Removal | Cold Bay | 2023-04-01 | SFAPT00399
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (1) [on 2023.02.24 the ANTADVDT changed to February 2023.] | (2) [on 2022.12.17 project was added.]; [on 2023.02.24 the ANTADVDT changed to February 2023.] | JOE PARENT VOCATIONAL CENTER DEMOLITION & REMEDIATION | Aniak | 2023-03-01 | CFAPT00843
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (5) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to February 2023.] | (9) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 REGION changed.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 FEDNUM changed.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to February 2023.] | Kodiak Airport Structure Removal | Kodiak | 2023-03-01 | SFAPT00398
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (7) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | (8) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 PHONENUM changed.] | Mchugh RWIS Tower Upgrade | Municipality Of Anchorage | 2023-03-01 | CFHWY00428
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (4) [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.] | (5) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2023-03-01 | 25RC053613
Central Region | ANTADVDT | 2023-02-01 | 2023-06-01 | (1) [on 2022.03.15 the ANTADVDT changed to February 2023.] | (6) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2023-06-01 | Z512210000
Central Region | ANTADVDT | 2023-06-01 | 2023-09-01 | (3) [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.] | (4) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.] | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | Anchorage | 2023-09-01 | CFHWY00286
Central Region | DESCRIPTION | This project will design and construct 2 new singlee bay SRBEs to replace a exsiting and obsole SREB for the Kwethluk Airport | This project will design and construct 2 new single bay SREBs to replace an existing and obsolete SREB for the Kwethluk Airport. This project is anticipated to bid with the KWETHLUK AIRPORT REHABILITATION Project. |  | (1) [on 2023.02.24 project was added.] | KWETHLUK AIRPORT SREB | Kwethluk | 2023-03-01 | CFAPT00801
Central Region | ENGEST |  | Between $200,000 and $500,000 |  | (3) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-06-01 | CFHWY00883
Central Region | FEDNUM | 3-02-0000-027-2020 | 3-02-0019-014-2023 | (1) [on 2023.02.24 the ANTADVDT changed to February 2023.] | (2) [on 2022.12.17 project was added.]; [on 2023.02.24 the ANTADVDT changed to February 2023.] | JOE PARENT VOCATIONAL CENTER DEMOLITION & REMEDIATION | Aniak | 2023-03-01 | CFAPT00843
Central Region | PHONENUM | (907)269-0602 | (907)269-0623 | (1) [on 2023.02.24 the ANTADVDT changed to June 2023.] | (3) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-06-01 | CFAPT00993
Central Region | PHONENUM | (907)269-0602 | (907)269-0623 |  | (1) [on 2023.02.24 project was added.] | SELDOVIA AIRPORT IMPROVEMENTS | Seldovia | 2024-01-01 | CFAPT00937
Central Region | PROJMAN | Matthew H Hansen | Kim D Satterfield | (1) [on 2023.02.24 the ANTADVDT changed to June 2023.] | (3) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-06-01 | CFAPT00993
Central Region | PROJMAN | Matthew H Hansen | Kim D Satterfield |  | (1) [on 2023.02.24 project was added.] | SELDOVIA AIRPORT IMPROVEMENTS | Seldovia | 2024-01-01 | CFAPT00937
Northern Region | (DELETED) |  |  | (2) [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (6) [on 2022.08.14 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.02.24 PROJNAME changed.] | Fairbanks 5th Avenue Reconstruction | Fairbanks | 2023-03-01 | NFHWY00445 | NFHWY00445 | TA19(001) | Ivet Hall | (907)451-5386 | Reconstruct 5th Avenue between Barnette Street and Noble Street including ADA Improvements, intersection improvements, drainage improvements, roadside hardware, and utilities. |  | Between $2,500,000 and $5,000,000
Northern Region | (DELETED) |  |  |  | (5) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 FEDNUM changed.]; [on 2022.08.14 PROJNAME changed.] | Buckland Airport Improvements | Buckland | 2023-06-01 | NFAPT00604 | NFAPT00604 | 3-02-0399-___-____ | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate the runway and taxiway, stabilize the embankments, resurface the airport access road, apply dust palliative, and replace the airport lighting system. |  | Between $5,000,000 and $10,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.02.22 the ANTADVDT changed to July 2022.] | (3) [on 2022.02.22 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.] | Deering Airport Improvements | Deering | 2023-06-01 | NFAPT00249 | NFAPT00249 | 3-02-0400-XX-202X | Jonathan J Hutchinson | (907)451-5479 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDLINFO |  | The Department is currently considering using design-build to deliver this project. | (2) [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (4) [on 2022.01.18 project was added.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2022.10.20 PROJNAME changed.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-03-01 | Z607150000
Northern Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (3) [on 2022.10.20 the ANTADVDT changed to December 2022.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to March 2023.] | (5) [on 2022.06.15 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2022.10.20 the ANTADVDT changed to December 2022.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to March 2023.] | Edgerton Highway MP 24 - 29 Resurfacing | Mccarthy | 2023-04-01 | NFHWY00587
Northern Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (4) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (6) [on 2022.05.16 project was added.]; [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.11.17 FEDNUM changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | Northern Region ADA Improvements - Fairbanks: College Road | Fairbanks | 2023-04-01 | NFHWY00591
Northern Region | ANTADVDT | 2023-03-01 | 2023-11-01 | (1) [on 2022.12.17 the ANTADVDT changed to March 2023.] | (6) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2023-11-01 | Z631860000
Northern Region | ANTADVDT | 2023-11-01 | 2024-01-01 |  | (3) [on 2022.06.15 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.02.24 ENGEST changed.] | ELLIOTT HIGHWAY MP 18 - 29 RESURFACING | Livengood | 2024-01-01 | NFHWY00588
Northern Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 |  | (3) [on 2022.06.15 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.02.24 ENGEST changed.] | ELLIOTT HIGHWAY MP 18 - 29 RESURFACING | Livengood | 2024-01-01 | NFHWY00588
Northern Region | PROJNAME | ELLIOTT HWY MP 51-63 REHABILITATION | Elliott Highway Milepost 51-63 Rehabilitation | (1) [on 2023.01.17 the ANTADVDT changed to March 2023.] | (2) [on 2022.05.16 project was added.]; [on 2023.01.17 the ANTADVDT changed to March 2023.] | Elliott Highway Milepost 51-63 Rehabilitation | Livengood | 2023-03-01 | NFHWY00420
Northern Region | PROJNAME | FAST AREA SURFACE UPGRADES FFY2023 | FAST Area Surface Upgrades FFY2023 | (2) [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.12.17 the ANTADVDT changed to April 2023.] | (7) [on 2022.03.15 project was added.]; [on 2022.06.15 ADDLINFO changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 FEDNUM changed.]; [on 2023.02.24 ENGEST changed.] | FAST Area Surface Upgrades FFY2023 | Fairbanks North Star Borough | 2023-04-01 | NFHWY00633
Southcoast Region | (DELETED) |  |  | (3) [on 2022.04.15 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | (6) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the ANTADVDT changed to September 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 ENGEST changed.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.] | POW HOLLIS HWY GUARDRAIL SAFETY IMPROVEMENTS HSIP | Prince Of Wales Island | 2023-02-01 | SFHWY00306 | SFHWY00306 | 3260 | Nathan A Purves | (907)465-4521 | Determine the extent of the zone where we can expect a driver to recover control of there vehicle and remove/replace downstream guardrail end anchors that fall in that zone with guardrail parallel end terminals that are compliant with the Manual for Assessing Safety Hardware 16 (MASH16). |  | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.01.17 project was added.] | FFY23 HNS AP SPM PAVEMENT MARKINGS | Haines | 2023-03-01 | SFAPT00421 | SFAPT00421 | N/A | David B Epstein | (907)465-4483 | Repaint pavement markings on the runway, taxiway, and apron
Southcoast Region | (DELETED) |  |  |  | (1) [on 2022.08.14 project was added.] | KING SALMON AIRPORT RWY 18-36 AND GA APRON PVMNT REHAB PROJ | King Salmon | 2023-07-01 | SFAPT00362 | SFAPT00362 | N/A | Peter J Jackson | (907)465-4439 | Repave Runway 18-36 and Taxiways C,D,M, Terminal and GA Apron. Remove aligned taxiway on runway 36 |  | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  |  | (5) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2023.01.17 PHONENUM changed.]; [on 2023.01.17 PROJMAN changed.] | KING SALMON AIRPORT PERIMETER FENCING UPGRADES | King Salmon | 2023-08-01 | SFAPT00124 | SFAPT00124 | N/A | David B Epstein | (907)465-4483 | Replace/upgrade access controls/gates to meet 49 CFR 1542 requirements. Replace existing fencing as needed. | Construct perimeter fencing and gate upgrades. Upgrades include providing new automatic vehicle gates and pedestrian gates with electric lock gate systems. | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  | (2) [on 2022.02.22 DESCRIPTION changed.]; [on 2022.09.13 the project was removed.] | JNU KAXDIGOOWU HEEN DEI IMP (BROTHERHOOD BRIDGE TRAIL IMP) | Juneau | 2023-04-01 | SFHWY00259 | SFHWY00259 | TA18010 | Peter J Jackson | (907)465-4439 | This project will design and improve the Kaxdigoowu Heen Dei (Kax) Trail from River Road to the edge of Brotherhood Meadow, where a re-route planned for construction in 2019 would end, Work will primarily consist of selected areas of subgrade repair, repave the trail, The pedestrian bridge at Montana Creek will be replaced to provide a larger span that allows for some natural stream movement and can withstand emergency and maintenance vehicle use, and the banks armored to increase the expected useful life of the bridge. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  | (3) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.] | (7) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2023-05-01 | SFHWY00186 | SFHWY00186 | 3244 | Nathan A Purves | (907)465-4521 | Provide additional illumination at the Stedman/Deermount intersection to achieve a level of luminance that meets current DOT&PF standards. Construct a concrete sidewalk bulbout on the Stedman side of the marked crosswalk. The bulbout will extend from the existing sidewalk to the edge of the traveled way. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | FFY20 VAR NON-PRIMARY VISUAL AID REPLACEMENT | Regionwide | 2023-08-01 | SFAPT00250 | SFAPT00250 | 3-02-0200-132-2020 | Peter J Jackson | (907)465-4439 | Remove the existing airport beacon and tower and replace with new beacon and tip down tower.
Southcoast Region | ADDED |  |  | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (4) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2022.09.13 the project was removed.] | CRAIG ADA IMPROVEMENTS | Craig | 2024-02-01 | SFHWY00377 | SFHWY00377 | 3274 | Bran P Pollard | (907)465-4526 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  |  | JNU L00P RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | Juneau | 2024-02-01 | SFHWY00403 | SFHWY00403 | 966030 | Nathan A Purves | (907)465-4521 | Construct a single-lane roundabout at the Loop Road - Mendenhall Boulevard - Valley Boulevard intersection.
Southcoast Region | ADDED |  |  |  | (7) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-02-01 | SFAPT00178 | SFAPT00178 | N/A | Gregory K Lockwood | (907)465-2393 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
Southcoast Region | ANTADVDT | 2023-02-01 | 2023-03-01 |  | (1) [on 2023.01.17 project was added.] | SE District Hwy Painting FFY23 - NHS | Regionwide | 2023-03-01 | SFHWY00463
Southcoast Region | ANTADVDT | 2023-02-01 | 2023-03-01 |  | (1) [on 2023.01.17 project was added.] | SR Airport Pavement Markings FFY23 | Regionwide | 2023-03-01 | SFAPT00289-1
Southcoast Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (5) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (6) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2023-04-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2023-04-01 | 2023-10-01 | (2) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.] | (6) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2023-10-01 | SFHWY00103
Southcoast Region | ANTADVDT | 2023-07-01 | 2023-11-01 | (8) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.] | (9) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2023-11-01 | Z680850000
Southcoast Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (2) [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.] | (6) [on 2022.09.13 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2024-01-01 | SFHWY00326
Southcoast Region | ANTADVDT | 2023-11-01 | 2023-12-01 | (5) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.] | (13) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-12-01 | SFHWY00359
Southcoast Region | DESCRIPTION | Replace 10 vehicle (nos. 1, 2, 3, 7, 8, 11, 13, 16, 17, and 20) and 4 pedestrian (nos. 4, 6, 12, and 15) access points. Provide card reader access to pedestrian gate nos. 4, 6, 12 and 15, and all three doors to the ARFF Building. Provide card reader access points to vehicle gates 2, 7, 13, and 16. Repair approximately 1200-1500 feet of fence line, permanently remove/fence over vehicle gate nos. 5, 10, 18, and 19. Permanently remove/fence over pedestrian gate nos. 9 and 14. | Replace automated vehicle gate 3; Replace and widen vehicle gate 9 from 20' to 24'; Replace non-automated vehicle gate 10; Replace locking systems for vehicle gates 3 and 9; Replace locking systems for fence pedestrian gates 4 and 11; Remove vehicle gates 5 and 6 and replace with fence; Replace and relocate pedestrian gate 11; Repair approximately 1200-1500 feet of fence line. | (2) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.] | (8) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2023-09-01 | SFAPT00412