## 2023.04.14 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (6) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | (6) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | AMATS: HILAND RD MP 0 TO MP 3.2 PAVEMENT PRESERVATION | Eagle River | 2023-03-01 | CFHWY00568 | CFHWY00568 | 1663 | Galen K Jones | (907)269-0550 | Resurface Hiland Road, including milling, paving, minor subgrade rehabilitation, drainage improvements, updating guardrail and sign posts to meet current safety standards, replacing striping and select signage, curb and gutter, lighting, and roadside signal and or traffic data hardware. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (7) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.10.20 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (12) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.]; [on 2022.10.20 the ANTADVDT changed to January 2023.]; [on 2022.10.20 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2022.12.17 FEDNUM changed.]; [on 2022.12.17 PROJNAME changed.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | ANC TAXIWAY Z WEST IMPROVEMENTS | Anchorage | 2023-03-01 | CFAPT00465 | CFAPT00465 | 3-02-0016-218-2023 | Philip W Cheasebro | (907)269-0606 | This Federally Funded contract provides geometric upgrades as necessary to accommodate larger ADG VI, TDG 6 aircraft. The proposed geometric upgrades include widening Taxiway's Z & E, constructing a new entrance Taxiway R, and rehabilitating Taxilane's R & E. Additional work includes: • Rehabilitate or relocate existing private taxilane approaches as needed • Remove TW F entrance taxiway • Relocate existing service road • Drainage improvements • Replace taxiway lighting and sign and install new lights and signs as needed • Relocate/adjust utilities as needed • Relocate/adjust FAA NAVAIDS as needed | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/CFAPT00465 ANC Taxiway Z Improvements West - Phase 1 - PrePSE.pdf ">Preliminary Plans (~46 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $40,000,000 and $50,000,000
Central Region | (DELETED) |  |  | (4) [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.] | (10) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.07.12 ENGEST changed.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to January 2023.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.01.17 FEDNUM changed.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2023-03-01 | CFAPT00855 | CFAPT00855 | 3-02-0016-XXX-2023 | Jennifer M Lombardo | (907)266-2731 | Rehabilitate the apron surface. Project will include striping and drainage improvements. | Rehabilitate Apron Surface | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (2) [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (4) [on 2022.11.17 project was added.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 FEDNUM changed.] | CHIGNIK AIRPORT SREB REHAB | Chignik | 2023-03-01 | SFAPT00368 | SFAPT00368 | 3-02-0330-002-2023 | Alyson K Wardell | (907)269-0869 | Damaged panels and doors are allowing weather and wildlife access to building interior, damaging equipment and shortening the life of the building. This project will replace the metal wall panels and the man door and its frame, to protect the snow removal equipment and extend the life of the building. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (2) [on 2023.02.24 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | (4) [on 2022.12.17 project was added.]; [on 2023.02.24 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.]; [on 2023.03.15 FEDNUM changed.] | JOE PARENT VOCATIONAL CENTER DEMOLITION & REMEDIATION | Aniak | 2023-03-01 | CFAPT00843 | CFAPT00843 | 3-02-0019-014-2023 | Eric F Hershey | (907)269-5572 | This federally funded project will remediate, demolish and remove the existing Joe Parent Vocational Center building, a well house including decommissioning of water well, a 90,000 gallon aboveground water tank and associated pump house building, underground and aboveground fuel storage tanks, utilities work, and any other debris, obstructions, and improvements, in Aniak, Alaska as described in the contract documents. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  |  | (1) [on 2023.03.15 project was added.] | Juneau State Office Building Boiler Upgrades | City & Borough Of Juneau | 2023-03-01 | SPFAC00431 | SPFAC00431 | N/A | Christopher S Hodgin | (907)269-7484 | State funded project includes repairs and upgrades to the existing heating plant at the Juneau State Office Building. New installed work includes replacement of leaking sections of Boiler #1 and complete section replacement of Boiler #3, new burner installation, a new housekeeping pad and all supportive work as required. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (6) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | (10) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 REGION changed.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 FEDNUM changed.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | Kodiak Airport Structure Removal | Kodiak | 2023-03-01 | SFAPT00398 | SFAPT00398 | AIP 3-02-0000-027-2020 | Jesse Campbell | (907)266-2723 | This federally funded project includes demolition and removal of existing buildings, removal of existing fencing, existing tank removal, and utility work in Kodiak, Alaska as indicated in the contract documents. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (8) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | (9) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 PHONENUM changed.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | Mchugh RWIS Tower Upgrade | Municipality Of Anchorage | 2023-03-01 | CFHWY00428 | CFHWY00428 | 0106(094) | John W Turley | None | RWIS facilities must be migrated off of the existing tower at McHugh MP 111.8 of the Seward Highway. The existing tower will be demolished and a new tower will be installed within DOT ROW. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (2) [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | (4) [on 2022.02.22 PHONENUM changed.]; [on 2022.03.15 ENGEST changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | Colleen Street Intersection and Frontage Road | Palmer | 2023-04-01 | CFHWY00006 | CFHWY00006 | 0A15033 | Sean M Baski | (907)269-0566 | Construct improvements to the Glenn Highway and South Colleen Street intersection, and improve connectivity and access. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00431/00431_Plans.pdf">Preliminary Plans (~37 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (2) [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | (3) [on 2022.02.22 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | Glenn Hwy: Parks Hwy to S. Inner Springer Lp. (Phase II) | Palmer | 2023-04-01 | CFHWY00431 | CFHWY00431 | 0A15037 | Sean M Baski | (907)269-0566 | This project will reconstruct the Glenn Highway from the Parks Highway to S. Inner Springer Loop as a four-lane divided highway. Project work will add lanes, widen shoulders, add turn lanes and frontage roads, signals, illumination, other traffic safety related improvements. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00431/00431_Plans.pdf">Preliminary Plans (~54 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  | (2) [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | (3) [on 2022.02.22 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | Glenn Hwy: Parks to S. Inner Springer Lp. Pathway (Phase II) | Palmer | 2023-04-01 | CFHWY00432 | CFHWY00432 | 0A15038 | Sean M Baski | (907)269-0566 | This project will construct a pathway along the Glenn Highway and other roads. It also includes roadside hardware and drainage, intersection, and ADA improvements. This project will construct the second phase of the Glenn Hwy: Mile Post 34-42 Parks to Old Glenn Pathway project. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00431/00431_Plans.pdf">Preliminary Plans (~54 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> Please note, this project will be advertising with project number CFHWY00431. | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (4) [on 2022.02.22 the ANTADVDT changed to September 2022.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.11.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.] | (12) [on 2022.02.22 the ANTADVDT changed to September 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.] | TAKOTNA RIVER BRIDGE REPLACEMENT | Takotna | 2023-04-01 | CFHWY00129 | CFHWY00129 | 1569 | Steven J Rzepka | (907)269-0592 | This Project replaces the Takotna River Bridge (bridge #0463). Project includes bridge work, roadway resurfacing, roadside hardware, drainage improvements, and utilities. | Replacement of the Takotna River Bridge (bridge #0463). May include bridge work, roadside hardware, drainage improvements, and utilities. Project will advertise with Z516210000 Takotna: Gold Creek Bridge & Tatalina Bridge Replacement. <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00129_51621/00129_Plans.pdf">Preliminary Plans (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (3) [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.11.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.] | (10) [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.04.15 PROJMAN changed.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.] | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT | Takotna | 2023-04-01 | Z516210000 | Z516210000 | 000S783 | Steven J Rzepka | (907)269-0592 | The Alaska Department of Transportation and Public Facilities (DOT&PF) in cooperation with the Federal Highway Administration (FHWA) proposes to replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge #462. | Replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge. Will advertise with CFHWY00129 Takotna River Bridge Replacement. <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00129_51621/51621_Plans.pdf">Preliminary Plans (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $5,000,000 and $10,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2022.12.17 project was added.] | Willow Airport (UUO) Surface Preservation Maintenance (SPM) | Willow | 2023-05-01 | 22-25-1-005 | 22-25-1-005 | CFAPT00811 / 3-02-0320-XXX-2022 | Jeremy R Thompson | (907)269-0767 | Provide and compact CASC on runway, taxiways and service areas to replace deteriorated surfacing material. Apply dust palliative to retain the critical fine particles in the crushed surfacing. To be treated with dust palliative for fines preservation to bind aggregate to prevent loss of fines for RWY 13/31 (4,400 LF), Service Area Taxiway (3,365 LF), East/West Taxiway (570 LF), South Taxiway (796 LF) and apron (30,321 SY).
Central Region | ADDED |  |  |  |  | ANC Gate N7 Passenger Boarding Bridge Replacement Design-Build | Anchorage | 2023-04-01 | CFAPT01076 | CFAPT01076 | AIP 3-02-0016-XXX-2023 | Jesse Campbell | (907)266-2723 | Install a new passenger boarding bridge (PBB) at gate N7 in the North Terminal (NT) including new foundation along with mechanical and electrical upgrades. Existing PBB will be removed and disposed. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | Peninsula District Paving | Kenai Peninsula Borough | 2023-04-01 | 23-25-1-002 | 23-25-1-002 | N/A | Vernon S Vreeland | (907)269-0778 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Kenai Peninsula District Boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  |  | AMATS: DOWNTOWN TRAIL CONNECTION | Anchorage | 2024-03-01 | CFHWY00586 | CFHWY00586 | 1662 | Kristina H Busch | (907)269-0567 | Project will construct a connection between the Tony Knowles Coastal Trail to the Ship Creek Trail in downtown Anchorage. Major Project Elements include Bridge Work (Pedestrian), Roadside Hardware, Drainage Improvements, Intersection Improvements and ADA Improvements.
Central Region | ADDED |  |  |  |  | ANC TAXIWAY R NORTH IMPROVEMENTS | Anchorage | 2024-03-01 | CFAPT00880 | CFAPT00880 | N/A | Matthew H Hansen | (907)269-0602 | This project will design and construct improvements for TW R from approximately TL P to TW Q for Airplane Design Group 6. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  | (1) [on 2022.11.17 the ANTADVDT changed to August 2023.] | (3) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the project was removed.] | CHEVAK AIRPORT REHABILITATION | Chevak | 2024-03-01 | Z537250000 | Z537250000 | 3-02-0468-00X-202X | Aaron C Hughes | (907)269-0523 | This project will rehabilitate the runway, taxiway, apron, and airport access road. The runway safety area will be expanded, and runway grades will be corrected to meet line-of-sight requirements. Additional improvements include replacement of airfield lighting, FAA navaids, wind cones, segmented circle, build a supplemental wind cone access, and apply dust palliative. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  | (2) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.] | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2024-03-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Cynthia L Ferguson | (907)269-0693 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards.
Central Region | ADDED |  |  |  | (2) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2024-03-01 | CFHWY00503 | CFHWY00503 | 1644 | Cynthia L Ferguson | (907)269-0693 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements.
Central Region | ADDED |  |  |  |  | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-03-01 | CFHWY01084 | CFHWY01084 | N/A | Tom J Schmid | (907)269-0543 | New bridge, drainage improvements, ditch grading, guardrail, signage, utility relocations, clearing and grubbing. This Child Project will construct the second phase of improvements included in the Parent Project CFHWY00592. | Construct a bridge at Railroad Creek at MP128.5 along the Parks Highway. | Between $5,000,000 and $10,000,000
Central Region | ADDLINFO | <img name="pdf_icon" src="/library/button_images/pdf_icon.gif" width="30" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/8_CFAPT00682_KWT-Plans_PS&E%20Review%20DRAFT.pdf">Preliminary Plans (~20 Mb) </a><br><img name="pdf_icon" src="/library/button_images/pdf_icon.gif" width="30" height="18" border="0"> | <a class=linkcopy href="https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/8_CFAPT00682_KWT-Plans_PS&E%20Review%20DRAFT.pdf">Preliminary Plans (~20 Mb) </a><br> | (1) [on 2022.10.20 the ANTADVDT changed to March 2023.] | (7) [on 2022.06.15 project was added.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.08.14 ENGEST changed.]; [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.11.17 FEDNUM changed.]; [on 2023.02.24 ADDLINFO changed.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-04-01 | CFAPT00682
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (1) [on 2022.10.20 the ANTADVDT changed to March 2023.] | (7) [on 2022.06.15 project was added.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.08.14 ENGEST changed.]; [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.11.17 FEDNUM changed.]; [on 2023.02.24 ADDLINFO changed.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-04-01 | CFAPT00682
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 |  | (2) [on 2023.02.24 project was added.]; [on 2023.03.15 DESCRIPTION changed.] | KWETHLUK AIRPORT SREB | Kwethluk | 2023-04-01 | CFAPT00801
Central Region | ANTADVDT | 2023-03-01 | 2023-05-01 | (1) [on 2023.02.24 the ANTADVDT changed to March 2023.] | (2) [on 2023.01.17 project was added.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | Mat-Su High Tower Repairs | Matanuska-Susitna Borough | 2023-05-01 | 23-25-1-001
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 |  | (1) [on 2023.02.24 project was added.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2023-04-01 | 25RC053608
Central Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (5) [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | (6) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2023-04-01 | 25RC053613
Central Region | ANTADVDT | 2023-04-01 | 2023-07-01 | (3) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | (7) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2023-07-01 | CFHWY00253
Central Region | ANTADVDT | 2023-04-01 | 2023-07-01 |  | (1) [on 2023.02.24 project was added.] | SEWARD HWY STERLING HWY INTERSECTION IMPROVEMENTS | Cooper Landing | 2023-07-01 | CFHWY00943
Central Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (3) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.] | (3) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.] | MEKORYUK AIRPORT REHABILITATION | Mekoryuk | 2023-06-01 | CFAPT00288
Central Region | ANTADVDT | 2023-06-01 | 2023-09-01 | (2) [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to June 2023.] | (6) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2022.10.20 PHONENUM changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-09-01 | CFHWY00012
Central Region | DESCRIPTION | Rehabilitate the airport runway, taxiway, safety areas, apron and access road. Replace lighting, nav-aids, and improve drainage. Remove OFA obstructions. | This project will reshape the airport embankment, resurface the airport operating surfaces (runway, taxiway and apron) and access road, and replace the airfield lighting system and electrical enclosure building. Other improvements include clearing and grubbing, replacing culverts, signs, wind cones, segmented circle, aircraft tie downs, rotating beacon, applying dust palliative, and replacing one Snow Removal Equipment Building (SREB) with two heated SREBs including supplemental infrastructure. Utility work will include replacing the power pole and overhead electric line east of the apron. FAA PAPI and REIL underground system and foundations will be replaced, pads resurfaced, and the equipment will be reused. | (1) [on 2022.10.20 the ANTADVDT changed to March 2023.] | (7) [on 2022.06.15 project was added.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.08.14 ENGEST changed.]; [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.11.17 FEDNUM changed.]; [on 2023.02.24 ADDLINFO changed.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-04-01 | CFAPT00682
Central Region | ENGEST |  | Between $1,000,000 and $2,500,000 |  | (1) [on 2023.03.15 project was added.] | ANC UNDERGROUND STORAGE TANK REPLACEMENT | Anchorage | 2023-04-01 | CSAPT00935
Central Region | FEDNUM | N/A | 3-02-0435-002-2023 |  | (2) [on 2023.02.24 project was added.]; [on 2023.03.15 DESCRIPTION changed.] | KWETHLUK AIRPORT SREB | Kwethluk | 2023-04-01 | CFAPT00801
Central Region | PROJNAME | ANC UNDERGROUND UST REPLACEMENT GENERATORS AT NT, ST, & ARFF | ANC UNDERGROUND STORAGE TANK REPLACEMENT |  | (1) [on 2023.03.15 project was added.] | ANC UNDERGROUND STORAGE TANK REPLACEMENT | Anchorage | 2023-04-01 | CSAPT00935
Marine Highways | ADDED |  |  |  |  | AMHS JNU AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | Juneau | 2024-01-01 | SAMHS00419 | SAMHS00419 | 933048 | Misty L Butler | (907)465-4414 | Make improvements to the AMHS Auke Bay Terminal East Berth. Work would include: Replacement of mooring dolphins, refurbish/replace transfer bridge and support float, install mechanical and electrical upgrades. |  | Between $5,000,000 and $10,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.02.24 project was added.] | Alaska Highway Gerstle River Bridge #520 Replacement | Northern Region | 2023-03-01 | NFHWY00653 | NFHWY00653 | 0A22009 | Sarah J Schlichting | (907)451-2041 | Replace the Gerstle River Bridge #520 located on the Alaska Highway at MP 1393. Project includes drainage improvements, road reconstruction, roadside hardware, and utilities. | This project will be advertised as a CMGC. See project website for additional project information: https://alaska-hwy-bridge-replacements-akdot.hub.arcgis.com/. Project will be combined with NFHWY00743 Alaska Highway Johnson River Bridge #518 Replacement for CMGC advertising. | Between $50,000,000 and $60,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.02.24 project was added.] | Alaska Highway Johnson River Bridge #518 Replacement | Delta Junction | 2023-03-01 | NFHWY00743 | NFHWY00743 | 0A22008 | Sarah J Schlichting | (907)451-2041 | Replace Johnson River Bridge #518 on the Alaska Highway at MP 1380. Project includes drainage improvements, roadside hardware, and utilities. | This project will be advertised as a CMGC. See project website for additional project information: https://alaska-hwy-bridge-replacements-akdot.hub.arcgis.com/. Project will be combined with NFHWY00653 Alaska Highway Gerstle River Bridge #520 Replacement for CMGC advertising. | Between $30,000,000 and $40,000,000
Northern Region | (DELETED) |  |  |  | (5) [on 2022.06.15 project was added.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 FEDNUM changed.]; [on 2022.12.17 PROJNAME changed.]; [on 2023.02.24 ENGEST changed.] | FIA GA Apron and Taxiway Reconstruction | Fairbanks North Star Borough | 2023-03-01 | NFAPT00689 | NFAPT00689 | 3-02-0096-__-____ | RJ Stumpf | (907)474-2587 | Reconstruct the general aviation apron and associated taxiways, replace taxiway lighting, and other improvements. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.02.24 project was added.] | Richardson Highway NB Chena Flood Control Bridge #1364 Replacement | North Pole | 2023-03-01 | NFHWY00782 | NFHWY00782 | 0A24035 | Jennifer J Wright | (907)371-8949 | Replace the Northbound Chena Flood Control Bridge #1364 on the Richardson Highway at MP 346. Project will include drainage improvements, roadside hardware, and utilities. | This project will be advertised as a CMGC. See project website for additional project information: https://richardson-highway-mp-346-nb-bridge-1346-replacement-akdot.hub.arcgis.com/. Project will be combined with NFHWY00781 Steese Hwy MP 5 CHSR Undercrossing Bridge Replacement for CMGC advertising. | Between $20,000,000 and $30,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.02.24 project was added.] | STEESE HWY MP 5 BRIDGE #1342 REPLACEMENT | Fairbanks North Star Borough | 2023-03-01 | NFHWY00781 | NFHWY00781 | 670046 | Jennifer J Wright | (907)371-8949 | Replace Bridge #1342, Chena Hot Springs Undercrossing at Steese Highway MP 5. Project includes drainage improvements, roadside hardware, and utilities. | This project will be advertised as a CMGC. See project website for additional project information: https://steese-highway-mp-5-bridge-1342-replacement-akdot.hub.arcgis.com/. Project will be combined with NFHWY00782 Richardson Hwy NB Flood Control Bridge Replacement for CMGC advertising. | Between $5,000,000 and $10,000,000
Northern Region | (DELETED) |  |  | (3) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2022.]; [on 2023.02.24 the ANTADVDT changed to April 2023.] | (6) [on 2022.05.16 project was added.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.08.14 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to January 2022.]; [on 2023.02.24 the ANTADVDT changed to April 2023.] | East College Road Resurfacing | Fairbanks | 2023-04-01 | NFHWY00645 | NFHWY00645 | 640013 | Russell M Johnson | (907)451-5059 | Resurface College Road between the Margaret/Antoinette and Old Steese Highway intersections including the College Road/Johansen Expressway Interchange on and off ramps. Project will include ADA and drainage improvements, pavement preservation, roadside hardware, and utilities. | Project is anticipated to be combined with NFHWY00591 Northern Region ADA Improvements - Fairbanks: College Road | Between $5,000,000 and $10,000,000
Northern Region | (DELETED) |  |  | (5) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.] | (7) [on 2022.05.16 project was added.]; [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.11.17 FEDNUM changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.] | Northern Region ADA Improvements - Fairbanks: College Road | Fairbanks | 2023-04-01 | NFHWY00591 | NFHWY00591 | PENDING | Ivet Hall | (907)451-5386 | Reconstruct pedestrian facilities and adjacent areas on sections of College Road in Fairbanks. Project includes drainage improvements. | Project is anticipated to be combined with NFHWY00645 East College Road Resurfacing. | Between $1,000,000 and $2,500,000
Northern Region | ADDLINFO | The Department is currently considering using design-build to deliver this project. |  | (2) [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (5) [on 2022.01.18 project was added.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2022.10.20 PROJNAME changed.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 ADDLINFO changed.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-04-01 | Z607150000
Northern Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (1) [on 2023.01.17 the ANTADVDT changed to March 2023.] | (3) [on 2022.05.16 project was added.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 PROJNAME changed.] | Elliott Highway Milepost 51-63 Rehabilitation | Livengood | 2023-04-01 | NFHWY00420
Northern Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (2) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (4) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-04-01 | Z768840000
Northern Region | ANTADVDT | 2023-03-01 | 2023-04-01 | (2) [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (5) [on 2022.01.18 project was added.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2022.10.20 PROJNAME changed.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 ADDLINFO changed.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-04-01 | Z607150000
Northern Region | ANTADVDT | 2023-04-01 | 2023-05-01 | (1) [on 2023.01.17 the ANTADVDT changed to April 2023.] | (5) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.] | HSIP: Old Steese Highway Shoulder Widening | Fox | 2023-05-01 | NFHWY00527
Northern Region | ANTADVDT | 2023-06-01 | 2023-05-01 |  | (5) [on 2022.07.12 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.11.17 FEDNUM changed.]; [on 2022.11.17 PROJNAME changed.] | Little Diomede Helipad Improvements | Diomede | 2023-05-01 | Z614700000
Northern Region | FEDNUM | 3-02-0399-___-____ | 3-02-0381-___-____ |  | (5) [on 2022.07.12 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.11.17 FEDNUM changed.]; [on 2022.11.17 PROJNAME changed.] | Little Diomede Helipad Improvements | Diomede | 2023-05-01 | Z614700000
Southcoast Region | ADDED |  |  | (3) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.] | (7) [on 2022.01.18 ENGEST changed.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the project was removed.] | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | Hoonah | 2024-03-01 | SFAPT00236 | SFAPT00236 | N/A | Loren K Gehring | (907)465-8189 | Relocation of an existing stream bed and conduct dredging under the seaplane mooring float to restore sufficient water depths and/or relocation of the seaplane float structure to deeper water at the same location. Phase: T02000 - Par - All Costs | Construction funding uncertain. | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  | (4) [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.02.24 the project was removed.] | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | Kodiak | 2024-03-01 | SFHWY00260 | SFHWY00260 | 3247 | Bran P Pollard | (907)465-4526 | Resurface Rezanoff Drive from Marine Way to the airport. Associated preventative maintenance activities may include minor structural section improvements, drainage repairs, lighting and signals, striping, signs, and ADA improvements. Project Location and Length: Rezanoff Drive from Marine Way to the airport for an approximate length of 4.70 miles. | (Design by Northern Region) | Between $10,000,000 and $20,000,000
Southcoast Region | ANTADVDT | 2023-03-01 | 2023-05-01 | (3) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (4) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.06.15 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2023-05-01 | Z680910000
Southcoast Region | ANTADVDT | 2023-04-01 | 2023-05-01 |  | (3) [on 2022.02.22 DESCRIPTION changed.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.] | JNU KAXDIGOOWU HEEN DEI IMP (BROTHERHOOD BRIDGE TRAIL IMP) | Juneau | 2023-05-01 | SFHWY00259
Southcoast Region | ANTADVDT | 2023-04-01 | 2023-05-01 | (6) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.] | (7) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2023-05-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2023-04-01 | 2023-05-01 | (1) [on 2023.02.24 the ANTADVDT changed to April 2023.] | (4) [on 2022.11.17 project was added.]; [on 2022.12.17 ADDLINFO changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 ENGEST changed.] | NECK LAKE ROAD RECONSTRUCTION SEGMENT 2 WFLHD | Prince Of Wales Island | 2023-05-01 | SFHWY00375
Southcoast Region | ANTADVDT | 2023-09-01 | 2023-12-01 | (2) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.] | (9) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2023-12-01 | SFAPT00412