## 2023.06.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (2) [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.] | (3) [on 2022.11.17 project was added.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.] | 500 Hollywood Drive Structures Removal | Central Region | 2023-05-01 | z537350000 | z537350000 | N/A | None | None | This federally funded contract includes the removal and disposal or salvage of all buildings, foundations, fences, structures, old pavements, and any other obstructions and improvements at 500 Hollywood Drive, located in Anchorage, Alaska: |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  |  | (1) [on 2023.05.15 project was added.] | ANC NORTH TERMINAL BAGGAGE HANDLING SYSTEM IMPROVEMENTS | Anchorage | 2023-05-01 | CFAPT01087 | CFAPT01087 | AIP 3-02-0016-XXX-2023 | Jennifer C Pepin | (907)266-2549 | The Work of this federally funded project includes all necessary construction services as required to construct improvements to the baggage handling system at the Ted Stevens Anchorage International Airport North Terminal. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (2) [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.] | (5) [on 2022.08.14 project was added.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 ENGEST changed.] | ANC POSTMARK DRIVE REPAIRS 2023 | Anchorage | 2023-05-01 | CSAPT00984 | CSAPT00984 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate the pavement on Postmark Drive from West Northern Lights Boulevard to approximately Taxiway Uniform Tug Road intersection. Project includes pavement planning, paving, and striping. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (1) [on 2023.05.15 the ANTADVDT changed to May 2023.] | (2) [on 2023.02.24 project was added.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | ANC RON 3 & 4 REHABILITATION | Anchorage | 2023-05-01 | CFAPT01064 | CFAPT01064 | 3-02-0016-XXX-2023 | Jennifer M Lombardo | (907)266-2731 | Rehabilitions the concrete surface on hardstands RON 3 & 4. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (4) [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (6) [on 2022.10.20 project was added.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2023-05-01 | CFAPT00983 | CFAPT00983 | 3-02-0016-XXX-2023 | Jennifer M Lombardo | (907)266-2731 | Remove and replace approximately 1,000 feet of security fence along the northeast edge of the airfield. Project includes clearing, grubbing, embankment extension and replacing swing gates. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (1) [on 2023.02.24 the ANTADVDT changed to May 2023.] | (7) [on 2022.09.13 project was added.]; [on 2023.02.24 ADDLINFO changed.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.02.24 PROJNAME changed.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.] | BETHEL TUNDRA RIDGE ROAD | Bethel | 2023-05-01 | Z542890000 | Z542890000 | 1207 | Kelly L Summers | (907)269-6235 | Resurface Tundra Ridge Rd, a distance of about 5,500 feet. |  | Between $5,000,000 and $10,000,000
Central Region | (DELETED) |  |  | (2) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (5) [on 2022.11.17 project was added.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 REGION changed.] | Lemon Creek Correctional Center Structural Repairs CM/GC | Juneau | 2023-05-01 | 25C2023065 | 25C2023065 | N/A | Jesse Campbell | (907)266-2723 | This State funded project will provide structural repairs, drainage improvements, interior renovations, and ancillary systems upgrades at the Lemon Creek Correctional Center in Juneau, AK. An optional second phase to provide a new maximum security housing module may be included if funding becomes available. |  | Between $5,000,000 and $10,000,000
Central Region | (DELETED) |  |  | (2) [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (3) [on 2023.01.17 project was added.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | Mat-Su High Tower Repairs | Matanuska-Susitna Borough | 2023-05-01 | 23-25-1-001 | 23-25-1-001 | CFHWY00972 | Vernon S Vreeland | (907)269-0778 | The Contractor shall provide labor, equipment, materials, components, tools, traffic control, mobilization, demobilization and all other incidentals necessary to replace damaged components on high towers and to retrofit lighting to LED as shown in Appendixes and the specifications. Work includes lowering and raising high towers. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  |  | (3) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.] | SEWARD AIRPORT IMPROVEMENTS | Seward | 2023-06-01 | Z548570000 | Z548570000 | N/A | Joy A Vaughn | (907)269-0812 | Shift, raise and reconstruct R/W 16/34. Construct Armor protection. Rehabilitate aprons, replace airport lighting, and construct pads for NAVAIDS. Close R/W 13/31, Taxiways A, D, and E. Miscellaneous fencing, signing, etc... |  | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2022.03.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.08.14 project was added.] | ANC TAXIWAY Z IMPROVEMENTS EAST | Anchorage | 2023-07-01 | CFAPT00835 | CFAPT00835 | N/A | Philip W Cheasebro | (907)269-0606 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron.
Central Region | (DELETED) |  |  |  | (2) [on 2022.12.17 project was added.]; [on 2023.05.15 PHONENUM changed.] | HSIP: STERLING HIGHWAY SHOULDER WIDENING MP 157-169 | Kenai Peninsula | 2023-07-01 | CFHWY00991 | CFHWY00991 | 211052 | Kelly L Summers | (907)269-6235
Central Region | (DELETED) |  |  |  | (1) [on 2022.08.14 project was added.] | KWIGILLINGOK AIRPORT IMPROVEMENTS | Kwigillingok | 2023-07-01 | Z525710000 | Z525710000 | N/A | Joy A Vaughn | (907)269-0812 | Reconstruct and extend Kwigillingok Airport to community class standards. Will acquire ROW, improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building(s). | Reconstruct and extend Kwigillingok Airport to community class standards. Improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building. Actual Advertising Date contingent upon federal funding availability. Check back often for updates.
Central Region | (DELETED) |  |  | (1) [on 2022.09.13 the ANTADVDT changed to August 2023.] | (4) [on 2022.04.15 project was added.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.05.15 PHONENUM changed.] | PARKS HWY MP 99 - 163 Drainage & Culvert Improvements | Matanuska-Susitna Borough | 2023-08-01 | CFHWY00592 | CFHWY00592 | 0A41042 | Tom J Schmid | None | Project will construct improvements to drainage including culvert repair, replacement, and new installations, as necessary to provide adequate drainage. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  |  | Sterling Safety Corridor Improvements MP 82.5 to 94 Design Build | Sterling | 2023-07-01 | CFHWY00130A | CFHWY00130A | 0A33026 | Julia R Hanson | (907)269-0753 | This project will use the Progressive Design-Build delivery method. The selected Design-Build team will provide design and support services to design a four-lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed federally funded project will improve safety and reduce congestion. The Design-Build team and the Contracting Agency will negotiate a Target Maximum Price for the preliminary design and, if agreement is reached, a design-build contract to finish the design and construct the project may be awarded. |  | Between $70,000,000 and $80,000,000
Central Region | ADDED |  |  |  |  | ANCHORAGE AREA PAVEMENT PRESERVATION GROUP A | Anchorage | 2024-05-01 | CFHWY00851 | CFHWY00851 | 1739 | Christina A Huber | (907)269-0572 | Pavement preservation on multiple routes. Work may include improvements to roadside hardware, drainage, intersections, automated traffic recorders, pedestrian facilities, bridge work, striping, and utilities.
Central Region | ADDED |  |  |  | (2) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-05-01 | CFAPT00572 | CFAPT00572 | N/A | Philip W Cheasebro | (907)269-0606 | Rehabilitate the runway, taxiway, safety areas, apron, and access road. Place and compact CASC, apply dust palliative, and replace the airport lighting system.
Central Region | ANTADVDT | 2023-04-01 | 2023-06-01 |  | (1) [on 2023.04.14 project was added.] | Peninsula District Paving | Kenai Peninsula Borough | 2023-06-01 | 23-25-1-002
Central Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (1) [on 2023.02.24 the ANTADVDT changed to May 2023.] | (5) [on 2022.01.18 PHONENUM changed.]; [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.02.24 ENGEST changed.] | MEKORYUK AIRPORT SNOW REMOVAL EQUIPMENT BUILDING | Mekoryuk | 2023-06-01 | CFAPT00269
Central Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (2) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (3) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2023-06-01 | 25RC053608
Central Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (7) [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (8) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2023-06-01 | 25RC053613
Central Region | ANTADVDT | 2023-06-01 | 2023-08-01 |  | (4) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-08-01 | CFHWY00883
Central Region | ANTADVDT | 2023-06-01 | 2023-07-01 | (2) [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.] | (4) [on 2022.09.13 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.] | KENAI PENINSULA BRIDGE DECK REHABILITATIONS FY2023 | Kenai Peninsula | 2023-07-01 | CFHWY00946
Central Region | ANTADVDT | 2023-06-01 | 2023-07-01 | (7) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.] | (15) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2023-07-01 | CFAPT00882
Central Region | ANTADVDT | 2023-06-01 | 2023-08-01 | (4) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.04.14 the ANTADVDT changed to June 2023.] | (4) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.04.14 the ANTADVDT changed to June 2023.] | MEKORYUK AIRPORT REHABILITATION | Mekoryuk | 2023-08-01 | CFAPT00288
Central Region | ANTADVDT | 2023-06-01 | 2023-07-01 | (2) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.] | (7) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2023-07-01 | Z512210000
Central Region | ANTADVDT | 2023-07-01 | 2023-09-01 | (4) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.] | (8) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2023-09-01 | CFHWY00253
Central Region | ANTADVDT | 2023-07-01 | 2023-11-01 | (3) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | (5) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-11-01 | Z581060000
Central Region | ANTADVDT | 2023-08-01 | 2023-11-01 |  | (2) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2023-11-01 | CFHWY01083
Central Region | ANTADVDT | 2023-08-01 | 2023-11-01 |  | (1) [on 2023.05.15 project was added.] | SEWARD HWY: MP 75-90 ROAD&BRIDGE REHAB PHASE III | Anchorage | 2023-11-01 | Z581050000
Central Region | ENGEST | Between $200,000 and $500,000 | Between $1,000,000 and $2,500,000 |  | (1) [on 2023.04.14 project was added.] | Peninsula District Paving | Kenai Peninsula Borough | 2023-06-01 | 23-25-1-002
Central Region | ENGEST | Between $90,000,000 and $100,000,000 | Greater than $100,000,000 | (4) [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.] | (8) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2022.10.20 PHONENUM changed.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-11-01 | CFHWY00012
Central Region | PHONENUM | (907)269-0693 | (907)269-0657 |  | (4) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-08-01 | CFHWY00883
Central Region | PHONENUM | (907)269-6235 | (907)269-0546 | (3) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | (5) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-11-01 | Z581060000
Central Region | PHONENUM | None | (907)269-0546 |  | (2) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2023-11-01 | CFHWY01083
Central Region | PHONENUM | None | (907)269-0546 |  | (2) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-03-01 | CFHWY01084
Central Region | PROJMAN | Cynthia L Ferguson | Noah C King |  | (4) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-08-01 | CFHWY00883
Central Region | PROJMAN | Kelly L Summers | Aaron L Hunting | (3) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | (5) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-11-01 | Z581060000
Central Region | PROJMAN | Tom J Schmid | Aaron L Hunting |  | (2) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2023-11-01 | CFHWY01083
Central Region | PROJMAN | Tom J Schmid | Aaron L Hunting |  | (2) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-03-01 | CFHWY01084
Northern Region | (DELETED) |  |  | (3) [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (9) [on 2022.03.15 project was added.]; [on 2022.06.15 ADDLINFO changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to March 2023.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 FEDNUM changed.]; [on 2023.02.24 ENGEST changed.]; [on 2023.03.15 PROJNAME changed.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | FAST Area Surface Upgrades FFY2023 | Fairbanks North Star Borough | 2023-05-01 | NFHWY00633 | NFHWY00633 | Pending | John J Netardus | (907)451-5448 | Resurface pavement, replace pavement markings, replace sidewalk curb with Americans with Disabilities Act (ADA) compliant curb ramps at street corners, improve sidewalks and pedestrian facilities, improve intersections, and install cross culverts on various streets and sidewalks in Fairbanks and North Pole. | Proposed work in 2023 includes, subject to funding availability: Aztec Road Service Area resurfacing (Holmes/Dennis Road area-FNSB) and City of Fairbanks 2nd Avenue dog park access road. Possible College Road RRFB. | Between $1,000,000 and $2,500,000
Northern Region | ADDED |  |  |  |  | COPPER CENTER VISITOR CENTER PAVEMENT PRESERVATION | Copper Center | 2023-11-01 | NFHWY00720 | NFHWY00720 | 8650106 | Russell M Johnson | (907)451-5059 | Resurface pavement at the Copper Center Visitor Center complex. |  | Between $200,000 and $500,000
Northern Region | ADDED |  |  |  |  | DENALI HIGHWAY CULVERT REPLACEMENT | Northern Region | 2024-01-01 | NFHWY00701 | NFHWY00701 | N/A | David K Fischer | (907)451-5357 | Replace culverts on the Denali Highway at MP 93.2, MP 107 and MP 124.5. Project includes roadside hardware.
Northern Region | ADDED |  |  |  |  | Deadhorse Airport Improvements | Deadhorse | 2024-05-01 | NFAPT00549 | NFAPT00549 | 3-02-0339-___-____ | Jonathan J Hutchinson | (907)451-5479 | Construct drainage improvements at the Deadhorse Airport and along Deadhorse Drive and fill in-fields adjacent to the runway and apron. Construct a wildlife perimeter fence with a service road around the airfield. |  | Between $20,000,000 and $30,000,000
Northern Region | ADDED |  |  |  |  | KOTZEBUE AIRPORT CROSSWIND RUNWAY IMPROVEMENTS | Kotzebue | 2024-05-01 | NFAPT00600 | NFAPT00600 | N/A | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate and construct safety improvements to the Kotzebue Airport crosswind runway 18-36 and taxiway G, replace airfield lighting, apply dust palliative, and construct a new general aviation apron.
Northern Region | ADDLINFO |  | Project will be advertised as a CMGC RFP. | (4) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (6) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-07-01 | Z768840000
Northern Region | ANTADVDT | 2023-05-01 | 2023-06-01 |  | (1) [on 2023.05.15 project was added.] | FIA Response Center Sleeping Quarters FY2023 | Fairbanks North Star Borough | 2023-06-01 | NSAPT00791
Northern Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (2) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (6) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-06-01 | NFHWY00527
Northern Region | ANTADVDT | 2023-05-01 | 2023-07-01 | (4) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (6) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-07-01 | Z768840000
Northern Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (1) [on 2023.05.15 the ANTADVDT changed to May 2023.] | (3) [on 2022.10.20 project was added.]; [on 2023.01.17 PROJNAME changed.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | Richardson Highway Milepost 233 Bear Creek Bridge #0593 Replacement | Delta Junction | 2023-06-01 | NFHWY00278
Northern Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (4) [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.] | (9) [on 2022.01.18 project was added.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2022.10.20 PROJNAME changed.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 ADDLINFO changed.]; [on 2023.04.14 ADDLINFO changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.05.15 FEDNUM changed.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-06-01 | Z607150000
Northern Region | ANTADVDT | 2023-06-01 | 2023-07-01 |  | (4) [on 2022.07.12 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.02.24 PROJNAME changed.] | Chalkyitsik Airport Improvements | Chalkyitsik | 2023-07-01 | Z625970000
Northern Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $30,000,000 and $40,000,000 | (2) [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.] | (7) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2023-11-01 | Z631860000
Northern Region | FEDNUM | 2472 | 0002(472) | (2) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (6) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-06-01 | NFHWY00527
Northern Region | PROJNAME | HSIP: Old Steese Highway Shoulder Widening | Old Steese Highway Shoulder Widening (HSIP) | (2) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (6) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-06-01 | NFHWY00527
Northern Region | PROJNAME | SEPPALA DRIVE UPGRADE | Seppala Drive Upgrade |  | (1) [on 2023.02.24 project was added.] | Seppala Drive Upgrade | Nome | 2023-12-01 | Z620030000
Southcoast Region | (DELETED) |  |  |  | (3) [on 2022.09.13 project was added.]; [on 2023.01.17 PHONENUM changed.]; [on 2023.01.17 PROJMAN changed.] | HYG - HYDABURG SEAPLANE FACILITY REFURBISHMENT | Hydaburg | 2023-08-01 | SFAPT00328 | SFAPT00328 | N/A | David H Lowell | (907)465-4812 | Refurbish and/or replace existing seaplane float facility in Hydaburg, AK. Investigate replacement at a new location |  | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  |  | (2) [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.] | KTN AIRPORT SEAPLANE RAMP AND HAUL OUT REFURBISHMENT | Ketchikan | 2023-08-01 | SFAPT00327 | SFAPT00327 | N/A | Loren K Gehring | (907)465-8189 | Refurbish and/or replace existing seaplane float and haul-out ramp facility at the Ketchikan Airport. Investigate replacement at a new location. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  |  | (5) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.10.20 project was added.]; [on 2022.12.17 the project was removed.]; [on 2023.02.24 project was added.] | KDK CHINIAK HIGHWAY REHABILITATION: MILE POST 15 TO 31 | Kodiak | 2024-01-01 | SFHWY00111 | SFHWY00111 | 391015 | James L Brown | (907)465-1796 | Rehabilitate the Chiniak Highway from Milepost 15 to just past 31 to improve and preserve the roadway subgrade and surface. Address lighting, guardrails, drainage, culverts and other highway appurtenances as needed. |  | Between $10,000,000 and $20,000,000
Southcoast Region | (DELETED) |  |  | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (5) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.] | CRAIG ADA IMPROVEMENTS | Craig | 2024-02-01 | SFHWY00377 | SFHWY00377 | 3274 | Bran P Pollard | (907)465-4526 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit. |  | Between $2,500,000 and $5,000,000
Southcoast Region | (DELETED) |  |  |  | (5) [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.04.14 project was added.] | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | Kodiak | 2024-03-01 | SFHWY00260 | SFHWY00260 | 3247 | Bran P Pollard | (907)465-4526 | Resurface Rezanoff Drive from Marine Way to the airport. Associated preventative maintenance activities may include minor structural section improvements, drainage repairs, lighting and signals, striping, signs, and ADA improvements. Project Location and Length: Rezanoff Drive from Marine Way to the airport for an approximate length of 4.70 miles. | (Design by Northern Region) | Between $10,000,000 and $20,000,000
Southcoast Region | ADDED |  |  |  | (9) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2023-02-01 | SFAPT00178 | SFAPT00178 | N/A | Gregory K Lockwood | (907)465-2393 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
Southcoast Region | ADDED |  |  |  |  | FFY2020 EAS YAKUTAT OBSTRUCTION REMOVAL | Yakutat | 2023-07-01 | SFAPT00204 | SFAPT00204 | 3-02-0200-135-2020 | Spencer M Gates | (907)465-1014 | Cut 16 acres of trees on the south side of runway 29. |  | Between $200,000 and $500,000
Southcoast Region | ADDED |  |  | (3) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (8) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.05.15 the project was removed.] | WRG ZIMOVIA HWY ROCK FALL MITIGATION HSIP | Wrangell | 2023-08-01 | SFHWY00308 | SFHWY00308 | 3262 | Nathan A Purves | (907)465-4521 | Perform slope stabilization and mitigation work at two rock fall sites on Zimovia Highway in Wrangell, Alaska. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-03-01 | SFHWY00440 | SFHWY00440 | 93006 | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS00l, AK 2021 01 HNS002, AK 2021 01 HNS003, and AK 2021 01 HNS004. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway. |  | Between $200,000 and $500,000
Southcoast Region | ADDED |  |  |  |  | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-03-01 | SFHWY00446 | SFHWY00446 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS005, AK 2021 01 HNS006, AK 2021 01 HNS007, AK 2021 01 HNS008, AK 2021 01 HNS009, AK 2021 01 HNS010, AK 2021 01 HNS011, and AK 2021 01 HNS012. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway & Lutak Road. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-03-01 | SFHWY00481 | SFHWY00481 | 933051 | Joel D Osburn | (907)465-4409 | This project will design and construct a chip seal overlay on Glacier Highway, between Brotherhood Bridge and the Auke Bay Roundabout. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  |  |  | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2024-04-01 | SDRER00445 | SDRER00445 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Damage Inventory Numbers 461220 - 461221, 461229, 461231 - 461236, 461253, 461255 - 461257, 461652, 784622, and 918887 - 918890. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Beach Road, Front Street, Allen-Menaker Road, Comstock Road, Piedad Road and Mud Bay Road. This project is funded by FEMA. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  | (3) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.] | (9) [on 2022.01.18 ENGEST changed.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.05.15 the project was removed.] | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | Hoonah | 2024-05-01 | SFAPT00236 | SFAPT00236 | N/A | Loren K Gehring | (907)465-8189 | Relocation of an existing stream bed and conduct dredging under the seaplane mooring float to restore sufficient water depths and/or relocation of the seaplane float structure to deeper water at the same location. Phase: T02000 - Par - All Costs | Construction funding uncertain. | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | HNS LUTAK ROAD 437114 - DEC 20 SE PR | Haines | 2024-05-01 | SDRER00448 | SDRER00448 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Damage Inventory Numbers 461224, 461227, 461237 - 461239, 461243 - 461250, 784625 - 784632, and 786036. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Lutak Road. This project is funded by FEMA. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  | (6) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.] | (15) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-05-01 | SFHWY00359 | SFHWY00359 | 3267 | Brett M Wells | (907)465-1607 | Replace the twin culverts at Bridget Cove Creek. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | KTN SAXMAN TO SURF ST PAVEMENT REHABILITATION - SOUTH TONGAS | Ketchikan | 2024-05-01 | Z675710000 | Z675710000 | 902031 | David A Pyeatt | None | Updated 7/14/10: Widening, guardrail and drainage improvements and roadway reconstruction and repaving. Rev. 8/10 Construct recreational path on water side of roadway. Improve vertical and horizontal alignment. Provide additional parking if required to mitigate for loss due to addition of separated pathway. Provide geotech and coastal engineering to minimize impacts to ROW and environmentally sensitive areas. Additional public involvement as required to present ROW challenges posed by the separated pathway. Coordinate utilities with Ketchikan and Saxman communities. | Rehabilitate the roadway and appurtenances from the north end of the City of Saxman to Surf Street. Widen the roadway and construct a new shared use pathway on the water side where none exists. | Between $10,000,000 and $20,000,000
Southcoast Region | ADDED |  |  |  |  | KTN SOUTH TONGASS HWY DEERMOUNT TO SAXMAN WIDENING | Ketchikan | 2024-05-01 | Z676850000 | Z676850000 | 902039 | David A Pyeatt | None | Reconstruct roadway and non-motorized facilities, as necessary, to improve safe movement of vehicle, bicycle and pedestrian traffic. | Rehabilitate the roadway and appurtenances from Deermount Street to the north end of the City of Saxman. Reconstruct the sidewalks and shared use pathway. Construct a new shared use pathway where none exists. Construct a new sidewalk on the uphill side of the road from the existing terminus near Deermount Street to the lower USCG base entrance. | Between $40,000,000 and $50,000,000
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-07-01 | (6) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.] | (9) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2023-07-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (1) [on 2023.04.14 the ANTADVDT changed to May 2023.] | (4) [on 2022.02.22 DESCRIPTION changed.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | JNU KAXDIGOOWU HEEN DEI IMP (BROTHERHOOD BRIDGE TRAIL IMP) | Juneau | 2023-06-01 | SFHWY00259
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-08-01 | (7) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (8) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2023-08-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (4) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (5) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.06.15 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2023-06-01 | Z680910000
Southcoast Region | ANTADVDT | 2023-09-01 | 2023-12-01 |  | (1) [on 2023.02.24 project was added.] | JNU WAYDELICH CREEK: LOWER WALL REPAIRS | Juneau | 2023-12-01 | SFHWY00485
Southcoast Region | ANTADVDT | 2023-09-01 | 2023-12-01 |  | (1) [on 2023.02.24 project was added.] | JNU WAYDELICH CREEK: UPPER WALL REPAIRS - DEC 20 SE PR | Juneau | 2023-12-01 | SFHWY00414
Southcoast Region | ANTADVDT | 2023-11-01 | 2024-01-01 |  | (5) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-01-01 | Z686060000
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-03-01 |  | (1) [on 2023.02.24 project was added.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2024-03-01 | SDRER00436
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-04-01 |  | (1) [on 2023.02.24 project was added.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2024-04-01 | SFHWY00438
Southcoast Region | DESCRIPTION | This project is to provide funding for state support and review of Neck Lake Road Segment 2 design developed under FHWA, Western Federal Lands Highway Division. | This project is to provide funding for state support and review of Neck Lake Road Segment 2 design developed under FHWA, Western Federal Lands Highway Division. Neck Lake Rd Stage 1 Match Transfer funding is also processed thru this project. | (2) [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (5) [on 2022.11.17 project was added.]; [on 2022.12.17 ADDLINFO changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | POW NECK LAKE RD RECNTN STAGES 1 & 2 - WFLHD | Prince Of Wales Island | 2023-05-01 | SFHWY00375
Southcoast Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $500,000 and $1,000,000 |  | (1) [on 2023.02.24 project was added.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2024-04-01 | SFHWY00438
Southcoast Region | PROJNAME | NECK LAKE ROAD RECONSTRUCTION SEGMENT 2 WFLHD | POW NECK LAKE RD RECNTN STAGES 1 & 2 - WFLHD | (2) [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (5) [on 2022.11.17 project was added.]; [on 2022.12.17 ADDLINFO changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | POW NECK LAKE RD RECNTN STAGES 1 & 2 - WFLHD | Prince Of Wales Island | 2023-05-01 | SFHWY00375
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Never appeared on Difadel or TAS prior.
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This month.
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Slipping to next FFY
Note on D47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This month.