## 2023.07.14 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (1) [on 2023.06.15 the ANTADVDT changed to June 2023.] | (3) [on 2023.04.14 project was added.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 ENGEST changed.] | Peninsula District Paving | Kenai Peninsula Borough | 2023-06-01 | 23-25-1-002 | 23-25-1-002 | N/A | Vernon S Vreeland | (907)269-0778 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Kenai Peninsula District Boundaries, on an as-needed basis. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (5) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.] | (9) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2023-09-01 | CFHWY00253 | CFHWY00253 | 221019 | Alex L Read | (907)269-0641 | This project will rehabilitate the Kenai Spur Highway between Soldotna and Kenai. A 5-lane highway will be constructed between the Sports Lake Road and Robin Drive intersections to increase capacity and improve safety. This is the second of two phases to construct the project. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00253/00253.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $40,000,000 and $50,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.] | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2024-03-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Cynthia L Ferguson | (907)269-0693 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards.
Central Region | (DELETED) |  |  |  | (3) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2024-03-01 | CFHWY00503 | CFHWY00503 | 1644 | Cynthia L Ferguson | (907)269-0693 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements.
Central Region | ADDED |  |  |  | (2) [on 2022.05.16 project was added.]; [on 2022.09.13 the project was removed.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2024-06-01 | CFHWY00555 | CFHWY00555 | 1657 | Julia R Hanson | (907)269-0753 | This AMATS funded project will reconstructed the traffic signal and street lighting system on 4th Ave between A Street and Ingra Street. Work may included signing, Striping, ATRs, drainage, paving, pedestrian & ADA amenities, utility relocation, landscaping and roadside hardware.
Central Region | ADDED |  |  |  |  | GLENN HIGHWAY: AIRPORT HEIGHTS TO PARK HIGHWAY REHAB | Anchorage | 2024-06-01 | CFHWY00545 | CFHWY00545 | 1656 | Chris L Bentz | (907)269-0652 | This project will rehabilitate the Glenn Highway from the intersection with Airport Heights ( MP 0.0) to the Parks Highway Interchange ( MP 33.0). The project may include Bridge work, roadside hardware, drainage Improvements, interchange improvements, ADA improvements, utilities and safety improvements. |  | Greater than $100,000,000
Central Region | ADDLINFO |  | <a class=linkcopy href=https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/9_00993%20ANC%20Terminal%20Water%20Main%20Improvements%20-%20TAL.pdf>Preliminary Plans (~21 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (2) [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | (6) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.03.15 PHONENUM changed.]; [on 2023.03.15 PROJMAN changed.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-07-01 | CFAPT00993
Central Region | ADDLINFO | The project will be delivered using the Progressive Design-Build method. |  | (1) [on 2023.04.14 the ANTADVDT changed to July 2023.] | (3) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2023-10-01 | CFHWY00943
Central Region | ADDLINFO |  | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> |  | (1) [on 2023.06.15 project was added.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2023-08-01 | CFHWY00130A
Central Region | ANTADVDT | 2023-06-01 | 2023-08-01 | (4) [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.] | (5) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.] | ANC SUPPLY WAREHOUSE ROOF REPLACEMENT | Anchorage | 2023-08-01 | CSAPT00858
Central Region | ANTADVDT | 2023-06-01 | 2023-08-01 | (2) [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (6) [on 2022.01.18 PHONENUM changed.]; [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.02.24 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | MEKORYUK AIRPORT SNOW REMOVAL EQUIPMENT BUILDING | Mekoryuk | 2023-08-01 | CFAPT00269
Central Region | ANTADVDT | 2023-06-01 | 2023-07-01 | (8) [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (9) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2023-07-01 | 25RC053613
Central Region | ANTADVDT | 2023-07-01 | 2023-08-01 | (6) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.] | (8) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2023-08-01 | CFHWY00395
Central Region | ANTADVDT | 2023-07-01 | 2023-10-01 | (1) [on 2023.04.14 the ANTADVDT changed to July 2023.] | (3) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2023-10-01 | CFHWY00943
Central Region | ANTADVDT | 2023-07-01 | 2023-08-01 |  | (1) [on 2023.06.15 project was added.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2023-08-01 | CFHWY00130A
Central Region | ANTADVDT | 2023-08-01 | 2023-10-01 | (1) [on 2023.06.15 the ANTADVDT changed to August 2023.] | (7) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-10-01 | CFHWY00883
Central Region | ANTADVDT | 2024-02-01 | 2024-04-01 |  | (3) [on 2022.05.16 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.03.15 project was added.] | HSIP: 5TH AVE: CONCRETE ST TO KARLUK ST PEDESTRIAN IMPROVMNT | Anchorage | 2024-04-01 | CFHWY00856
Central Region | DESCRIPTION | Design and construct improvements to the Seward Highway and Sterling Highway intersection to improve traffic flow and safety. Anticipated work includes road reconstruction, lighting, drainage, utility relocation, and avalanche hazard mitigation. | Design and construct improvements to the Seward Highway and Sterling Highway intersection to improve traffic flow and safety. Anticipated work includes road reconstruction, lighting, drainage, utility relocation, and avalanche hazard mitigation. This project will use the Progressive Design-Build (PDB) delivery method. The selected PDB team will provide design and support services to design the intersection improvements. The PDB team and the Contracting Agency will negotiate a Target Maximum Price for construction based on the preliminary design and, if agreement is reach, a design-build contract to finish the design and construct the project may be awarded. | (1) [on 2023.04.14 the ANTADVDT changed to July 2023.] | (3) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2023-10-01 | CFHWY00943
Central Region | DESCRIPTION | This project will use the Progressive Design-Build delivery method. The selected Design-Build team will provide design and support services to design a four-lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed federally funded project will improve safety and reduce congestion. The Design-Build team and the Contracting Agency will negotiate a Target Maximum Price for the preliminary design and, if agreement is reached, a design-build contract to finish the design and construct the project may be awarded. | This project will use the Progressive Design-Build (PDB) delivery method. The selected PDB team will provide design and support services to design a four-lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed federally funded project will improve safety and reduce congestion. The PDB team and the Contracting Agency will negotiate a Target Maximum Price for construction based on the preliminary design and, if agreement is reached, a design-build contract to finish the design and construct the project may be awarded. |  | (1) [on 2023.06.15 project was added.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2023-08-01 | CFHWY00130A
Central Region | ENGEST |  | Between $5,000,000 and $10,000,000 |  | (2) [on 2022.11.17 project was added.]; [on 2023.05.15 PROJNAME changed.] | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | Wasilla | 2023-10-01 | CFHWY00622
Central Region | ENGEST |  | Between $10,000,000 and $20,000,000 | (1) [on 2023.06.15 the ANTADVDT changed to November 2023.] | (2) [on 2023.05.15 project was added.]; [on 2023.06.15 the ANTADVDT changed to November 2023.] | SEWARD HWY: MP 75-90 ROAD&BRIDGE REHAB PHASE III | Anchorage | 2023-11-01 | Z581050000
Central Region | FEDNUM | 1642 | 1642 | (6) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.] | (8) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2023-08-01 | CFHWY00395
Central Region | FEDNUM | 1417 | 1417 | (3) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | (8) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2023-07-01 | Z512210000
Central Region | FEDNUM | 1727 | 1727 | (1) [on 2023.06.15 the ANTADVDT changed to August 2023.] | (7) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-10-01 | CFHWY00883
Central Region | FEDNUM | 3-02-0176-003-2022 | 3-02-0176-003-2023 | (5) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.04.14 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.] | (5) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.04.14 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.] | MEKORYUK AIRPORT REHABILITATION | Mekoryuk | 2023-08-01 | CFAPT00288
Central Region | FEDNUM | 510007 | 510007 | (4) [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.]; [on 2023.03.15 the ANTADVDT changed to September 2023.] | (5) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.]; [on 2023.03.15 the ANTADVDT changed to September 2023.] | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | Anchorage | 2023-09-01 | CFHWY00286
Central Region | FEDNUM | 1700 | 1700 |  | (2) [on 2022.11.17 project was added.]; [on 2023.05.15 PROJNAME changed.] | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | Wasilla | 2023-10-01 | CFHWY00622
Central Region | FEDNUM | 1685 | 1685 | (1) [on 2023.05.15 the ANTADVDT changed to November 2023.] | (2) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Central Region | 2023-11-01 | CFHWY00523
Central Region | FEDNUM | 537008 | 537008 | (4) [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.] | (9) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2022.10.20 PHONENUM changed.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-11-01 | CFHWY00012
Central Region | FEDNUM | 211052 | 211052 | (4) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to November 2023.] | (8) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-11-01 | Z581060000
Central Region | FEDNUM | 1694 | 1694 | (1) [on 2022.11.17 the ANTADVDT changed to July 2023.] | (6) [on 2022.04.15 project was added.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.] | AMATS: EAGLE RIVER LOOP RD - EAGLE RIVER RD TO OLD GLENN HWY | Eagle River | 2023-12-01 | CFHWY00731
Central Region | FEDNUM | 1692 | 1692 | (1) [on 2022.11.17 the ANTADVDT changed to July 2023.] | (4) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.] | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | Eagle River | 2023-12-01 | CFHWY00621
Central Region | FEDNUM | 1686 | 1686 |  | (1) [on 2023.03.15 project was added.] | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | Big Lake | 2024-02-01 | CFHWY00392
Central Region | FEDNUM | 421102 | 421102 |  | (3) [on 2022.05.16 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.03.15 project was added.] | HSIP: 5TH AVE: CONCRETE ST TO KARLUK ST PEDESTRIAN IMPROVMNT | Anchorage | 2024-04-01 | CFHWY00856
Central Region | FEDNUM | 1662 | 1662 |  | (1) [on 2023.04.14 project was added.] | AMATS: DOWNTOWN TRAIL CONNECTION | Anchorage | 2024-03-01 | CFHWY00586
Central Region | FEDNUM | 1739 | 1739 |  | (1) [on 2023.06.15 project was added.] | ANCHORAGE AREA PAVEMENT PRESERVATION GROUP A | Anchorage | 2024-05-01 | CFHWY00851
Central Region | PHONENUM | (907)269-0602 | (907)269-0623 |  | (1) [on 2023.04.14 project was added.] | ANC TAXIWAY R NORTH IMPROVEMENTS | Anchorage | 2024-03-01 | CFAPT00880
Central Region | PROJMAN | Matthew H Hansen | Kim D Satterfield |  | (1) [on 2023.04.14 project was added.] | ANC TAXIWAY R NORTH IMPROVEMENTS | Anchorage | 2024-03-01 | CFAPT00880
Central Region | PROJNAME | SEWARD HWY STERLING HWY INTERSECTION IMPROVEMENTS | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | (1) [on 2023.04.14 the ANTADVDT changed to July 2023.] | (3) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2023-10-01 | CFHWY00943
Central Region | PROJNAME | Sterling Safety Corridor Improvements MP 82.5 to 94 Design Build | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build |  | (1) [on 2023.06.15 project was added.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2023-08-01 | CFHWY00130A
Marine Highways | FEDNUM | 933048 | 933048 |  | (1) [on 2023.04.14 project was added.] | AMHS JNU AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | Juneau | 2024-01-01 | SAMHS00419
Northern Region | (DELETED) |  |  | (2) [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (4) [on 2022.10.20 project was added.]; [on 2023.01.17 PROJNAME changed.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | Richardson Highway Milepost 233 Bear Creek Bridge #0593 Replacement | Delta Junction | 2023-06-01 | NFHWY00278 | NFHWY00278 | 714024 | Jennifer J Wright | (907)371-8949 | Reconstruct the Richardson Highway between Milepost 232 - 234.5 and replace Bear Creek Bridge #0593. Project will include drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  | (6) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 FEDNUM changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2023.03.15 the project was removed.] | Buckland Airport Improvements | Buckland | 2024-06-01 | NFAPT00604 | NFAPT00604 | 3-02-0399-___-____ | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate the runway and taxiway, stabilize the embankments, resurface the airport access road, apply dust palliative, and replace the airport lighting system. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  | (1) [on 2022.02.22 the ANTADVDT changed to July 2022.] | (4) [on 2022.02.22 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2023.03.15 the project was removed.] | Deering Airport Improvements | Deering | 2024-06-01 | NFAPT00249 | NFAPT00249 | 3-02-0400-XX-202X | Jonathan J Hutchinson | (907)451-5479 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  |  | HSIP: CITY OF FAIRBANKS SYSTEMIC SIGNAL UPGRADES | Fairbanks | 2024-03-01 | NFHWY00592 | NFHWY00592 | 2495 | Carl F Heim | (907)451-5359 | Reconstruct 22 signalized intersections at multiple locations in the City of Fairbanks. Work includes roadside hardware and intersection improvements. | This project will be advertised with HSIP: Northern Region Systemic Signal Upgrades (NFHWY00531) | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  |  | HSIP: NORTHERN REGION SYSTEMIC SIGNAL UPGRADES | Fairbanks North Star Borough | 2024-03-01 | NFHWY00531 | NFHWY00531 | 2474 | Carl F Heim | (907)451-5359 | Reconstruct eight signalized intersections at multiple locations in the Fairbanks and Parks Highway Nenana Canyon area. Work includes roadside hardware and intersection improvements. | This project will be constructed with HSIP: City of Fairbanks Systemic Signal Upgrades (NFHWY00592) | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  |  | RUBY SLOUGH ROAD REHABILITATION | Ruby | 2024-03-01 | NFHWY00630 | NFHWY00630 | 2509 | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate Ruby Slough Road from Ruby Slough to the landfill. Project will include drainage improvements and roadside hardware. |  | Between $5,000,000 and $10,000,000
Northern Region | ANTADVDT | 2023-06-01 | 2023-07-01 | (1) [on 2023.06.15 the ANTADVDT changed to June 2023.] | (2) [on 2023.05.15 project was added.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | FIA Response Center Sleeping Quarters FY2023 | Fairbanks North Star Borough | 2023-07-01 | NSAPT00791
Northern Region | ANTADVDT | 2023-06-01 | 2023-07-01 | (1) [on 2023.05.15 the ANTADVDT changed to June 2023.] | (4) [on 2022.08.14 project was added.]; [on 2023.01.17 FEDNUM changed.]; [on 2023.01.17 PROJNAME changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.] | Marshall Airport Improvements | Marshall | 2023-07-01 | NFAPT00371
Northern Region | ANTADVDT | 2023-06-01 | 2023-11-01 | (3) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (9) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 FEDNUM changed.]; [on 2023.06.15 PROJNAME changed.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-11-01 | NFHWY00527
Northern Region | ANTADVDT | 2023-06-01 | 2023-09-01 | (5) [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (10) [on 2022.01.18 project was added.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2022.10.20 PROJNAME changed.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 ADDLINFO changed.]; [on 2023.04.14 ADDLINFO changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.05.15 FEDNUM changed.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-09-01 | Z607150000
Northern Region | ENGEST |  | Between $1,000,000 and $2,500,000 |  | (1) [on 2023.06.15 project was added.] | Denali Highway Culvert Replacement | Cantwell | 2024-01-01 | NFHWY00701
Northern Region | FEDNUM | 2204 | 2204 | (5) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | (8) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-07-01 | Z768840000
Northern Region | FEDNUM | 713010 | 713010 | (2) [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.] | (8) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2023-11-01 | Z631860000
Northern Region | FEDNUM | 712035 | 712035 |  | (1) [on 2023.01.17 project was added.] | RICHARDSON HWY MP 82-115 RESURFACING (CONST MP 97-115) | Valdez | 2023-12-01 | NFHWY00218
Northern Region | FEDNUM | N/A | Pending |  | (1) [on 2023.06.15 project was added.] | Denali Highway Culvert Replacement | Cantwell | 2024-01-01 | NFHWY00701
Northern Region | FEDNUM | 650035 | 650035 | (1) [on 2023.03.15 the ANTADVDT changed to January 2024.] | (5) [on 2022.06.15 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.02.24 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.03.15 ENGEST changed.] | Elliott Highway MP 18 - 29 Resurfacing | Livengood | 2024-01-01 | NFHWY00588
Northern Region | LOCATION | Northern Region | Cantwell |  | (1) [on 2023.06.15 project was added.] | Denali Highway Culvert Replacement | Cantwell | 2024-01-01 | NFHWY00701
Northern Region | PROJNAME | DENALI HIGHWAY CULVERT REPLACEMENT | Denali Highway Culvert Replacement |  | (1) [on 2023.06.15 project was added.] | Denali Highway Culvert Replacement | Cantwell | 2024-01-01 | NFHWY00701
Northern Region | PROJNAME | ELLIOTT HIGHWAY MP 18 - 29 RESURFACING | Elliott Highway MP 18 - 29 Resurfacing | (1) [on 2023.03.15 the ANTADVDT changed to January 2024.] | (5) [on 2022.06.15 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.02.24 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.03.15 ENGEST changed.] | Elliott Highway MP 18 - 29 Resurfacing | Livengood | 2024-01-01 | NFHWY00588
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.06.15 project was added.] | KTN SAXMAN TO SURF ST PAVEMENT REHABILITATION - SOUTH TONGAS | Ketchikan | 2024-05-01 | Z675710000 | Z675710000 | 902031 | David A Pyeatt | None | Updated 7/14/10: Widening, guardrail and drainage improvements and roadway reconstruction and repaving. Rev. 8/10 Construct recreational path on water side of roadway. Improve vertical and horizontal alignment. Provide additional parking if required to mitigate for loss due to addition of separated pathway. Provide geotech and coastal engineering to minimize impacts to ROW and environmentally sensitive areas. Additional public involvement as required to present ROW challenges posed by the separated pathway. Coordinate utilities with Ketchikan and Saxman communities. | Rehabilitate the roadway and appurtenances from the north end of the City of Saxman to Surf Street. Widen the roadway and construct a new shared use pathway on the water side where none exists. | Between $10,000,000 and $20,000,000
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.06.15 project was added.] | KTN SOUTH TONGASS HWY DEERMOUNT TO SAXMAN WIDENING | Ketchikan | 2024-05-01 | Z676850000 | Z676850000 | 902039 | David A Pyeatt | None | Reconstruct roadway and non-motorized facilities, as necessary, to improve safe movement of vehicle, bicycle and pedestrian traffic. | Rehabilitate the roadway and appurtenances from Deermount Street to the north end of the City of Saxman. Reconstruct the sidewalks and shared use pathway. Construct a new shared use pathway where none exists. Construct a new sidewalk on the uphill side of the road from the existing terminus near Deermount Street to the lower USCG base entrance. | Between $40,000,000 and $50,000,000
Southcoast Region | ADDED |  |  |  | (2) [on 2022.10.20 project was added.]; [on 2023.02.24 the project was removed.] | ANG AIRPORT INITIATION | Angoon | 2024-06-01 | SFAPT00086 | SFAPT00086 | N/A | David B Epstein | (907)465-4483 | Construction of a new airport and access roadways located 2.5 miles south of Angoon. CC: 24300114 LC: 33002332 |  | Greater than $100,000,000
Southcoast Region | ADDED |  |  |  | (6) [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.06.15 the project was removed.] | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | Kodiak | 2024-06-01 | SFHWY00260 | SFHWY00260 | 3247 | Bran P Pollard | (907)465-4526 | Resurface Rezanoff Drive from Marine Way to the airport. Associated preventative maintenance activities may include minor structural section improvements, drainage repairs, lighting and signals, striping, signs, and ADA improvements. Project Location and Length: Rezanoff Drive from Marine Way to the airport for an approximate length of 4.70 miles. |  | Between $10,000,000 and $20,000,000
Southcoast Region | ADDED |  |  |  |  | SGY, HNH, PSG ROADWAY & CULVERTS - DEC 20 SE PR | Southcoast Region | 2024-06-01 | SFHWY00447 | SFHWY00447 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2020 01 HNH001, AK 2020 01 HNH002, AK 2021 01 PTG002, AK 2021 01 PTG003, and AK 2021 01 SGY001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites in Hoonah, Petersburg & Skagway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ANTADVDT | 2023-02-01 | 2024-02-01 |  | (10) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-02-01 | SFAPT00178
Southcoast Region | ANTADVDT | 2023-08-01 | 2023-10-01 | (8) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.] | (9) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2023-10-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-03-01 | (3) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.] | (10) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-03-01 | SFAPT00412
Southcoast Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (3) [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to January 2024.] | (7) [on 2022.09.13 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2024-02-01 | SFHWY00326
Southcoast Region | DESCRIPTION | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. |  | (10) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-02-01 | SFAPT00178
Southcoast Region | DESCRIPTION | Assess and correct guardrail safety deficiencies along Principal and Minor Arterial routes with posted speeds of 40 mph or higher. Typical deficiencies include, but are not limited to, steel washers on the face of rail, insufficient length of need, steel blockouts without backup plates, and break away cable terminals. | Assess and correct guardrail safety deficiencies along Principal and Minor Arterial routes with posted speeds of 40 mph or higher. Typical deficiencies include, but are not limited to, steel washers on the face of rail, insufficient length of need, steel blockouts without backup plates, and break away cable terminals. |  | (1) [on 2022.09.13 project was added.] | SR REGIONWIDE GUARDRAIL INVENTORY AND UPGRADE HSIP | Regionwide | 2023-08-01 | SFHWY00404
Southcoast Region | DESCRIPTION | Construct a single-lane roundabout at the Loop Road - Mendenhall Boulevard - Valley Boulevard intersection. | Construct a single-lane roundabout at the Loop Road - Mendenhall Boulevard - Valley Boulevard intersection. |  | (2) [on 2023.03.15 project was added.]; [on 2023.05.15 ENGEST changed.] | JNU L00P RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | Juneau | 2024-02-01 | SFHWY00403
Southcoast Region | DESCRIPTION | This project is for Sitka Seawalk Stage II, which will continue the Sea Walk from the Sitka Public Library to the O¿Connell Lightering Facility. This project would improve pedestrian and ADA accessibility to the existing facilities. | This project is for Sitka Seawalk Stage II, which will continue the Sea Walk from the Sitka Public Library to the O¿Connell Lightering Facility. This project would improve pedestrian and ADA accessibility to the existing facilities. |  | (1) [on 2023.05.15 project was added.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2024-02-01 | SFHWY00312
Southcoast Region | FEDNUM | 958032 | 958032 | (4) [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.] | (10) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.06.15 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-06-01 | SFHWY00058-3
Southcoast Region | FEDNUM | 902042 | 902042 | (5) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (6) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.06.15 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2023-06-01 | Z680910000
Southcoast Region | FEDNUM | 3244 | 3244 | (4) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | (9) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2023-07-01 | SFHWY00186
Southcoast Region | FEDNUM | 3225 | 3225 | (1) [on 2022.09.13 the ANTADVDT changed to August 2023.] | (5) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2023-08-01 | SFHWY00070
Southcoast Region | FEDNUM | 3278 | 3278 |  | (1) [on 2022.09.13 project was added.] | SR REGIONWIDE GUARDRAIL INVENTORY AND UPGRADE HSIP | Regionwide | 2023-08-01 | SFHWY00404
Southcoast Region | FEDNUM | 3262 | 3262 | (3) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (9) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.] | WRG ZIMOVIA HWY ROCK FALL MITIGATION HSIP | Wrangell | 2023-08-01 | SFHWY00308
Southcoast Region | FEDNUM | 3214 | 3214 | (3) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.] | (7) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2023-10-01 | SFHWY00103
Southcoast Region | FEDNUM | 933050 | 933050 | (1) [on 2023.06.15 the ANTADVDT changed to December 2023.] | (2) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.] | JNU WAYDELICH CREEK: LOWER WALL REPAIRS | Juneau | 2023-12-01 | SFHWY00485
Southcoast Region | FEDNUM | 93003 | 93003 | (1) [on 2023.06.15 the ANTADVDT changed to December 2023.] | (2) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.] | JNU WAYDELICH CREEK: UPPER WALL REPAIRS - DEC 20 SE PR | Juneau | 2023-12-01 | SFHWY00414
Southcoast Region | FEDNUM | 3265 | 3265 | (3) [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to January 2024.] | (7) [on 2022.09.13 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2024-02-01 | SFHWY00326
Southcoast Region | FEDNUM | 956028 | 956028 | (1) [on 2023.06.15 the ANTADVDT changed to January 2024.] | (6) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-01-01 | Z686060000
Southcoast Region | FEDNUM | 3233 | 3233 |  | (1) [on 2023.02.24 project was added.] | KTN AIRPORT FERRY CAPACITY MODIFICATIONS (GRAVINA) | Ketchikan | 2024-01-01 | SFHWY00184
Southcoast Region | FEDNUM | 972018 | 972018 | (10) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.] | (13) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2024-01-01 | Z680850000
Southcoast Region | FEDNUM | 966030 | 966030 |  | (2) [on 2023.03.15 project was added.]; [on 2023.05.15 ENGEST changed.] | JNU L00P RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | Juneau | 2024-02-01 | SFHWY00403
Southcoast Region | FEDNUM | 93006 | 93006 |  | (1) [on 2023.06.15 project was added.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-03-01 | SFHWY00440
Southcoast Region | FEDNUM | 933051 | 933051 |  | (1) [on 2023.06.15 project was added.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-03-01 | SFHWY00481
Southcoast Region | FEDNUM | 93005 | 93005 | (1) [on 2023.06.15 the ANTADVDT changed to April 2024.] | (3) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2024-04-01 | SFHWY00438
Southcoast Region | FEDNUM | 3267 | 3267 | (6) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.] | (16) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-05-01 | SFHWY00359
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Likely pushed out to over a year. Original was Feb 2023.
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has changed for the last 4 months, 8 times total.
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 6 Date Changes.
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Crosses FFY
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: High Visibility/Interest Project.
Note on D51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Slippage, crossing FFY
Note on E52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Excessive changes
Note on D68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Slippage, crossing FFY
Note on E68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Excessive changes.