## Tentative Award Schedule
PROJID | PROJNAME | STATENUM | FEDNUM | REGION | LOCATION | PROJMAN | PHONENUM | ANTADVDT | DESCRIPTION | ADDLINFO | ENGEST
SFHWY00463 | SE District Hwy Painting FFY23 - NHS | SFHWY00463 | N/A | Southcoast Region | Regionwide | David B Epstein | (907)465-4483 | 2023-03-01 | SCOPE: Development of NHS & Non-NHS preservation maintenance projects. These projects consist of pavement preservation on highways, catch basins, culverts, pavement markings, luminary replacement, bridge preservation, drainage preservation, gravel surface preservation, & vegetation management on various NHS & Non-NHS routes in the Southcoast Region. Design work will be accomplished under this program, and separate projects will be established for the construction phase for each federal fiscal years program. |  | Between $1,000,000 and $2,500,000
SFAPT00289-1 | SR Airport Pavement Markings FFY23 | SFAPT00289-1 | 3-02-0000-027-2020 | Southcoast Region | Regionwide | David B Epstein | (907)465-4483 | 2023-03-01 | Perform SPM at various primary and non-primary airports in SR. Planned maintenance activities include: maintaining pavement markings on runways, taxiways, and aprons at Ketchikan, Petersburg, Wrangell, and Yakutat. |  | Between $500,000 and $1,000,000
SFHWY00308 | WRG ZIMOVIA HWY ROCK FALL MITIGATION HSIP | SFHWY00308 | 3262 | Southcoast Region | Wrangell | Nathan A Purves | (907)465-4521 | 2023-03-01 | Perform slope stabilization and mitigation work at two rock fall sites on Zimovia Highway in Wrangell, Alaska. |  | Between $500,000 and $1,000,000
CFAPT01076 | ANC Gate N7 Passenger Boarding Bridge Replacement Design-Build | CFAPT01076 | AIP 3-02-0016-XXX-2023 | Central Region | Anchorage | Jesse Campbell | (907)266-2723 | 2023-04-01 | Install a new passenger boarding bridge (PBB) at gate N7 in the North Terminal (NT) including new foundation along with mechanical and electrical upgrades. Existing PBB will be removed and disposed. |  | Between $1,000,000 and $2,500,000
CSAPT00932 | ANC NORTH TERMINAL BAGGAGE HANDLING SYSTEM IMPROVEMENTS | CSAPT00932 | N/A | Central Region | Anchorage | Jennifer C Pepin | (907)266-2549 | 2023-04-01 | Upgrade the baggage handling system (BHS) with an automatic sorter and up to three additional induction points. |  | Between $500,000 and $1,000,000
CFAPT01064 | ANC RON 3 & 4 REHABILITATION | CFAPT01064 | 3-02-0016-XXX-2023 | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | 2023-04-01 | Rehabilitions the concrete surface on hardstands RON 3 & 4. |  | Between $1,000,000 and $2,500,000
CFAPT00983 | ANC SECURITY FENCING IMPROVEMENTS 2023 | CFAPT00983 | 3-02-0016-XXX-2023 | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | 2023-04-01 | Remove and replace approximately 1,000 feet of security fence along the northeast edge of the airfield. Project includes clearing, grubbing, embankment extension and replacing swing gates. |  | Between $200,000 and $500,000
CSAPT00858 | ANC SUPPLY WAREHOUSE ROOF REPLACEMENT | CSAPT00858 | N/A | Central Region | Anchorage | Jennifer C Pepin | (907)266-2549 | 2023-04-01 | This project will replace the roof on the 14,400 sf, 1970's era supply warehouse (WH107). Aging and failing roofing will be replaced with new roofing and additional insulation to meet the current requirements. |  | Between $500,000 and $1,000,000
CSAPT00935 | ANC UNDERGROUND STORAGE TANK REPLACEMENT | CSAPT00935 | N/A | Central Region | Anchorage | Jennifer C Pepin | (907)266-2549 | 2023-04-01 | Replace the Underground Storage Tanks (USTs) for the emergency/standby generators at the North Terminal, South Terminal, and the Airport Fire and Police building that were all installed in 1998. The USTs will be replaced with Aboveground Storage Tanks (ASTs). |  | Between $1,000,000 and $2,500,000
SFAPT00399 | Cold Bay Airport Structure Removal | SFAPT00399 | AIP 3-02-0000-027-2020 | Central Region | Cold Bay | Jesse Campbell | (907)266-2723 | 2023-04-01 | This federally funded project includes demolition and removal of two existing hangar buildings, removal of existing fencing, existing tank removal, and utility work in Cold Bay, Alaska as indicated in the contract documents. |  | Between $500,000 and $1,000,000
NFHWY00587 | Edgerton Highway MP 24 - 29 Resurfacing | NFHWY00587 | 850030 | Northern Region | Mccarthy | John J Netardus | (907)451-5448 | 2023-04-01 | Resurface the Edgerton Highway from MP 24 - 29. Project will include drainage improvements, roadside hardware, and utilities. |  | Between $2,500,000 and $5,000,000
NFHWY00420 | Elliott Highway Milepost 51-63 Rehabilitation | NFHWY00420 | 651032 | Northern Region | Livengood | David K Fischer | (907)451-5357 | 2023-04-01 | Rehabilitate the Elliott Highway from MP 51-63 including bridge work (Tolovana River Bridge #0440), roadside hardware, drainage improvements, and utilities. |  | Between $20,000,000 and $30,000,000
NFHWY00633 | FAST Area Surface Upgrades FFY2023 | NFHWY00633 | Pending | Northern Region | Fairbanks North Star Borough | John J Netardus | (907)451-5448 | 2023-04-01 | Resurface pavement, replace pavement markings, replace sidewalk curb with Americans with Disabilities Act (ADA) compliant curb ramps at street corners, improve sidewalks and pedestrian facilities, improve intersections, and install cross culverts on various streets and sidewalks in Fairbanks and North Pole. | Proposed work in 2023 includes, subject to funding availability: Aztec Road Service Area resurfacing (Holmes/Dennis Road area-FNSB) and City of Fairbanks 2nd Avenue dog park access road. Possible College Road RRFB. | Between $1,000,000 and $2,500,000
Z768840000 | Kotzebue to Cape Blossom Road - Stage II | Z768840000 | 2204 | Northern Region | Kotzebue | Jonathan J Hutchinson | (907)451-5479 | 2023-04-01 | Construct a road from Kotzebue to Cape Blossom. Project work will include a new bridge over Sadie Creek (#1596), roadside hardware, drainage improvements, and utilities |  | Between $40,000,000 and $50,000,000
CFAPT00682 | KWETHLUK AIRPORT REHABILITATION | CFAPT00682 | 3-02-0435-002-2023 | Central Region | Kwethluk | Joy A Vaughn | (907)269-0812 | 2023-04-01 | This project will reshape the airport embankment, resurface the airport operating surfaces (runway, taxiway and apron) and access road, and replace the airfield lighting system and electrical enclosure building. Other improvements include clearing and grubbing, replacing culverts, signs, wind cones, segmented circle, aircraft tie downs, rotating beacon, applying dust palliative, and replacing one Snow Removal Equipment Building (SREB) with two heated SREBs including supplemental infrastructure. Utility work will include replacing the power pole and overhead electric line east of the apron. FAA PAPI and REIL underground system and foundations will be replaced, pads resurfaced, and the equipment will be reused. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/8_CFAPT00682_KWT-Plans_PS&E%20Review%20DRAFT.pdf">Preliminary Plans (~20 Mb) </a><br> | Between $20,000,000 and $30,000,000
CFAPT00801 | KWETHLUK AIRPORT SREB | CFAPT00801 | 3-02-0435-002-2023 | Central Region | Kwethluk | Matthew R Epp | (907)764-4881 | 2023-04-01 | This project will design and construct 2 new single bay SREBs to replace an existing and obsolete SREB for the Kwethluk Airport. This project is anticipated to bid with the KWETHLUK AIRPORT REHABILITATION Project.
25C2023065 | Lemon Creek Correctional Center Structural Repairs CM/GC | 25C2023065 | N/A | Southcoast Region | Juneau | Jesse Campbell | (907)266-2723 | 2023-04-01 | This State funded project will provide structural repairs, drainage improvements, interior renovations, and ancillary systems upgrades at the Lemon Creek Correctional Center in Juneau, AK. An optional second phase to provide a new maximum security housing module may be included if funding becomes available. |  | Between $2,500,000 and $5,000,000
CFAPT00882 | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | CFAPT00882 | 3-02-0013-XXX-2023 | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | 2023-04-01 | Rehabilitate the pavement of Aircraft and Lakeshore Dr from Voight Cir to the Lake Hood East property boundary south of runway 14/32. Project includes roadway reconditioning, structural section repairs, drainage improvements, and striping. | Rehabilitate Aircraft and Lakeshore Drive pavement. Includes drainage improvements. | Between $2,500,000 and $5,000,000
25RC053608 | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | 25RC053608 | N/A | Central Region | City & Borough Of Sitka | None | None | 2023-04-01 | This State funded project will replace the windows at Building 295 Heritage Hall at Mt. Edgeucmbe High School, Sitka, Alaska. |  | Between $200,000 and $500,000
25RC053613 | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | 25RC053613 | N/A | Central Region | Sitka | Christopher S Hodgin | (907)269-7484 | 2023-04-01 | This state funded project includes the demolition of the existing kitchen make-up air and exhaust systems and replacement with new systems, at the Mt. Edgecumbe High School Campus in Sitka, Alaska |  | Between $200,000 and $500,000
23-25-1-002 | Peninsula District Paving | 23-25-1-002 | N/A | Central Region | Kenai Peninsula Borough | Vernon S Vreeland | (907)269-0778 | 2023-04-01 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Kenai Peninsula District Boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
NFHWY00278 | Richardson Highway Milepost 233 Bear Creek Bridge #0593 Replacement | NFHWY00278 | 714024 | Northern Region | Delta Junction | Jennifer J Wright | (907)371-8949 | 2023-04-01 | Reconstruct the Richardson Highway between Milepost 232 - 234.5 and replace Bear Creek Bridge #0593. Project will include drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Z607150000 | Richardson Highway MP 266-341 Passing Lanes | Z607150000 | 0A23021 | Northern Region | Fairbanks North Star Borough | Carl F Heim | (907)451-5359 | 2023-04-01 | Construct passing lanes at multiple locations between Milepost 266 and 341 on the Richardson Highway. Work includes roadside hardware, drainage improvements, intersection improvements and utilities. |  | Between $30,000,000 and $40,000,000
z537350000 | 500 Hollywood Drive Structures Removal | z537350000 | N/A | Central Region | Central Region | None | None | 2023-05-01 | This federally funded contract includes the removal and disposal or salvage of all buildings, foundations, fences, structures, old pavements, and any other obstructions and improvements at 500 Hollywood Drive, located in Anchorage, Alaska: |  | Between $200,000 and $500,000
CSAPT00931 | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | CSAPT00931 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | 2023-05-01 | Project will include: 1) constructing a new vehicle access control gate at AFM West; 2) install head bolt outlets (HBO) at the TW A and DeHavilland Avenue snow disposal sites; and 3) re-grade the tug road ditch south of the Trans-northern lease lot. |  | Between $500,000 and $1,000,000
CSAPT00984 | ANC POSTMARK DRIVE REPAIRS 2023 | CSAPT00984 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | 2023-05-01 | Rehabilitate the pavement on Postmark Drive from West Northern Lights Boulevard to approximately Taxiway Uniform Tug Road intersection. Project includes pavement planning, paving, and striping. |  | Between $500,000 and $1,000,000
Z542890000 | BETHEL TUNDRA RIDGE ROAD | Z542890000 | 1207 | Central Region | Bethel | Kelly L Summers | (907)269-0546 | 2023-05-01 | Resurface Tundra Ridge Rd, a distance of about 5,500 feet. |  | Between $2,500,000 and $5,000,000
SFAPT00212 | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | SFAPT00212 | 3-02-0200-120-2018 | Southcoast Region | Regionwide | Peter J Jackson | (907)465-4439 | 2023-05-01 | Remove and replace secondary wind cone and install new conduit and wire. Remove and replace primary wind cone and install new conduit and wire. Remove and replace rotating Airport Beacon. Phase 4 - CC 24300206 LC 33004012 |  | Between $200,000 and $500,000
SFHWY00186 | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | SFHWY00186 | 3244 | Southcoast Region | Ketchikan | Nathan A Purves | (907)465-4521 | 2023-05-01 | Provide additional illumination at the Stedman/Deermount intersection to achieve a level of luminance that meets current DOT&PF standards. Construct a concrete sidewalk bulbout on the Stedman side of the marked crosswalk. The bulbout will extend from the existing sidewalk to the edge of the traveled way. |  | Between $500,000 and $1,000,000
NFHWY00527 | HSIP: Old Steese Highway Shoulder Widening | NFHWY00527 | 2472 | Northern Region | Fox | Carl F Heim | (907)451-5359 | 2023-05-01 | Reconstruct the Old Steese Highway between Gold Dredge #8 and the Fox Intersection. Work includes roadside hardware, drainage improvements, intersection improvements, and utilities. |  | Between $5,000,000 and $10,000,000
SFHWY00259 | JNU KAXDIGOOWU HEEN DEI IMP (BROTHERHOOD BRIDGE TRAIL IMP) | SFHWY00259 | TA18010 | Southcoast Region | Juneau | Peter J Jackson | (907)465-4439 | 2023-05-01 | This project will design and improve the Kaxdigoowu Heen Dei (Kax) Trail from River Road to the edge of Brotherhood Meadow, where a re-route planned for construction in 2019 would end, Work will primarily consist of selected areas of subgrade repair, repave the trail, The pedestrian bridge at Montana Creek will be replaced to provide a larger span that allows for some natural stream movement and can withstand emergency and maintenance vehicle use, and the banks armored to increase the expected useful life of the bridge. |  | Between $1,000,000 and $2,500,000
SFAPT00144 | KDK AIRPORT PERIMETER FENCING UPGRADES | SFAPT00144 | 3-02-0158-0XX-202X | Southcoast Region | Kodiak | James L Brown | (907)465-1796 | 2023-05-01 | Project will replace/upgrade access controls and gates to meet 49 CFR 1542 requirements. Replace existing fencing when needed. |  | Between $5,000,000 and $10,000,000
CFHWY00946 | KENAI PENINSULA BRIDGE DECK REHABILITATIONS FY2023 | CFHWY00946 | 0A33033 | Central Region | Kenai Peninsula | Galen K Jones | (907)269-0550 | 2023-05-01 | This project proposes to make preservation-related improvements to bridges within Kenai Peninsula Borough to reduce future maintenance and extend their serviceable lifespan. Work includes bridge deck polyester concrete overlays, structural retrofits, miscellaneous structural repairs, expansion joints, bridge rail upgrades, guardrail and end terminals, paving, signing, and striping. |  | Between $2,500,000 and $5,000,000
Z680910000 | KTN TONGASS AVE IMPROVEMENTS | Z680910000 | 902042 | Southcoast Region | Ketchikan | Peter J Jackson | (907)465-4439 | 2023-05-01 | Refurbish Tongass Avenue, from MP 0.2010 to 1.2565 including rehabilitation of asphalt and concert pavement surfaces, curb and gutter, sidewalk, correct ADA deficiencies, make improvements to the signalization, lane configurations, and to the pedestrian and bicycle facilities to improve safety and level of service. |  | Between $5,000,000 and $10,000,000
Z614700000 | Little Diomede Helipad Improvements | Z614700000 | 3-02-0381-___-____ | Northern Region | Diomede | Jonathan J Hutchinson | (907)451-5479 | 2023-05-01 | Rehabilitate the rock revetment, helipad surface and the lighting system, and replace the windcone and rotating beacon. |  | Between $5,000,000 and $10,000,000
NFAPT00371 | Marshall Airport Improvements | NFAPT00371 | 3-02-0363-___-____ | Northern Region | Marshall | Christopher F Johnston | (907)451-2322 | 2023-05-01 | Rehabilitate the runway, taxiway, apron, airport access road, and the snow removal equipment building, replace airport lighting and segmented circle, and apply dust palliative. |  | Between $10,000,000 and $20,000,000
23-25-1-001 | Mat-Su High Tower Repairs | 23-25-1-001 | CFHWY00972 | Central Region | Matanuska-Susitna Borough | Vernon S Vreeland | (907)269-0778 | 2023-05-01 | The Contractor shall provide labor, equipment, materials, components, tools, traffic control, mobilization, demobilization and all other incidentals necessary to replace damaged components on high towers and to retrofit lighting to LED as shown in Appendixes and the specifications. Work includes lowering and raising high towers. |  | Between $200,000 and $500,000
CFAPT00269 | MEKORYUK AIRPORT SNOW REMOVAL EQUIPMENT BUILDING | CFAPT00269 | AIP 3-02-0176-003-2022 | Central Region | Mekoryuk | Matthew R Epp | (907)764-4881 | 2023-05-01 | Project will construct a new heated 2-bay SREB, vehicle fueling station.. | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/6_00288%20-%20Mekoryuk%20Airport%20Rehabilitation%20Pre%20PSE-TAS.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $2,500,000 and $5,000,000
SFHWY00375 | NECK LAKE ROAD RECONSTRUCTION SEGMENT 2 WFLHD | SFHWY00375 | AK PFH 58(2) | Southcoast Region | Prince Of Wales Island | Gregory K Lockwood | (907)465-2393 | 2023-05-01 | This project is to provide funding for state support and review of Neck Lake Road Segment 2 design developed under FHWA, Western Federal Lands Highway Division. | Phase 1 of Neck Lake Road Reconstruction will consist of approximately 3.96 miles of road reconstruction on Neck Lake Road beginning at the intersection of NPOWI Highway. The project will be advertised by Western Federal Lands. For more info go to: https://highways.dot.gov/federal-lands/projects/ak/pfh-58-1 | Between $10,000,000 and $20,000,000
CFAPT00993 | ANC TERMINAL WATER MAIN IMPROVEMENTS | CFAPT00993 | N/A | Central Region | Anchorage | Kim D Satterfield | (907)269-0623 | 2023-06-01 | Repair the water main pipes at the South Terminal, North Terminal and Old Field Maintenance. |  | Between $10,000,000 and $20,000,000
Z625970000 | Chalkyitsik Airport Improvements | Z625970000 | 3-02-0046-___-____ | Northern Region | Chalkyitsik | Jonathan J Hutchinson | (907)451-5479 | 2023-06-01 | Resurface the runway, taxiway, apron, and access road and place a dust palliative. Replace airport lighting system and elctrical building. Replace segmented circle and windcone. Construct a new snow removal equipment building. Improve airport drainage and remove obstructions. |  | Between $10,000,000 and $20,000,000
CFHWY00883 | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | CFHWY00883 | 1727 | Central Region | Wasilla | Cynthia L Ferguson | (907)269-0693 | 2023-06-01 | This HSIP project will construct a flashing beacon and load center at the intersection of Church Road and Spruce Ave. Work may include drainage improvements, roadside hardware, ADA improvements (curb ramp & pathway), and utilities. |  | Between $200,000 and $500,000
SFHWY00058-3 | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | SFHWY00058-3 | 958032 | Southcoast Region | Juneau | David A Pyeatt | (907)465-4490 | 2023-06-01 | Work required for this project includes reconstructing and resurfacing Douglas Highway from Egan Drive to about 700 feet south of Cordova Street. Other work includes ADA improvements, storm drain system repairs, signing and striping improvements, and bridge joint repairs. A list of anticipated work items are listed below: • Pavement removal and roadway excavation • Pavement cold planing • Removal and installation of concrete gutter and curb & gutters • Removal and installation of asphalt and concrete sidewalks • Reconstruction of existing accessible sidewalk ramps • Replacement and lining of existing culverts and storm drains • Construction of riprap aprons • Installation of new curb inlets • Removal and installation of storm drain manholes • Replacement of existing signs • Addition of new signs • New pavement markings • Replacement of existing guardrail and bridge transition rail |  | Between $5,000,000 and $10,000,000
CFAPT00288 | MEKORYUK AIRPORT REHABILITATION | CFAPT00288 | 3-02-0176-003-2022 | Central Region | Mekoryuk | Philip W Cheasebro | (907)269-0606 | 2023-06-01 | Rehabilitate/reconstruct runway, taxiway, and access road. Install new lighting. Install new heated two-bay SREB and install dust palliative. | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/6_00288%20-%20Mekoryuk%20Airport%20Rehabilitation%20Pre%20PSE-TAS.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
Z548570000 | SEWARD AIRPORT IMPROVEMENTS | Z548570000 | N/A | Central Region | Seward | Joy A Vaughn | (907)269-0812 | 2023-06-01 | Shift, raise and reconstruct R/W 16/34. Construct Armor protection. Rehabilitate aprons, replace airport lighting, and construct pads for NAVAIDS. Close R/W 13/31, Taxiways A, D, and E. Miscellaneous fencing, signing, etc... |  | Between $20,000,000 and $30,000,000
Z512210000 | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Z512210000 | 1417 | Central Region | Wasilla | Chris L Bentz | (907)269-0652 | 2023-06-01 | Upgrade Seward Meridian to a four-lane roadway and a multi-use, separated pathway along the west side from the Palmer-Wasilla Highway to Bogard Road and extend SMP one mile from Bogard Road to Seldon Road. Intersection improvements include a signal at the Bogard Road intersection and at the Seldon Road intersection. A new bridge, Cottonwood Creek Bridge #1696, would replace the existing culvert at the Cottonwood Creek crossing. | <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/51221/51221_Plans.pdf">Preliminary Plans (~40 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/51221/51221_CrossSections.pdf">Preliminary Cross Sections (~5 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $50,000,000 and $60,000,000
Z581060000 | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Z581060000 | 211052 | Central Region | Kenai Peninsula | Kelly L Summers | (907)269-0546 | 2023-06-01 | Reconstruction and upgrading of 12 miles of Sterling Highway along existing corridor. Project upgrades include widening, construction of passing lanes, resurfacing, scenic turnouts, drainage improvements, minor realignment, and configuration to current AASHTO geometric standards. Also, rehabilitation/replacement of the North Fork Anchor River and Anchor River Bridges. | Reconstruct and upgrade 12 miles of the Sterling Hwy along the existing corridor from Anchor Pt to Baycrest Hill. Replacement of North Fork Anchor River and Anchor River Bridges. Project upgrades include widening, construction of passing lanes, resurfacing, drainage improvements, minor realignment, and configuration to current AASHTO geometric standards. | Between $80,000,000 and $90,000,000
CFAPT00835 | ANC TAXIWAY Z IMPROVEMENTS EAST | CFAPT00835 | N/A | Central Region | Anchorage | Philip W Cheasebro | (907)269-0606 | 2023-07-01 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron.
CFHWY00395 | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | CFHWY00395 | 1642 | Central Region | Anchorage | Cynthia L Ferguson | (907)269-0693 | 2023-07-01 | Pavement Preservation project for Elmore Road: Abbott Rd. to Providence Dr. This project includes resurfacing, roadside hardware, drainage improvements, intersection improvements, and ADA improvements as necessary. |  | Between $10,000,000 and $20,000,000
CFHWY00523 | GLENN HIGHWAY BRIDGE DECK PRESERVATION | CFHWY00523 | 1685 | Central Region | Central Region | Christina A Huber | (907)269-0572 | 2023-07-01 | Pavement preservation, bridge work, roadside hardware, drainage improvements, and utilities. |  | Between $5,000,000 and $10,000,000
CFHWY00991 | HSIP: STERLING HIGHWAY SHOULDER WIDENING MP 157-169 | CFHWY00991 | 211052 | Central Region | Kenai Peninsula | Kelly L Summers | (907)269-0546 | 2023-07-01
CFHWY00253 | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | CFHWY00253 | 221019 | Central Region | Kenai | Alex L Read | (907)269-0641 | 2023-07-01 | This project will rehabilitate the Kenai Spur Highway between Soldotna and Kenai. A 5-lane highway will be constructed between the Sports Lake Road and Robin Drive intersections to increase capacity and improve safety. This is the second of two phases to construct the project. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00253/00253.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $40,000,000 and $50,000,000
Z525710000 | KWIGILLINGOK AIRPORT IMPROVEMENTS | Z525710000 | N/A | Central Region | Kwigillingok | Joy A Vaughn | (907)269-0812 | 2023-07-01 | Reconstruct and extend Kwigillingok Airport to community class standards. Will acquire ROW, improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building(s). | Reconstruct and extend Kwigillingok Airport to community class standards. Improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building. Actual Advertising Date contingent upon federal funding availability. Check back often for updates.
CFHWY00943 | SEWARD HWY STERLING HWY INTERSECTION IMPROVEMENTS | CFHWY00943 | 0A32025 | Central Region | Cooper Landing | Julia R Hanson | (907)269-0753 | 2023-07-01 | Construct improvements to the Seward Highway and Sterling Highway intersection to improve traffic flow and safety. | The project will be delivered using the Progressive Design-Build method. | Between $20,000,000 and $30,000,000
SFAPT00250 | FFY20 VAR NON-PRIMARY VISUAL AID REPLACEMENT | SFAPT00250 | 3-02-0200-132-2020 | Southcoast Region | Regionwide | Peter J Jackson | (907)465-4439 | 2023-08-01 | Remove the existing airport beacon and tower and replace with new beacon and tip down tower.
SFAPT00328 | HYG - HYDABURG SEAPLANE FACILITY REFURBISHMENT | SFAPT00328 | N/A | Southcoast Region | Hydaburg | David H Lowell | (907)465-4812 | 2023-08-01 | Refurbish and/or replace existing seaplane float facility in Hydaburg, AK. Investigate replacement at a new location |  | Between $5,000,000 and $10,000,000
SFAPT00327 | KTN AIRPORT SEAPLANE RAMP AND HAUL OUT REFURBISHMENT | SFAPT00327 | N/A | Southcoast Region | Ketchikan | Loren K Gehring | (907)465-8189 | 2023-08-01 | Refurbish and/or replace existing seaplane float and haul-out ramp facility at the Ketchikan Airport. Investigate replacement at a new location. |  | Between $1,000,000 and $2,500,000
SFHWY00070 | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | SFHWY00070 | 3225 | Southcoast Region | Ketchikan | Kirk D Miller | (907)465-1215 | 2023-08-01 | This project will replace or rehabilitate the Sayles/Gorge Street Viaduct (#1841). | Remove and replace existing bridge structure. | Between $2,500,000 and $5,000,000
CFHWY01083 | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | CFHWY01083 | N/A | Central Region | Wasilla | Tom J Schmid | (907)269-0543 | 2023-08-01 | Culvert replacement, drainage improvements, ditch grading, guardrail, signage, utility relocations, clearing and grubbing. This Child Project will construct the first phase of improvements included in the Parent Project CFHWY00592. . | Replacing 10 critical culverts along the Parks Highway. | Between $5,000,000 and $10,000,000
CFHWY00592 | PARKS HWY MP 99 - 163 Drainage & Culvert Improvements | CFHWY00592 | 0A41042 | Central Region | Matanuska-Susitna Borough | Tom J Schmid | (907)269-0543 | 2023-08-01 | Project will construct improvements to drainage including culvert repair, replacement, and new installations, as necessary to provide adequate drainage. |  | Between $5,000,000 and $10,000,000
SFHWY00404 | SR REGIONWIDE GUARDRAIL INVENTORY AND UPGRADE HSIP | SFHWY00404 | 3278 | Southcoast Region | Regionwide | Nathan A Purves | (907)465-4521 | 2023-08-01 | Assess and correct guardrail safety deficiencies along Principal and Minor Arterial routes with posted speeds of 40 mph or higher. Typical deficiencies include, but are not limited to, steel washers on the face of rail, insufficient length of need, steel blockouts without backup plates, and break away cable terminals.
CFAPT00992 | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | CFAPT00992 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | 2023-09-01 | Reconstruct approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, new structural section, drainage improvements and pavement markings. |  | Between $2,500,000 and $5,000,000
CFHWY00260 | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | CFHWY00260 | AKBLM AFO 2014(1) | Central Region | Anchorage | Cynthia L Ferguson | (907)269-0693 | 2023-09-01 | Relocate the BLM Road to the Cambell Tract Facility 260 feet to align East 68th Avenue with intersection improvements to include bus stop and integration to existing signalized intersection. |  | Between $5,000,000 and $10,000,000
CFHWY00286 | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | CFHWY00286 | 510007 | Central Region | Anchorage | Jon W Knowles | (907)269-0643 | 2023-09-01 | Pavement Preservation of DeArmoun Rd. from East 140th Avenue to Hillside Drive including improvements to drainage, intersections, ADA, roadside hardware, and utilities. High Friction Surface Treatment may be reapplied. |  | Between $2,500,000 and $5,000,000
NFHWY00097 | HSIP: RICHARDSON HWY MP 351 INTERCHANGE | NFHWY00097 | 0A24034 | Northern Region | North Pole | David K Fischer | (907)451-5357 | 2023-09-01 | REVISED SCOPE: Reconstruct the Old Richardson Highway and Richardson Highway intersection at MP 351 of the Richardson Highway. Work will include intersection improvements, bridge work, roadside hardware, drainage improvements, and utilities. Additional work includes construction of new frontage roads and reconstruction of a portion of Keeney Road. | Construct an overpass at the Old Richardson Hwy (12 Mile) and relocate the intersection of Old Rich and Richardson Hwy, including realigning access of Keeney Road. | Between $20,000,000 and $30,000,000
SFHWY00485 | JNU WAYDELICH CREEK: LOWER WALL REPAIRS | SFHWY00485 | 933050 | Southcoast Region | Juneau | Joel D Osburn | (907)465-4409 | 2023-09-01 | This project will repair the damage & deterioration to the lower part of the retaining wall at Waydelich Creek. Repairs may include, but are not limited to embankment, geotextile, concrete, steel reinforcement, riprap, drainage, roadside hardware, and utilities. |  | Between $200,000 and $500,000
SFHWY00414 | JNU WAYDELICH CREEK: UPPER WALL REPAIRS - DEC 20 SE PR | SFHWY00414 | 93003 | Southcoast Region | Juneau | Joel D Osburn | (907)465-4409 | 2023-09-01 | This project will construct permanent repairs (PR) to the upper portion of the Waydelich Creek retaining wall damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK2021-1 JNS003. Repairs may include, but are not limited to, asphalt, embankment, geotextile, concrete, steel reinforcement, riprap, drainage, roadside hardware, and utilities. |  | Between $200,000 and $500,000
CFHWY00012 | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | CFHWY00012 | 537008 | Central Region | Anchorage | Christina A Huber | (907)269-0572 | 2023-09-01 | This federally funded project will reconstruct the Seward Highway between O'Malley Road and Dimond Blvd. Work may include: new north and south bound lanes and auxiliary lanes, a new interchange connecting 92nd Avenue to Academy Drive, reconstruction of the existing interchanges within the project limits, construction and reconstruction of frontage roads, pathway and sidewalk improvements, noise walls and drainage improvements. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00012/00012_Plans.pdf">Preliminary Plans (~150 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $90,000,000 and $100,000,000
SFHWY00103 | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | SFHWY00103 | 3214 | Southcoast Region | Sitka | Nathan A Purves | (907)465-4521 | 2023-10-01 | Provide additional illumination at the Halibut Point Road/Peterson Avenue Intersection to achieve a level of luminance that meets current DOT&PF standards. Modify adjacent roadway lighting as needed to maintain satisfactory continuous illumination. Establish a pass-through crossing to facilitate less challenging pedestrian movements. Improve intersection sight distance by removing utility equipment located in the southeast quadrant of the intersection, acquiring property to remove parking spaces that, when occupied, create sight line obstructions, and modifying access to an apartment building adjacent to the intersection (shorten curb cut). Replace existing S1-1 School signs with W11-2 advance pedestrian warning signs. |  | Between $1,000,000 and $2,500,000
CFHWY00622 | WASILLA-FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVE PRESERV | CFHWY00622 | 1700 | Central Region | Wasilla | Chris L Bentz | (907)269-0652 | 2023-10-01 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities.
Z686060000 | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Z686060000 | 956028 | Southcoast Region | Haines | Gregory K Lockwood | (907)465-2393 | 2023-11-01 | Reconstruction of Haines Highway from Milepost 20 to 25 including the Chilkat River bridge. | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise | Between $40,000,000 and $50,000,000
Z631860000 | Richardson Highway MP 148-173 (CONST MP 167-173) | Z631860000 | 713010 | Northern Region | Paxson | Russell M Johnson | (907)451-5059 | 2023-11-01 | Reconstruct the Richardson Highway between MP 167 and 173. Project includes roadside hardware, drainage improvements and utility relocations. | Reconstruct the Richardson Highway between mileposts 167-173. | Between $20,000,000 and $30,000,000
Z680850000 | SGY STATE STREET PAVEMENT REHABILITATION | Z680850000 | 972018 | Southcoast Region | Skagway | David A Pyeatt | (907)465-4490 | 2023-11-01 | Rehabilitate the pavement, replace curb and gutter in select areas, upgrade curb ramps and vehicular curb cuts to meet ADA standards, repair and/or replace drainage facilities as needed, and replace all signs within the project limits. | Rehabilitate the pavement from 1st Avenue to the Skagway River Bridge. Repair and/or replace existing drainage infrastructure. Replace existing sidewalk, curb ramps, and driveways to meet current ADA requirements. | Between $20,000,000 and $30,000,000
CFHWY00731 | AMATS: EAGLE RIVER LOOP RD - EAGLE RIVER RD TO OLD GLENN HWY | CFHWY00731 | 1694 | Central Region | Eagle River | Julia R Hanson | (907)269-0753 | 2023-12-01 | Pavement preservation, which may include improvements to roadside hardware, drainage, intersections, automated traffic recorders, pedestrian facilities, striping, signs, and utilities. | Project will be combined with CFHWY00621 North Eagle River Access Road Pavement Preservation | Between $2,500,000 and $5,000,000
SDRER00436 | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | SDRER00436 | N/A | Southcoast Region | Haines | Joel D Osburn | (907)465-4409 | 2023-12-01 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Disaster Inventory Numbers 461219, 461641, 548035, and 461258. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Mud Bay Road, Sawmill Road, and at the DOT&PF Maintenance Yard. This project is funded by FEMA. |  | Between $1,000,000 and $2,500,000
SFHWY00359 | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | SFHWY00359 | 3267 | Southcoast Region | Juneau | Brett M Wells | (907)465-1607 | 2023-12-01 | Replace the twin culverts at Bridget Cove Creek. |  | Between $500,000 and $1,000,000
SFHWY00438 | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | SFHWY00438 | 93005 | Southcoast Region | Juneau | Joel D Osburn | (907)465-4409 | 2023-12-01 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK 2021 01 JNU002, AK 2021 01 JNU004, AK 2021 01 JNU005, and AK 2021 01 JNU006. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Glacier Highway/Lemon Road, Egan Drive/Glacier Highway, and Glacier Highway/Twin Lakes Drive. This project is funded by FHWA. |  | Between $1,000,000 and $2,500,000
CFHWY00621 | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | CFHWY00621 | 1692 | Central Region | Eagle River | Julia R Hanson | (907)269-0753 | 2023-12-01 | This preventative maintenance project will resurface North Eagle River Access Road and may include as necessary; signing and striping, guardrail and other roadside hardware, signalization, lighting, drainage work, dig-outs, bridge repair, curb ramps, automated traffic recorders, and utility relocation. | Project will be combined with CFHWY00731 AMATS: Eagle River Loop Road Pavement Preservation. | Between $1,000,000 and $2,500,000
NFHWY00218 | RICHARDSON HWY MP 82-115 RESURFACING (CONST MP 97-115) | NFHWY00218 | 712035 | Northern Region | Valdez | Russell M Johnson | (907)451-5059 | 2023-12-01 | Resurface the Richardson Highway from MP 97 - 115. Improvements include bridge work, drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Z620030000 | SEPPALA DRIVE UPGRADE | Z620030000 | 000S828 | Northern Region | Nome | Christopher F Johnston | (907)451-2322 | 2023-12-01 | Realign and rehabilitate Seppala Drive in Nome. Work includes pavement rehabilitation, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. |  | Between $10,000,000 and $20,000,000
SFAPT00412 | WRG GATES AND SECURITY UPGRADES | SFAPT00412 | N/A | Southcoast Region | Wrangell | David B Epstein | (907)465-4483 | 2023-12-01 | Replace automated vehicle gate 3; Replace and widen vehicle gate 9 from 20' to 24'; Replace non-automated vehicle gate 10; Replace locking systems for vehicle gates 3 and 9; Replace locking systems for fence pedestrian gates 4 and 11; Remove vehicle gates 5 and 6 and replace with fence; Replace and relocate pedestrian gate 11; Repair approximately 1200-1500 feet of fence line. |  | Between $1,000,000 and $2,500,000
SAMHS00419 | AMHS JNU AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | SAMHS00419 | 933048 | Marine Highways | Juneau | Misty L Butler | (907)465-4414 | 2024-01-01 | Make improvements to the AMHS Auke Bay Terminal East Berth. Work would include: Replacement of mooring dolphins, refurbish/replace transfer bridge and support float, install mechanical and electrical upgrades. |  | Between $5,000,000 and $10,000,000
SFHWY00326 | COLD BAY TROUT CREEK CULVERTS WFL | SFHWY00326 | 3265 | Southcoast Region | Cold Bay | Brett M Wells | (907)465-1607 | 2024-01-01 | Replace two damaged culverts with new Aquatic Organism Passage structures across Trout Creek and Little Trout Creek in Cold Bay, AK. |  | Between $2,500,000 and $5,000,000
NFHWY00588 | ELLIOTT HIGHWAY MP 18 - 29 RESURFACING | NFHWY00588 | 650035 | Northern Region | Livengood | John J Netardus | (907)451-5448 | 2024-01-01 | Resurface the Elliott Highway from MP 18 - 29. Project will include selected areas of roadway rehabilitation, bridge work, drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
SFHWY00111 | KDK CHINIAK HIGHWAY REHABILITATION: MILE POST 15 TO 31 | SFHWY00111 | 391015 | Southcoast Region | Kodiak | James L Brown | (907)465-1796 | 2024-01-01 | Rehabilitate the Chiniak Highway from Milepost 15 to just past 31 to improve and preserve the roadway subgrade and surface. Address lighting, guardrails, drainage, culverts and other highway appurtenances as needed. |  | Between $10,000,000 and $20,000,000
SFHWY00184 | KTN AIRPORT FERRY CAPACITY MODIFICATIONS (GRAVINA) | SFHWY00184 | 3233 | Southcoast Region | Ketchikan | Kirk D Miller | (907)465-1215 | 2024-01-01 | Modify existing airport ferry vessel to expand passenger and vehicle space. | Modify Airport Ferry Shuttle to accommodate more passengers. Project construction not funded. This project is cancelled. | Between $200,000 and $500,000
CFAPT00937 | SELDOVIA AIRPORT IMPROVEMENTS | CFAPT00937 | 3-02-0258-XXX-202X | Central Region | Seldovia | Kim D Satterfield | (907)269-0623 | 2024-01-01 | Rehabilitate the runway, apron, and segmented circle access. Construct a new taxilane to the east of the existing apron. Replace culverts and improve drainage as needed. |  | Between $10,000,000 and $20,000,000
SFHWY00377 | CRAIG ADA IMPROVEMENTS | SFHWY00377 | 3274 | Southcoast Region | Craig | Bran P Pollard | (907)465-4526 | 2024-02-01 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit. |  | Between $2,500,000 and $5,000,000
CFHWY00394 | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | CFHWY00394 | 0A15039 | Central Region | Statewide | Kristina H Busch | (907)269-0567 | 2024-02-01 | Resurface the Glenn Highway from Kings River bridge to Cascade. Additional improvements may include bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities as necessary. Project construction may be phased. |  | Between $10,000,000 and $20,000,000
CFHWY00392 | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | CFHWY00392 | 1686 | Central Region | Big Lake | Alex L Read | (907)269-0641 | 2024-02-01 | Pavement preservation, roadside hardware, structural improvement in limited areas, minor drainage and/or safety improvements, utility adjustment/relocation, signing and striping. |  | Between $5,000,000 and $10,000,000
CFHWY00856 | HSIP: 5TH AVE: CONCRETE ST TO KARLUK ST PEDESTRIAN IMPROVMNT | CFHWY00856 | 421102 | Central Region | Anchorage | Cynthia L Ferguson | (907)269-0693 | 2024-02-01 | This HSIP project will construct a median barrier on 5th Avenue between Concrete Street and the couplet of 5th and 6th Avenues (Karluk Street). Work may include roadside hardware, drainage, improvements, and utilities.
SFHWY00403 | JNU L00P RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | SFHWY00403 | 966030 | Southcoast Region | Juneau | Nathan A Purves | (907)465-4521 | 2024-02-01 | Construct a single-lane roundabout at the Loop Road - Mendenhall Boulevard - Valley Boulevard intersection.
SFAPT00178 | UNALASKA TAXIWAY AND APRON REHABILITATION | SFAPT00178 | N/A | Southcoast Region | Unalaska | Gregory K Lockwood | (907)465-2393 | 2024-02-01 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
CFHWY00586 | AMATS: DOWNTOWN TRAIL CONNECTION | CFHWY00586 | 1662 | Central Region | Anchorage | Kristina H Busch | (907)269-0567 | 2024-03-01 | Project will construct a connection between the Tony Knowles Coastal Trail to the Ship Creek Trail in downtown Anchorage. Major Project Elements include Bridge Work (Pedestrian), Roadside Hardware, Drainage Improvements, Intersection Improvements and ADA Improvements.
CFAPT00880 | ANC TAXIWAY R NORTH IMPROVEMENTS | CFAPT00880 | N/A | Central Region | Anchorage | Matthew H Hansen | (907)269-0602 | 2024-03-01 | This project will design and construct improvements for TW R from approximately TL P to TW Q for Airplane Design Group 6. |  | Between $10,000,000 and $20,000,000
Z537250000 | CHEVAK AIRPORT REHABILITATION | Z537250000 | 3-02-0468-00X-202X | Central Region | Chevak | Aaron C Hughes | (907)269-0523 | 2024-03-01 | This project will rehabilitate the runway, taxiway, apron, and airport access road. The runway safety area will be expanded, and runway grades will be corrected to meet line-of-sight requirements. Additional improvements include replacement of airfield lighting, FAA navaids, wind cones, segmented circle, build a supplemental wind cone access, and apply dust palliative. |  | Between $10,000,000 and $20,000,000
SFAPT00236 | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | SFAPT00236 | N/A | Southcoast Region | Hoonah | Loren K Gehring | (907)465-8189 | 2024-03-01 | Relocation of an existing stream bed and conduct dredging under the seaplane mooring float to restore sufficient water depths and/or relocation of the seaplane float structure to deeper water at the same location. Phase: T02000 - Par - All Costs | Construction funding uncertain. | Between $500,000 and $1,000,000
CFHWY00502 | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | CFHWY00502 | 0A31063 | Central Region | Anchorage | Cynthia L Ferguson | (907)269-0693 | 2024-03-01 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards.
CFHWY00503 | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | CFHWY00503 | 1644 | Central Region | Anchorage | Cynthia L Ferguson | (907)269-0693 | 2024-03-01 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements.
SFHWY00260 | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | SFHWY00260 | 3247 | Southcoast Region | Kodiak | Bran P Pollard | (907)465-4526 | 2024-03-01 | Resurface Rezanoff Drive from Marine Way to the airport. Associated preventative maintenance activities may include minor structural section improvements, drainage repairs, lighting and signals, striping, signs, and ADA improvements. Project Location and Length: Rezanoff Drive from Marine Way to the airport for an approximate length of 4.70 miles. | (Design by Northern Region) | Between $10,000,000 and $20,000,000
CFHWY01084 | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | CFHWY01084 | N/A | Central Region | Wasilla | Tom J Schmid | (907)269-0543 | 2024-03-01 | New bridge, drainage improvements, ditch grading, guardrail, signage, utility relocations, clearing and grubbing. This Child Project will construct the second phase of improvements included in the Parent Project CFHWY00592. | Construct a bridge at Railroad Creek at MP128.5 along the Parks Highway. | Between $5,000,000 and $10,000,000