## 2022.06.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (1) [on 2022.03.15 the ANTADVDT changed to May 2022.] | A STREET, NORTHERN LIGHTS TO 40TH AVE PAVEMENT PRESERVATION | Anchorage | 2022-05-01 | CFHWY00223 | CFHWY00223 | 527030 | Kevin L Jackson | (907)269-0610 | Pavement preservation of A Street from Northern Lights Blvd to 40th Ave including improvements to drainage, intersections, ADA, roadside hardware, and utilities. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | Glenn Hwy MP 116 Paving | Matanuska-Susitna Borough | 2022-05-01 | 22-25-1-011 | 22-25-1-011 | N/A | Burrell L Nickeson | (907)269-0757 | This State-funded project is to perform asphalt paving and maintenance work on the Glenn Highway at MP 116. Striping and Traffic Control will be performed by DOT&PF. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (1) [on 2022.03.15 the ANTADVDT changed to May 2022.] | HSIP: A ST. MIDTOWN COUPLET OVERHEAD SIGNAL INDICATION U/G | Anchorage | 2022-05-01 | CFHWY00677 | CFHWY00677 | 1684 | Kevin L Jackson | (907)269-0610 | Upgrade roadside hardware on A Street between Benson Boulevard and Northern Lights Boulevard. Work incudes removing and replacing the traffic signals at the intersection of Benson Boulevard and A Street and Northern Lights Boulevard and A Street and lighting system replacment adjacent to intersections. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | Scammon Bay Airport (SCM) Surface Preservation Maintenance (SPM) | Scammon Bay | 2022-05-01 | 22-25-1-002 | 22-25-1-002 | 3-02-0255-XXX-2022 | Jeremy R Thompson | (907)338-1466 | Provide and compact Crushed Aggregate Surface Course (CASC). Surface course to be applied to RWY 10/28 (3,000 LF), TWY (175 LF) and (apron 8,333 SY) as needed.
Central Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | Scammon Bay Airport (SCM) Surface Preservation Maintenance (SPM) | Scammon Bay | 2022-05-01 | CFAPT00911 | CFAPT00911 | 3-02-0255-XXX-2022 | Jeremy R Thompson | (907)338-1466 | This federally funded contract provides a new crushed aggregate surface at the Scammon Bay Airport. Work includes new surface course material on the runway, taxiway, and apron.
Central Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | YKCC Mechanical Upgrades Phase 2 | Bethel | 2022-05-01 | 25RC201621 | 25RC201621 | N/A | Jesse Campbell | (907)269-0820 | This State funded project will provide mechanical and boiler upgrades at the Yukon-Kuskokwim Correctional Center in Bethel, Alaska. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.03.15 project was added.] | ANC TAXIWAY Z IMPROVEMENTS EAST | Anchorage | 2023-02-01 | CFAPT00835 | CFAPT00835 | N/A | Philip W Cheasebro | (907)269-0606 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron.
Central Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | HSIP: PALMER-FISHHOOK ROAD & TRUNK ROAD ROUNDABOUT | Palmer | 2023-03-01 | CFHWY00829 | CFHWY00829 | 441010 | Galen K Jones | (907)269-0550 | The project will reconstruct the three-leg intersection of Palmer-Fishhook Rd and Trunk Rd. This project may also include roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities.
Central Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | SEWARD AIRPORT IMPROVEMENTS | Seward | 2023-03-01 | Z548570000 | Z548570000 | N/A | Joy A Vaughn | (907)269-0812 | Shift, raise and reconstruct R/W 16/34. Construct Armor protection. Rehabilitate aprons, replace airport lighting, and construct pads for NAVAIDS. Close R/W 13/31, Taxiways A, D, and E. Miscellaneous fencing, signing, etc... |  | Between $20,000,000 and $30,000,000
Central Region | ADDED |  |  |  | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-01-01 | CFAPT00682 | CFAPT00682 | 3-02-0435-TBD | Joy A Vaughn | (907)269-0812 | Rehabilitate the airport runway, taxiway, safety areas, apron and access road. Replace lighting, nav-aids, the existing SREB and improve drainage. Remove OFA obstructions.
Central Region | ADDLINFO | Resurface Minnesota Drive in Anchorage, Alaska from Tudor Road to 15th Avenue. It will also include, roadside hardware, drainage, signalization, ADA curb ramp improvements. This project will be advertised with CFHWY00366 HSIP Anchorage Pedestrian Lighting. | This project will be advertised with CFHWY00366 HSIP Anchorage Pedestrian Lighting. <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00132/00132_Plans.pdf">Preliminary Plans (~27 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (6) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 ADDLINFO changed.] | MINNESOTA DR: TUDOR TO 15TH AVE PAVEMENT PRESERVATION | Anchorage | 2022-06-01 | CFHWY00132
Central Region | ANTADVDT | 2022-05-01 | 2022-06-01 | (1) [on 2022.05.16 project was added.] | Boney Courthouse Mechanical Upgrades and Earthquake Repairs - Rebid | Anchorage | 2022-06-01 | 2501000113-A
Central Region | ANTADVDT | 2022-05-01 | 2022-06-01 | (1) [on 2022.05.16 project was added.] | Boney Courthouse Plaza Earthquake Repair | Anchorage | 2022-06-01 | 25RC091612
Central Region | ANTADVDT | 2022-05-01 | 2022-08-01 | (4) [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.05.16 DESCRIPTION changed.]; [on 2022.05.16 FEDNUM changed.] | SLEETMUTE AIRPORT RESURFACING | Sleetmute | 2022-08-01 | CFAPT00293
Central Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (2) [on 2022.03.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to June 2022.] | KONGIGANAK AIRPORT IMPROVEMENTS | Kongiganak | 2022-07-01 | CFAPT00433
Central Region | ENGEST | Between $500,000 and $1,000,000 | Between $1,000,000 and $2,500,000 | (2) [on 2022.04.15 the ANTADVDT changed to April 2022.]; [on 2022.05.16 the ANTADVDT changed to June 2022.] | Ketchikan Pioneer Home Structural Upgrades | Central Region | 2022-06-01 | 2501000083
Central Region | PROJNAME | PARKS HWY MP 99 - 163 DRAINAGE & CULVERT IMPROVEMENTS | PARKS HWY MP 99 - 163 Drainage & Culvert Improvements | (1) [on 2022.04.15 project was added.] | PARKS HWY MP 99 - 163 Drainage & Culvert Improvements | Matanuska-Susitna Borough | 2023-03-01 | CFHWY00592
Marine Highways | ENGEST | Between $2,500,000 and $5,000,000 | Between $1,000,000 and $2,500,000 | (1) [on 2022.04.15 the ANTADVDT changed to August 2022.] | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | Ketchikan | 2022-08-01 | Z674660000
Marine Highways | PROJNAME | KTN FERRY TERMINAL IMPROVEMENTS (X-REF#SAMHS00015) | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | (1) [on 2022.04.15 the ANTADVDT changed to August 2022.] | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | Ketchikan | 2022-08-01 | Z674660000
Northern Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | Little Tonsina Access Road Bridge | Tonsina | 2022-05-01 | NRMBS00410 | NRMBS00410 | N/A | David M Arvey | (907)451-2621 | Replace the Little Tonsina River culverts with a new bridge; Little Tonsina River Bridge #568, on Burma Pit Road near MP 74.2 of the Richardson Highway. |  | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  | (3) [on 2022.04.15 FEDNUM changed.]; [on 2022.04.15 LOCATION changed.]; [on 2022.05.16 FEDNUM changed.] | Northern Region ADA Improvements - Fairbanks: 6th Avenue | Fairbanks North Star Borough | 2022-05-01 | NFHWY00551 | NFHWY00551 | 2511 | Ivet Hall | (907)451-5386 | This project proposes to reconstruct ADA improvements and potentially widen the north sidewalk on the 6th Avenue in Fairbanks, Alaska. The project may also include reconstruction, roadside-hardware, drainage improvements, intersection improvements and utilities. | Anticipated to advertise with NFHWY00504 project. | Between $500,000 and $1,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.04.15 DESCRIPTION changed.] | Northern Region ADA Improvements - Fairbanks: Geist Road | Fairbanks | 2022-05-01 | NFHWY00504 | NFHWY00504 | Pending | Ivet Hall | (907)451-5386 | This project proposes to reconstruct ADA improvements and potentially widen sidewalks on both sides of Geist Road within the project area in Fairbanks, Alaska. The project may also include reconstruction, roadside hardware, drainage improvements, intersection improvements and utilities. | Anticipated to advertise with NFHWY00551 project. | Between $500,000 and $1,000,000
Northern Region | (DELETED) |  |  | (3) [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.04.15 PROJNAME changed.] | Northern Region Digital Message Signs (TAG) | Fairbanks North Star Borough | 2022-05-01 | 25RC182609 | 25RC182609 | N/A | Ethan E Graetz | (907)451-2281 | Install and operate digital messaging signs on the Parks Highway MP 357 and Richardson Highway MP 359. |  | Between $2,500,000 and $5,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.02.22 the ANTADVDT changed to July 2022.] | Deering Airport Improvements | Deering | 2022-07-01 | NFAPT00249 | NFAPT00249 | 3-02-0400-XX-202X | Jonathan J Hutchinson | (907)451-5479 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  |  | ELLIOTT HIGHWAY MP 18 - 29 RESURFACING | Livengood | 2022-11-01 | NFHWY00588 | NFHWY00588 | 650035 | John J Netardus | (907)451-5448 | Resurface the Elliott Highway from MP 18 - 29. Project will include selected areas of roadway rehabilitation, bridge work, drainage improvements, roadside hardware, and utilities.
Northern Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | BUCKLAND AIRPORT IMPROVEMENTS | Buckland | 2023-03-01 | NFAPT00604 | NFAPT00604 | N/A | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate the runway and taxiway, stabilize the embankments, resurface the airport access road, apply dust palliative, and replace the airport lighting system. |  | Between $5,000,000 and $10,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | Manley Airport Improvement | Manley | 2023-03-01 | NFAPT00363 | NFAPT00363 | 3-02-0170-XXXX | Jonathan J Hutchinson | (907)451-5479 | Construct a new apron and taxiway, install taxiway lighting, address apron electrical issues, and apply dust palliative to airport operational surfaces. | Shelf Ready in 22 | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  | Northern Region Digital Message Signs (CMAQ) | Fairbanks North Star Borough | 2022-07-01 | NFHWY00707 | NFHWY00707 | Pending | Ethan E Graetz | (907)451-2281 | Install and operate digital messaging signs on the Parks Highway MP 357 and Richardson Highway MP 359. |  | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  | Murphy Dome Road Preventive Maintenance Surface Repairs | Fairbanks North Star Borough | 2022-09-01 | NFHWY00702 | NFHWY00702 | N/A | None | None | Reclaim, reshape, and resurface a section of Murphy Dome Road
Northern Region | ADDED |  |  |  | Parks Hwy MP 319-325 Reconstruction | Nenana | 2022-09-01 | Z606570000 | Z606570000 | 0A45028 | Jennifer J Wright | (907)371-8949 | Reconstruct the Parks Highway from MP 319-325. Project will include realignment, roadside hardware, drainage improvements and utilities. | Project will be advertised as CMGC RFP. Project website: https://dot.alaska.gov/nreg/parks305to325/ | Between $50,000,000 and $60,000,000
Northern Region | ADDED |  |  |  | Old Steese Highway Reconstruction | Fairbanks | 2022-10-01 | Z624870000 | Z624870000 | N/A | Russell M Johnson | (907)451-5059 | Revised Scope: Reconstruct the Old Steese Highway from 3rd Street to, and including, the intersection at Johansen Expressway. | Project will be advertised as CMGC RFP. Project website: https://dot.alaska.gov/nreg/oldsteese/ | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  | FIA GA APRON AND TAXIWAY RECONSTRUCTION | Fairbanks North Star Borough | 2023-03-01 | NFAPT00689 | NFAPT00689 | N/A | RJ Stumpf | (907)474-2587 | Reconstruct the general aviation apron and associated taxiways, replace taxiway lighting, and other improvements as funding allows.
Northern Region | ADDLINFO | CY21 and CY22 |  | (4) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 FEDNUM changed.]; [on 2022.05.16 ENGEST changed.] | Point Hope Airport Realignment | Point Hope | 2022-06-01 | Z638420000
Northern Region | ADDLINFO |  | Single chip seal overlay proposed. | (1) [on 2022.02.22 project was added.] | CHENA RIDGE ROAD AND CHENA PUMP ROAD RESURFACING | Fairbanks North Star Borough | 2023-01-01 | NFHWY00570
Northern Region | ADDLINFO |  | Proposed work in 2023 includes, subject to funding availability: Aztec Road Service Area resurfacing (Holmes/Dennis Road area-FNSB) and City of Fairbanks 2nd Avenue dog park access road. | (1) [on 2022.03.15 project was added.] | FAST AREA SURFACE UPGRADES FFY2023 | Fairbanks North Star Borough | 2023-02-01 | NFHWY00633
Northern Region | ANTADVDT | 2022-05-01 | 2022-06-01 | (4) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 FEDNUM changed.]; [on 2022.05.16 ENGEST changed.] | Point Hope Airport Realignment | Point Hope | 2022-06-01 | Z638420000
Northern Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (2) [on 2022.02.22 PROJNAME changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.] | Copper River Boat Launch Facilities Improvements (FLAP) | Mccarthy | 2022-07-01 | NFHWY00539
Northern Region | ENGEST |  | Between $2,500,000 and $5,000,000 |  | EDGERTON HWY MP 24 - 29 RESURFACING | Mccarthy | 2022-10-01 | NFHWY00587
Northern Region | ENGEST |  | Between $20,000,000 and $30,000,000 | (4) [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.05.16 PROJNAME changed.] | Richardson Highway MP 128-138 Rehabilitation | Tazlina | 2022-11-01 | NFHWY00265
Northern Region | LOCATION | Northern Region | Livengood | (4) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 ENGEST changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.] | Dalton Highway MP 18-37 Reconstruction | Livengood | 2022-07-01 | Z607350000
Northern Region | PROJMAN | Colleen M Ackiss | None | (7) [on 2022.02.22 PROJNAME changed.]; [on 2022.03.15 the ANTADVDT changed to January 2023.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.05.16 PHONENUM changed.] | Richardson Highway MP 35-40 Resurfacing | Valdez | 2023-01-01 | NFHWY00133
Northern Region | PROJNAME | Dalton Hwy MP 18-37 Reconstruction | Dalton Highway MP 18-37 Reconstruction | (4) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 ENGEST changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.] | Dalton Highway MP 18-37 Reconstruction | Livengood | 2022-07-01 | Z607350000
Northern Region | PROJNAME | EAST COLLEGE ROAD RESURFACING | East College Road Resurfacing | (1) [on 2022.05.16 project was added.] | East College Road Resurfacing | Fairbanks | 2022-11-01 | NFHWY00645
Southcoast Region | (DELETED) |  |  | (4) [on 2022.01.18 project was added.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.05.16 PROJNAME changed.] | JNU THANE ROAD 00039 - DEC 20 SE PR | Juneau | 2022-05-01 | SDRER00409 | SDRER00409 | WILL BE FEMA RSA -DMV | Joel D Osburn | (907)465-4409 | This project is a Permanent Repair (PR) due to flooding that occurred during the December, 2020 storm event in Southcoast Region of Alaska. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, and drainage. This project repairs a site on Thane Road at MPt 4.4. This is a FEMA funded project which will be reimbursed thru RSA with DMVA. |  | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  | (3) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-04-01 | SFHWY00359 | SFHWY00359 | 3267 | Darryl Lester | (907)465-4421 | Replace the twin culverts at Bridget Cove Creek. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  | (2) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2023-05-01 | SFHWY00070 | SFHWY00070 | 3225 | Kirk D Miller | (907)465-1215 | This project will replace or rehabilitate the Sayles/Gorge Street Viaduct (#1841). |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  | (3) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2023-05-01 | SFAPT00178 | SFAPT00178 | N/A | Gregory K Lockwood | (907)465-2393 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
Southcoast Region | ANTADVDT | 2022-05-01 | 2022-07-01 | (3) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2022-07-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2022-05-01 | 2022-06-01 | (3) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.] | FFY18 VARIOUS PRIMARY/NON-PRIMARY EAS A/P VISUAL AID REPLCMN | Regionwide | 2022-06-01 | SFAPT00174
Southcoast Region | ANTADVDT | 2022-05-01 | 2022-06-01 | (4) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.] | FFY19 VARIOUS PRIMARY/NON PRIMARY EAS AIRPORTS VISUAL AID RE | Regionwide | 2022-06-01 | SFAPT00203
Southcoast Region | ANTADVDT | 2022-06-01 | 2022-08-01 | (4) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 PROJNAME changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 the ANTADVDT changed to June 2022.] | JNU FRANKLIN AND THANE RESURFACING: TRAM PARKING LOT TO MT. ROBERTS ST | Juneau | 2022-08-01 | SFHWY00263
Southcoast Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (1) [on 2022.05.16 project was added.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-07-01 | SFAPT00363
Southcoast Region | ANTADVDT | 2022-07-01 | 2022-08-01 | (3) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2022-08-01 | Z680850000
Southcoast Region | ANTADVDT | 2022-11-01 | 2023-01-01 | (3) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-01-01 | SFHWY00058-3
Southcoast Region | DESCRIPTION | Refurbish Tongass Avenue, from MP 0.2000 to 1.2798 including rehabilitation of asphalt and concert pavement surfaces, curb and gutter, sidewalk, and correct ADA deficiencies, making improvements to the lane configurations and to the pedestrian and bike facilities to improve safety and level of service. | Refurbish Tongass Avenue, from MP 0.2010 to 1.2565 including rehabilitation of asphalt and concert pavement surfaces, curb and gutter, sidewalk, correct ADA deficiencies, make improvements to the signalization, lane configurations, and to the pedestrian and bicycle facilities to improve safety and level of service. | (1) [on 2022.04.15 the ANTADVDT changed to December 2022.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2022-12-01 | Z680910000
Southcoast Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $2,500,000 and $5,000,000 | (1) [on 2022.05.16 project was added.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-07-01 | SFAPT00363
Southcoast Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 | (3) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-01-01 | SFHWY00058-3
Southcoast Region | FEDNUM | N/A | AIP 3-02-0268-031-2022 | (1) [on 2022.05.16 project was added.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-07-01 | SFAPT00363
Southcoast Region | FEDNUM | AK2021-1 | 93001 | (2) [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.] | PSG Mitkof Hwy MPt 10.8 Culvert Replacement - DEC 20 SE PR | Petersburg | 2022-07-01 | SFHWY00379
Southcoast Region | PROJNAME | SIT AIRPORTEQ BLDG REHAB | Sitka Airport Snow Removal Equipment Building Rehabilitation | (1) [on 2022.05.16 project was added.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-07-01 | SFAPT00363