## 2022.07.12 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (2) [on 2022.05.16 project was added.]; [on 2022.06.15 the ANTADVDT changed to June 2022.] | Boney Courthouse Mechanical Upgrades and Earthquake Repairs - Rebid | Anchorage | 2022-06-01 | 2501000113-A | 2501000113-A | N/A | Eric F Hershey | (907)269-5572 | This federally funded project includes replacement and upgrades to the existing mechanical heating, ventilating, and air conditioning (HVAC) equipment damaged during the 2018 earthquake. This includes replacing two central air handlers, return fans, louvres, heat exchangers, pumps, and associated ductwork in the penthouse mechanical room. The work also includes an Enhancement option to replace variable air volume boxes and upgrade associated controls in the basement. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (2) [on 2022.05.16 project was added.]; [on 2022.06.15 the ANTADVDT changed to June 2022.] | Boney Courthouse Plaza Earthquake Repair | Anchorage | 2022-06-01 | 25RC091612 | 25RC091612 | PA-10-AK-4413-PW-00281 | Eric F Hershey | (907)269-5572 | This federally reimbursable contract includes the replacement of concrete sidewalks and plaza at the Boney Courthouse, located at 303 K St, Anchorage, Alaska, which was damaged during the November 2018 earthquake disaster. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (3) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.] | HSIP: ANCHORAGE PEDESTRIAN LIGHTING | Anchorage | 2022-06-01 | CFHWY00366 | CFHWY00366 | 1607 | Christopher L Post | (907)269-7885 | This HSIP Funded Project will increase visibility, reduce pedestrian/bicycle crashes and other traffic incidences by installing lighting. The proposed improvements are consistent with the Alaska Strategic Highway Safety Plan, Special Users Strategies to identify and implement appropriate engineering to address high-crash locations involving bicyclists and pedestrians. This project is also inline with MOA Vision Zero Safety Goals. | This project will be advertised with CFHWY00132 Minnesota Dr Tudor to 15th Pavement Preservation. <a class=linkcopy href="http://www.dot.state.ak.us/creg/design/highways/Projects/00366/00366.pdf">Preliminary Plans (~38 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (7) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.06.15 ADDLINFO changed.] | MINNESOTA DR: TUDOR TO 15TH AVE PAVEMENT PRESERVATION | Anchorage | 2022-06-01 | CFHWY00132 | CFHWY00132 | 421099 | Steven J Rzepka | (907)269-0592 | This is a Preventive Maintenance (PM) project for resurfacing Minnesota Drive in Anchorage, Alaska from Tudor Road to 15th Avenue. It will also include, as necessary: guardrail, drainage, signalization, ADA curb ramp improvements, signs and striping. | This project will be advertised with CFHWY00366 HSIP Anchorage Pedestrian Lighting. <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00132/00132_Plans.pdf">Preliminary Plans (~27 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (4) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.] | ANC TAXIWAY R SOUTH SURFACE SEAL | Anchorage | 2023-01-01 | CFAPT00758 | CFAPT00758 | N/A | Jennifer M Carle | (907)266-2731 | Apply a seal coat to the taxiway surface, select joint repairs and restripe. | Surface seal taxiway | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2023-04-01 | CFHWY00394 | CFHWY00394 | 0A15039 | Kristina H Busch | (907)269-0567 | Resurface the Glenn Highway from Kings River bridge to Cascade. Additional improvements may include bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities as necessary. Project construction may be phased. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  | Anchorage District Paving | Anchorage | 2022-07-01 | 22-25-1-16 | 22-25-1-16 | N/A | Vernon S Vreeland | (907)269-0778 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Anchorage Maintenance District boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | Mat-Su District Paving | Matanuska-Susitna Borough | 2022-07-01 | 22-25-1-013 | 22-25-1-013 | N/A | Vernon S Vreeland | (907)269-0778 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Matanuska-Susitna District boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2023-06-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Christopher L Post | (907)269-7885 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards.
Central Region | ADDED |  |  |  | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-06-01 | CFHWY00883 | CFHWY00883 | 1727 | Christopher L Post | (907)269-7885 | This HSIP project will construct a flashing beacon and load center at the intersection of Church Road and Spruce Ave. Work may include drainage improvements, roadside hardware, ADA improvements (curb ramp & pathway), and utilities.
Central Region | ADDED |  |  |  | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2023-06-01 | CFHWY00503 | CFHWY00503 | 1644 | Christopher L Post | (907)269-7885 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements.
Central Region | ADDED |  |  | (2) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.] | SEWARD AIRPORT IMPROVEMENTS | Seward | 2023-06-01 | Z548570000 | Z548570000 | N/A | Joy A Vaughn | (907)269-0812 | Shift, raise and reconstruct R/W 16/34. Construct Armor protection. Rehabilitate aprons, replace airport lighting, and construct pads for NAVAIDS. Close R/W 13/31, Taxiways A, D, and E. Miscellaneous fencing, signing, etc... |  | Between $20,000,000 and $30,000,000
Central Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (3) [on 2022.04.15 the ANTADVDT changed to April 2022.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.06.15 ENGEST changed.] | Ketchikan Pioneer Home Structural Upgrades | Ketchikan Gateway Borough | 2022-07-01 | 2501000083
Central Region | ANTADVDT | 2022-07-01 | 2023-03-01 | (2) [on 2022.02.22 PHONENUM changed.]; [on 2022.03.15 ENGEST changed.] | Colleen Street Intersection and Frontage Road | Palmer | 2023-03-01 | CFHWY00006
Central Region | ANTADVDT | 2022-07-01 | 2023-03-01 | (1) [on 2022.02.22 PHONENUM changed.] | Glenn Hwy: Parks Hwy to S. Inner Springer Lp. (Phase II) | Palmer | 2023-03-01 | CFHWY00431
Central Region | ANTADVDT | 2022-07-01 | 2023-03-01 | (1) [on 2022.02.22 PHONENUM changed.] | Glenn Hwy: Parks to S. Inner Springer Lp. Pathway (Phase II) | Palmer | 2023-03-01 | CFHWY00432
Central Region | ANTADVDT | 2022-07-01 | 2022-09-01 | (2) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2022-09-01 | CFAPT00491
Central Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (2) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to August 2022.] | AMATS: HILAND RD MP 0 TO MP 3.2 PAVEMENT PRESERVATION | Eagle River | 2022-09-01 | CFHWY00568
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (2) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2022-10-01 | CFAPT00855
Central Region | ANTADVDT | 2022-10-01 | 2023-01-01 | (6) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2023-01-01 | CFAPT00882
Central Region | DESCRIPTION | The project proposes to rehabilitate the runway and runway safety area; remove obstructions; rehabilitate Taxiways A & B; rehabilitate and expand the General Aviation apron toward the east; replace airfield lighting, remove Taxiway D; install a new turnaround taxiway at the east end of the runway, and install a new taxiway connecting the east end of the General Aviation apron to the runway. | The project proposes to rehabilitate the runway and runway safety area; remove terrain obstructions; rehabilitate Taxiways A & B; rehabilitate and expand the General Aviation apron; replace airfield lighting and signage; remove Taxiway D; and install a new turnaround taxiway at the east end of the runway. | (2) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2022-09-01 | CFAPT00491
Central Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $30,000,000 and $40,000,000 | (2) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2022-09-01 | CFAPT00491
Central Region | ENGEST | Between $500,000 and $1,000,000 | Between $2,500,000 and $5,000,000 | (2) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2022-10-01 | CFAPT00855
Central Region | ENGEST |  | Between $10,000,000 and $20,000,000 | (1) [on 2022.06.15 project was added.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-01-01 | CFAPT00682
Central Region | LOCATION | Central Region | Ketchikan Gateway Borough | (3) [on 2022.04.15 the ANTADVDT changed to April 2022.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.06.15 ENGEST changed.] | Ketchikan Pioneer Home Structural Upgrades | Ketchikan Gateway Borough | 2022-07-01 | 2501000083
Central Region | PROJMAN | Jennifer M Carle | Jennifer M Lombardo | (2) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2022-10-01 | CFAPT00855
Central Region | PROJMAN | Jennifer M Carle | Jennifer M Lombardo | (6) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2023-01-01 | CFAPT00882
Central Region | PROJMAN | Jennifer M Carle | Jennifer M Lombardo | (6) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2022-11-01 | CSAPT00931
Central Region | PROJMAN | Jennifer M Carle | Jennifer M Lombardo | (2) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.] | ANC RON 3 AND 4 JOINT REPAIRS | Anchorage | 2023-01-01 | CSAPT00754
Marine Highways | ANTADVDT | 2022-08-01 | 2022-10-01 | (3) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 PROJNAME changed.] | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | Ketchikan | 2022-10-01 | Z674660000
Northern Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | North Pole City Core Streetlight Standardization and Improvements | North Pole | 2022-06-01 | NFHWY00690 | NFHWY00690 | N/A | Ethan E Graetz | (907)451-2281 | Replace the lighting system with more energy efficient technologies and install new LED luminaires. Work will include roadside hardware and utilities. |  | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  | (6) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 FEDNUM changed.]; [on 2022.05.16 ENGEST changed.]; [on 2022.06.15 ADDLINFO changed.]; [on 2022.06.15 the ANTADVDT changed to June 2022.] | Point Hope Airport Realignment | Point Hope | 2022-06-01 | Z638420000 | Z638420000 | 3-02-0226-___-____ | Jonathan J Hutchinson | (907)451-5479 | Realign the runway at the Point Hope Airport. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.06.15 project was added.] | Northern Region Digital Message Signs (CMAQ) | Fairbanks North Star Borough | 2022-07-01 | NFHWY00707 | NFHWY00707 | Pending | Ethan E Graetz | (907)451-2281 | Install and operate digital messaging signs on the Parks Highway MP 357 and Richardson Highway MP 359. |  | Between $2,500,000 and $5,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.06.15 project was added.] | Murphy Dome Road Preventive Maintenance Surface Repairs | Fairbanks North Star Borough | 2022-09-01 | NFHWY00702 | NFHWY00702 | N/A | None | None | Reclaim, reshape, and resurface a section of Murphy Dome Road
Northern Region | ADDED |  |  |  | NENANA - TOTCHAKET ROAD | Nenana | 2022-07-01 | NSHWY00657 | NSHWY00657 | N/A | Jonathan J Hutchinson | (907)451-5479 | Construct the Nenana-Totchaket Road from the Nenana River to the Kantishna River. Project will include improving approximately 12 miles of road and constructing 20 new miles of road. | Project is being advertised as a CMGC RFP. More information available on the project website: https://dot.alaska.gov/nreg/nenana-totchaket/ | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  | Steele Creek Road Auxiliary Drainage Culvert | Fairbanks | 2022-08-01 | NSHWY00704 | NSHWY00704 | N/A | Daniel S Adamczak | (907)451-2294 | Install a 36" smooth wall steel pipe across Steele Creek Road at the Southwood approach to help manage drainage. After Installation the affected area of Steele Creek Road will be repaved and culvert shall have a thaw pipe and markers installed.
Northern Region | ADDED |  |  |  | Birch Hill Access Road Preventive maintenance | Northern Region | 2022-09-01 | NFHWY00703 | NFHWY00703 | N/A | Daniel S Adamczak | (907)451-2294 | Reclaim, reshape and resurface a section of Birch Hill Road.
Northern Region | ADDED |  |  | (2) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.] | BUCKLAND AIRPORT IMPROVEMENTS | Buckland | 2023-06-01 | NFAPT00604 | NFAPT00604 | N/A | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate the runway and taxiway, stabilize the embankments, resurface the airport access road, apply dust palliative, and replace the airport lighting system. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  | CHALKYITSIK AIRPORT IMPROVEMENTS | Chalkyitsik | 2023-06-01 | Z625970000 | Z625970000 | N/A | Jonathan J Hutchinson | (907)451-5479 | Resurface the runway, taxiway, apron, and access road and place a dust palliative. Replace airport lighting system and elctrical building. Replace segmented circle and windcone. Construct a new snow removal equipment building. Improve airport drainage and remove obstructions. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  | (2) [on 2022.02.22 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the project was removed.] | Deering Airport Improvements | Deering | 2023-06-01 | NFAPT00249 | NFAPT00249 | 3-02-0400-XX-202X | Jonathan J Hutchinson | (907)451-5479 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  | LITTLE DIOMEDE HELIPAD IMPROVEMENTS | Diomede | 2023-06-01 | Z614700000 | Z614700000 | N/A | Jonathan J Hutchinson | (907)451-5479 | REV 9/4/20: Rehabilitate the rock revetment, helipad surface and the lighting system, and replace the windcone and rotating beacon.
Northern Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (2) [on 2022.03.15 ENGEST changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.] | Fairbanks Area PM 2.5 Plug-Ins: Birch Hill, Chena Lakes, UAF | Fairbanks North Star Borough | 2022-07-01 | NFHWY00627
Northern Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (2) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to June 2022.] | Saint Mary's Airport Improvements | St Mary's | 2022-07-01 | Z605630000
Northern Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (4) [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.05.16 ENGEST changed.]; [on 2022.05.16 FEDNUM changed.] | Shishmaref Airport Erosion Control | Shishmaref | 2022-07-01 | NFAPT00370
Northern Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $30,000,000 and $40,000,000 | (2) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to June 2022.] | Saint Mary's Airport Improvements | St Mary's | 2022-07-01 | Z605630000
Northern Region | FEDNUM | N/A | Pending | (2) [on 2022.03.15 ENGEST changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.] | Fairbanks Area PM 2.5 Plug-Ins: Birch Hill, Chena Lakes, UAF | Fairbanks North Star Borough | 2022-07-01 | NFHWY00627
Northern Region | PROJNAME | FAIRBANKS AREA PM 2.5 PLUG-INS: BIRCH HILL, CHENA LAKES, UAF | Fairbanks Area PM 2.5 Plug-Ins: Birch Hill, Chena Lakes, UAF | (2) [on 2022.03.15 ENGEST changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.] | Fairbanks Area PM 2.5 Plug-Ins: Birch Hill, Chena Lakes, UAF | Fairbanks North Star Borough | 2022-07-01 | NFHWY00627
Southcoast Region | (DELETED) |  |  | (2) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.03.15 the ANTADVDT changed to May 2022.] | SR DM AIRPOR GATE/FENCE REPAIRS/REPLACEMENT | Gustavus | 2022-05-01 | SSAPT00093 | SSAPT00093 | N/A | Bran P Pollard | (907)465-4526 | Replace an existing electric cantilever gate with a new 24’ electric vertical pivot gate on a new concrete foundation at the Gustavus Airport. Project gate will connect to the existing Airport Access Control System, existing automatic vehicle gate controllers, and existing auxiliary automatic vehicle gate safety control systems. Includes removal of existing 20' cantilever gate, removal of existing concrete foundation, and removal of existing fencing. |  | Less than $200,000
Southcoast Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | Kodiak | 2023-03-01 | SFHWY00260 | SFHWY00260 | 3247 | Bran P Pollard | (907)465-4526 | Resurface Rezanoff Drive from Marine Way to the airport. Associated preventative maintenance activities may include minor structural section improvements, drainage repairs, lighting and signals, striping, signs, and ADA improvements. Project Location and Length: Rezanoff Drive from Marine Way to the airport for an approximate length of 4.70 miles. | (Design by Northern Region)
Southcoast Region | (DELETED) |  |  | (4) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2023-03-01 | SFAPT00227 | SFAPT00227 | N/A | David A Pyeatt | (907)465-4490 | ADQ airport ARFF Access improvements and Rehabilitation of Taxiway C, D and F. Project includes the non-private portion of the Apron. | PFAS Investigation may cause delay depending on results and how to manage waste material | Between $50,000,000 and $60,000,000
Southcoast Region | ADDED |  |  | (4) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-06-01 | SFHWY00359 | SFHWY00359 | 3267 | Darryl Lester | None | Replace the twin culverts at Bridget Cove Creek. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  | KTN HOADLEY CREEK BRIDGE REPLACEMENT | Ketchikan | 2023-06-01 | SFHWY00197 | SFHWY00197 | 902044 | Peter J Jackson | (907)465-4439 | Refurbish or replace Hoadley Creek Bridge (Bridge Number 725) and associated roadway approaches. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDLINFO |  | This project is a Permanent Repair (PR) due to flooding that occurred during the December, 2020 storm event in the Southcoast Region of Alaska. Repairs may include, but are not limited to, asphalt, embankment, roadside hardware, retaining walls, utilities, and drainage. May include mitigation to prevent future similar damage to facilities. This project repairs sites on Dyea Road at FEMA Damage Inventory Numbers 461214, 461216, 461217, 461260, 461261, 461648, 784616, and 784619. | (1) [on 2022.04.15 project was added.] | SGY DYEA ROAD 00049 - DEC 20 SE PR | Skagway | 2022-08-01 | SDRER00410
Southcoast Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (4) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to June 2022.] | FFY18 VARIOUS PRIMARY/NON-PRIMARY EAS A/P VISUAL AID REPLCMN | Regionwide | 2022-07-01 | SFAPT00174
Southcoast Region | ANTADVDT | 2022-06-01 | 2022-07-01 | (5) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to June 2022.] | FFY19 VARIOUS PRIMARY/NON PRIMARY EAS AIRPORTS VISUAL AID RE | Regionwide | 2022-07-01 | SFAPT00203
Southcoast Region | ANTADVDT | 2022-07-01 | 2022-08-01 | (4) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2022-08-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2022-07-01 | 2022-08-01 | (3) [on 2022.01.18 project was added.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.] | HNS MOSQUITO LAKE ROAD 00044 - DEC 20 SE PR | Haines | 2022-08-01 | SDRER00408
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-10-01 | (4) [on 2022.01.18 ENGEST changed.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to August 2022.] | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | Hoonah | 2022-10-01 | SFAPT00236
Southcoast Region | ANTADVDT | 2023-01-01 | 2023-03-01 | (2) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.] | CRAIG ADA IMPROVEMENTS | Craig | 2023-03-01 | SFHWY00377
Southcoast Region | PHONENUM | (907)465-4421 | None | (5) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 PROJNAME changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 the ANTADVDT changed to June 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.] | JNU FRANKLIN AND THANE RESURFACING: TRAM PARKING LOT TO MT. ROBERTS ST | Juneau | 2022-08-01 | SFHWY00263
Southcoast Region | PROJNAME | HNS MOSQUITO LAKE ROAD #550474 - DEC 20 SE PR | HNS MOSQUITO LAKE ROAD 00044 - DEC 20 SE PR | (3) [on 2022.01.18 project was added.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.] | HNS MOSQUITO LAKE ROAD 00044 - DEC 20 SE PR | Haines | 2022-08-01 | SDRER00408
Southcoast Region | PROJNAME | SGY DYEA ROAD 189468 - DEC 20 SE PR | SGY DYEA ROAD 00049 - DEC 20 SE PR | (1) [on 2022.04.15 project was added.] | SGY DYEA ROAD 00049 - DEC 20 SE PR | Skagway | 2022-08-01 | SDRER00410