## 2022.08.14 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (1) [on 2022.07.12 project was added.] | Anchorage District Paving | Anchorage | 2022-07-01 | 22-25-1-16 | 22-25-1-16 | N/A | Vernon S Vreeland | (907)269-0778 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Anchorage Maintenance District boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (5) [on 2022.04.15 the ANTADVDT changed to April 2022.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.07.12 the ANTADVDT changed to July 2022.]; [on 2022.07.12 LOCATION changed.] | Ketchikan Pioneer Home Structural Upgrades | Ketchikan Gateway Borough | 2022-07-01 | 2501000083 | 2501000083 | N/A | Alyson K Wardell | (907)269-0869 | Seismic upgrades for roof and building structure | Advertise contingent upon funds by User Agency | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (3) [on 2022.03.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.] | KONGIGANAK AIRPORT IMPROVEMENTS | Kongiganak | 2022-07-01 | CFAPT00433 | CFAPT00433 | 3-02-0380-004-2022 | Philip W Cheasebro | (907)269-0606 | This project will rehabilitate airport surfaces, expand the apron and runway safety areas (RSA), install a Snow Removal Equipment Building (SREB) and relocate the existing SREB. Install a rotating beacon on a tip-down pole, tie-downs, and replace airfield lighting at the Kongiganak Airport. Expected FFY 2022 funding. | Pre PS&E review documents are located at the link below: <a class=linkcopy href="http://www.dot.state.ak.us/creg/design/aviation/Tentative_Advertising_List_Docs/4_00433%20Kongiganak%20Pre%20PSE%20Plans_TAL.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.07.12 project was added.] | Mat-Su District Paving | Matanuska-Susitna Borough | 2022-07-01 | 22-25-1-013 | 22-25-1-013 | N/A | Vernon S Vreeland | (907)269-0778 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Matanuska-Susitna District boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (5) [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.05.16 DESCRIPTION changed.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.] | SLEETMUTE AIRPORT RESURFACING | Sleetmute | 2022-08-01 | CFAPT00293 | CFAPT00293 | 3-02-0272-001-2022 | Aaron C Hughes | (907)269-0523 | The project will resurface the runway, taxiway, and apron, extend runway safety areas, and replace the snow removal equipment building. Improvements include airport lighting, tie-downs, drainage, dust palliative, visual NAVAIDs, and clearing. | The project will resurface the runway, taxiway, and apron, extend runway safety areas, and replace the snow removal equipment building. Improvements include airport lighting, tie-downs, drainage, dust palliative, visual NAVAIDs, and clearing. | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | HSIP: 5TH AVE: CONCRETE ST TO KARLUK ST PEDESTRIAN IMPROVMNT | Anchorage | 2023-04-01 | CFHWY00856 | CFHWY00856 | 421102 | Christopher L Post | (907)269-7885 | This HSIP project will construct a median barrier on 5th Avenue between Concrete Street and the couplet of 5th and 6th Avenues (Karluk Street). Work may include roadside hardware, drainage, improvements, and utilities.
Central Region | (DELETED) |  |  | (1) [on 2022.07.12 project was added.] | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2023-06-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Christopher L Post | (907)269-7885 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards.
Central Region | (DELETED) |  |  | (1) [on 2022.07.12 project was added.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2023-06-01 | CFHWY00503 | CFHWY00503 | 1644 | Christopher L Post | (907)269-7885 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements.
Central Region | ADDED |  |  |  | ANC NORTH TERMINAL TICKET AND GATE CUPPS | Anchorage | 2022-08-01 | CSAPT00908 | CSAPT00908 | N/A | Jennifer C Pepin | (907)266-2549 | Modify or replace casework, including scales, for ADA compliance at North Terminal ticket lobby and passenger boarding areas. Install CUPPS equipment at each location. Install phones and public address system. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  | ANC SUPPLY WAREHOUSE ROOF REPLACEMENT | Anchorage | 2022-09-01 | CSAPT00858 | CSAPT00858 | N/A | Jennifer C Pepin | (907)266-2549 | This project will replace the roof on the 14,400 sf, 1970's era supply warehouse (WH107). Aging and failing roofing will be replaced with new roofing and additional insulation to meet the current requirements. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  | STERLING SAFETY CORRIDOR IMPROVEMENTS MP 82.5 TO 94 DESIGN BUILD | Sterling | 2022-11-01 | CFHWY00130 | CFHWY00130 | 0A33026 | Kelly L Summers | (907)269-0546 | The Department anticipates issuing an RFP for a federally funded Design-Build contract to provide the necessary engineering, labor, equipment, and materials to design, construct, and warranty a four lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed project will improve safety and reduce congestion within this existing safety corridor. The department’s solicitation is contingent on federal authority to proceed with construction. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $60,000,000 and $70,000,000
Central Region | ADDED |  |  |  | ANC POSTMARK DRIVE REPAIRS 2023 | Anchorage | 2023-01-01 | CSAPT00984 | CSAPT00984 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate 3,000 feet of Postmark Drive from West Northern Lights Boulevard to approximately Taxiway Uniform Tug Road intersection. Project includes pavement planning, paving, and striping. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | Anchorage | 2023-04-01 | CFAPT00992 | CFAPT00992 | N/A | Jennifer M Lombardo | (907)266-2731 | Reconstruct approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, new structural section, drainage improvements and pavement markings. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  | (2) [on 2022.03.15 project was added.]; [on 2022.06.15 the project was removed.] | ANC TAXIWAY Z IMPROVEMENTS EAST | Anchorage | 2023-07-01 | CFAPT00835 | CFAPT00835 | N/A | Philip W Cheasebro | (907)269-0606 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron.
Central Region | ADDED |  |  |  | KWIGILLINGOK AIRPORT IMPROVEMENTS | Kwigillingok | 2023-07-01 | Z525710000 | Z525710000 | N/A | Joy A Vaughn | (907)269-0812 | Reconstruct and extend Kwigillingok Airport to community class standards. Will acquire ROW, improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building(s). | Reconstruct and extend Kwigillingok Airport to community class standards. Improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building. Actual Advertising Date contingent upon federal funding availability. Check back often for updates.
Central Region | ANTADVDT | 2022-07-01 | 2022-10-01 | (4) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.05.16 PROJNAME changed.] | ANC TAXIWAY Z IMPROVEMENTS WEST - PHASE 1 | Anchorage | 2022-10-01 | CFAPT00465
Central Region | ANTADVDT | 2022-07-01 | 2022-08-01 | (2) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.] | Mchugh RWIS Tower Upgrade | Municipality Of Anchorage | 2022-08-01 | CFHWY00428
Central Region | ANTADVDT | 2022-07-01 | 2022-09-01 | (1) [on 2022.04.15 project was added.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2022-09-01 | 25RC053613
Central Region | ANTADVDT | 2022-07-01 | 2022-08-01 | (5) [on 2022.05.16 project was added.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 FEDNUM changed.]; [on 2022.06.15 PROJNAME changed.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-08-01 | SFAPT00363
Central Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (2) [on 2022.01.18 the ANTADVDT changed to July 2022.]; [on 2022.04.15 the ANTADVDT changed to August 2022.] | ANC Parking Garage PG111 Repairs and Improvement | Anchorage | 2022-09-01 | CSAPT00566
Central Region | ANTADVDT | 2022-08-01 | 2022-12-01 |  | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2022-12-01 | Z581060000
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (5) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.07.12 DESCRIPTION changed.]; [on 2022.07.12 ENGEST changed.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2022-10-01 | CFAPT00491
Central Region | ANTADVDT | 2022-10-01 | 2023-02-01 | (3) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2023-02-01 | CFHWY00260
Central Region | ANTADVDT | 2022-10-01 | 2023-01-01 | (1) [on 2022.03.15 PROJMAN changed.] | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | Anchorage | 2023-01-01 | CFHWY00286
Central Region | ANTADVDT | 2022-10-01 | 2023-02-01 | (3) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2023-02-01 | CFHWY00395
Central Region | ANTADVDT | 2023-03-01 | 2023-05-01 | (2) [on 2022.01.18 the project was removed.]; [on 2022.05.16 project was added.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-05-01 | CSAPT00719
Central Region | DESCRIPTION | This project will replace the roof membrane on the roof level of PG-111. Parking Garage and will make repairs to floor deck spalling and electric lighting that have resulted from water infiltration. | This project will repair or replace deck membranes of building PG-111. Parking Garage and will make other repairs including blue light system and electric lighting. | (2) [on 2022.01.18 the ANTADVDT changed to July 2022.]; [on 2022.04.15 the ANTADVDT changed to August 2022.] | ANC Parking Garage PG111 Repairs and Improvement | Anchorage | 2022-09-01 | CSAPT00566
Central Region | DESCRIPTION | Rehabilitate the airport runway, taxiway, safety areas, apron and access road. Replace lighting, nav-aids, the existing SREB and improve drainage. Remove OFA obstructions. | Rehabilitate the airport runway, taxiway, safety areas, apron and access road. Replace lighting, nav-aids, and improve drainage. Remove OFA obstructions. | (2) [on 2022.06.15 project was added.]; [on 2022.07.12 ENGEST changed.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-01-01 | CFAPT00682
Central Region | DESCRIPTION | Reconstruction (replacement) of the Takotna River Bridge (bridge #0463). Reconstruction may include bridge work, roadside hardware, drainage improvements, and utilities. | This Project replaces the Takotna River Bridge (bridge #0463). Project includes bridge work, roadway resurfacing, roadside hardware, drainage improvements, and utilities. | (7) [on 2022.02.22 the ANTADVDT changed to September 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.] | TAKOTNA RIVER BRIDGE REPLACEMENT | Takotna | 2023-02-01 | CFHWY00129
Central Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 | (3) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2023-02-01 | CFHWY00260
Central Region | ENGEST | Between $10,000,000 and $20,000,000 | Between $20,000,000 and $30,000,000 | (2) [on 2022.06.15 project was added.]; [on 2022.07.12 ENGEST changed.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-01-01 | CFAPT00682
Central Region | FEDNUM | N/A | 1746 | (1) [on 2022.03.15 PROJMAN changed.] | HSIP:CR Guardrail Inventory and Upgrade (North) | Matanuska-Susitna Borough | 2022-11-01 | CFHWY00939
Central Region | LOCATION | Central Region | Matanuska-Susitna Borough | (1) [on 2022.03.15 PROJMAN changed.] | HSIP:CR Guardrail Inventory and Upgrade (North) | Matanuska-Susitna Borough | 2022-11-01 | CFHWY00939
Central Region | LOCATION | Central Region | Kenai Peninsula | (1) [on 2022.03.15 PROJMAN changed.] | HSIP:CR Guardrail Inventory and Upgrade (South) | Kenai Peninsula | 2022-11-01 | CFHWY00938
Central Region | PHONENUM | (907)269-0820 | (907)266-2723 | (5) [on 2022.05.16 project was added.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 FEDNUM changed.]; [on 2022.06.15 PROJNAME changed.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-08-01 | SFAPT00363
Central Region | PHONENUM | (907)269-7885 | (907)269-0693 | (3) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2023-02-01 | CFHWY00260
Central Region | PHONENUM | (907)269-7885 | (907)269-0693 | (3) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2023-02-01 | CFHWY00395
Central Region | PHONENUM | (907)269-7885 | (907)269-0693 | (1) [on 2022.07.12 project was added.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-06-01 | CFHWY00883
Central Region | PROJMAN | Christopher L Post | Cynthia L Ferguson | (3) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2023-02-01 | CFHWY00260
Central Region | PROJMAN | Christopher L Post | Cynthia L Ferguson | (3) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2023-02-01 | CFHWY00395
Central Region | PROJMAN | Christopher L Post | Cynthia L Ferguson | (1) [on 2022.07.12 project was added.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2023-06-01 | CFHWY00883
Central Region | REGION | Southcoast Region | Central Region | (5) [on 2022.05.16 project was added.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 FEDNUM changed.]; [on 2022.06.15 PROJNAME changed.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-08-01 | SFAPT00363
Marine Highways | DESCRIPTION | This project encompasses the replacement of an existing vessel berthing and turning dolphin structure at the west end of Berth 1; placement of a new turning dolphin between Berths 1 and 3, refurbishment of fendering and platform components at the Berth 3 float; construction of a new pedestrian cover structure over the existing sidewalk from the terminal building to the Berth 3 approach; and the placement of cathodic protection anodes on all existing offshore pile supported structures at Berths 1 and 3. | The project would replace the ferry vessel fender system along the face of a 120’ long floating platform, install a new gangway and gangway landings, and make electrical and lighting improvements. All work on this project is at the AMHS Berth 3 Ferry Terminal in Ketchikan, Alaska. | (4) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.] | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | Ketchikan | 2022-10-01 | Z674660000
Northern Region | (DELETED) |  |  | (5) [on 2022.03.15 ENGEST changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.07.12 the ANTADVDT changed to July 2022.]; [on 2022.07.12 FEDNUM changed.]; [on 2022.07.12 PROJNAME changed.] | Fairbanks Area PM 2.5 Plug-Ins: Birch Hill, Chena Lakes, UAF | Fairbanks North Star Borough | 2022-07-01 | NFHWY00627 | NFHWY00627 | Pending | Ethan E Graetz | (907)451-2281 | Provide electrical motor vehicle plug-ins at the following locations in the Fairbanks PM 2.5 non-attainment area: Birch Hill, Chena Lakes, and the UAF U-Park Building. Project includes utilities and drainage improvements. |  | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  | (1) [on 2022.07.12 project was added.] | NENANA - TOTCHAKET ROAD | Nenana | 2022-07-01 | NSHWY00657 | NSHWY00657 | N/A | Jonathan J Hutchinson | (907)451-5479 | Construct the Nenana-Totchaket Road from the Nenana River to the Kantishna River. Project will include improving approximately 12 miles of road and constructing 20 new miles of road. | Project is being advertised as a CMGC RFP. More information available on the project website: https://dot.alaska.gov/nreg/nenana-totchaket/ | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  | (4) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.07.12 the ANTADVDT changed to July 2022.]; [on 2022.07.12 ENGEST changed.] | Saint Mary's Airport Improvements | St Mary's | 2022-07-01 | Z605630000 | Z605630000 | PENDING | Christopher F Johnston | (907)451-2322 | Rehabilitate and resurface runways, taxiways, and apron. Project will include replacing airport lighting and runway safety area improvements. |  | Between $30,000,000 and $40,000,000
Northern Region | (DELETED) |  |  | (5) [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.05.16 ENGEST changed.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.07.12 the ANTADVDT changed to July 2022.] | Shishmaref Airport Erosion Control | Shishmaref | 2022-07-01 | NFAPT00370 | NFAPT00370 | 3-02-0404-___-____ | Jonathan J Hutchinson | (907)451-5479 | Install erosion protection at the Shishmaref Airport. | 22E | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  | Aurora Drive Noyes Slough Bridge #0209 Replacement | Fairbanks | 2022-11-01 | NFHWY00124 | NFHWY00124 | 629001 | Lauren M Little | (907)378-5911 | Replace the Noyes Slough Bridge #0209 on Aurora Drive in Fairbanks. Project work includes bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements and utility work. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  | Healy Spur Road Rehabilitation | Healy | 2022-12-01 | NFHWY00580 | NFHWY00580 | 638005 | Jennifer J Wright | (907)371-8949 | Rehabilitate Healy Spur Road in Healy. Project will include widening shoulders and drainage improvements. |  | Between $1,000,000 and $2,500,000
Northern Region | ADDED |  |  |  | Richardson Highway MP 357-362 Bicycle/Pedestrian Path | Fairbanks | 2022-12-01 | Z615970000 | Z615970000 | 0A24032 | Lauren M Little | (907)378-5911 | Construct a paved bicycle/pedestrian path along the Richardson Highway starting near the intersection of Airport Way/Richardson Highway to the Badger Road/Old Richardson Highway intersection. Improvements will include bridge work, roadside hardware, drainage improvements, and utilities. | Project will be advertised with Z607340000 Richardson Hwy MP 359 Railroad Grade Separated Facility. | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  | Richardson Highway MP 359 Railroad Grade Separated Facility | Fairbanks | 2022-12-01 | Z607340000 | Z607340000 | 0A24033 | Lauren M Little | (907)378-5911 | Construct a railroad grade separated facility near MP 359 of the Richardson Highway. Work includes a new twin bridges, a troop undercrossing, roadside hardware, drainage improvements, and utility relocations. | Project will be advertised with Z615970000 Richardson Hwy MP 357-362 Bicycle/Pedestrian Path. | Between $20,000,000 and $30,000,000
Northern Region | ADDED |  |  |  | HSIP: OLD STEESE HIGHWAY SHOULDER WIDENING | Fox | 2023-02-01 | NFHWY00527 | NFHWY00527 | 2472 | Carl F Heim | (907)451-5359 | Reconstruct the Old Steese Highway between Gold Dredge #8 and the Fox Intersection. Work includes roadside hardware, drainage improvements, intersection improvements, and utilities.
Northern Region | ADDED |  |  |  | FAIRBANKS 5TH AVENUE RECONSTRUCTION | Fairbanks | 2023-05-01 | NFHWY00445 | NFHWY00445 | TA19001 | Ivet Hall | (907)451-5386 | Reconstruct 5th Avenue between Barnette Street and Noble Street including ADA Improvements, intersection improvements, drainage improvements, roadside hardware, and utilities.
Northern Region | ADDED |  |  |  | MARSHALL AIRPORT IMPROVEMENTS | Marshall | 2023-05-01 | NFAPT00371 | NFAPT00371 | N/A | Christopher F Johnston | (907)451-2322 | Rehabilitate the runway, taxiway, apron, airport access road, and the snow removal equipment building, replace airport lighting and segmented circle, and apply dust palliative. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDLINFO |  | The department was previously uncertain on funding and permit timelines for this project and is now confident the project will advertise in September 2022. | (6) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 ENGEST changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 LOCATION changed.]; [on 2022.06.15 PROJNAME changed.] | Dalton Highway MP 18-37 Reconstruction | Livengood | 2022-09-01 | Z607350000
Northern Region | ANTADVDT | 2022-07-01 | 2022-09-01 | (3) [on 2022.02.22 PROJNAME changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.] | Copper River Boat Launch Facilities Improvements (FLAP) | Mccarthy | 2022-09-01 | NFHWY00539
Northern Region | ANTADVDT | 2022-07-01 | 2022-09-01 | (6) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 ENGEST changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 LOCATION changed.]; [on 2022.06.15 PROJNAME changed.] | Dalton Highway MP 18-37 Reconstruction | Livengood | 2022-09-01 | Z607350000
Northern Region | ANTADVDT | 2022-09-01 | 2022-11-01 | (1) [on 2022.07.12 project was added.] | Birch Hill Access Road Preventive maintenance | Northern Region | 2022-11-01 | NFHWY00703
Northern Region | ANTADVDT | 2022-10-01 | 2023-03-01 | (3) [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.] | Nome Port Road Reconstruction | Nome | 2023-03-01 | Z621230000
Northern Region | ANTADVDT | 2022-10-01 | 2022-12-01 | (1) [on 2022.06.15 project was added.] | Old Steese Highway Reconstruction | Fairbanks | 2022-12-01 | Z624870000
Northern Region | ANTADVDT | 2022-11-01 | 2022-12-01 | (2) [on 2022.05.16 project was added.]; [on 2022.06.15 PROJNAME changed.] | East College Road Resurfacing | Fairbanks | 2022-12-01 | NFHWY00645
Northern Region | ANTADVDT | 2022-11-01 | 2022-12-01 | (1) [on 2022.05.16 project was added.] | Northern Region ADA Improvements - Fairbanks: College Road | Fairbanks | 2022-12-01 | NFHWY00591
Northern Region | DESCRIPTION | Install a 36" smooth wall steel pipe across Steele Creek Road at the Southwood approach to help manage drainage. After Installation the affected area of Steele Creek Road will be repaved and culvert shall have a thaw pipe and markers installed. | Install a 36" smooth wall steel pipe across Steele Creek Road at the Southwood approach to help manage drainage. After Installation the affected area of Steele Creek Road will be repaved and culvert shall have a thaw pipe, thaw wire and markers installed. | (1) [on 2022.07.12 project was added.] | Steele Creek Road Auxiliary Drainage Culvert | Fairbanks | 2022-08-01 | NSHWY00704
Northern Region | ENGEST | Between $50,000,000 and $60,000,000 | Between $40,000,000 and $50,000,000 | (6) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 ENGEST changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 LOCATION changed.]; [on 2022.06.15 PROJNAME changed.] | Dalton Highway MP 18-37 Reconstruction | Livengood | 2022-09-01 | Z607350000
Northern Region | ENGEST |  | Between $200,000 and $500,000 | (1) [on 2022.07.12 project was added.] | Steele Creek Road Auxiliary Drainage Culvert | Fairbanks | 2022-08-01 | NSHWY00704
Northern Region | ENGEST |  | Between $200,000 and $500,000 | (1) [on 2022.07.12 project was added.] | Birch Hill Access Road Preventive maintenance | Northern Region | 2022-11-01 | NFHWY00703
Northern Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 | (2) [on 2022.05.16 project was added.]; [on 2022.06.15 PROJNAME changed.] | East College Road Resurfacing | Fairbanks | 2022-12-01 | NFHWY00645
Northern Region | ENGEST |  | Between $200,000 and $500,000 | (1) [on 2022.02.22 the ANTADVDT changed to December 2022.] | NOR REG VARIOUS AIRPORTS VISUAL AID REPLACEMENT FFY2020 | Regionwide | 2022-12-01 | NFAPT00537
Northern Region | ENGEST |  | Between $5,000,000 and $10,000,000 | (2) [on 2022.02.22 project was added.]; [on 2022.06.15 ADDLINFO changed.] | Chena Ridge Road and Chena Pump Road Resurfacing | Fairbanks | 2023-01-01 | NFHWY00570
Northern Region | ENGEST | Between $10,000,000 and $20,000,000 | Between $5,000,000 and $10,000,000 | (1) [on 2022.05.16 project was added.] | ALASKA HWY PASSING LANES | Tok | 2023-02-01 | Z606320000
Northern Region | FEDNUM | N/A | 3-02-0399-___-____ | (3) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.] | Buckland Airport Improvements | Buckland | 2023-06-01 | NFAPT00604
Northern Region | LOCATION | Fairbanks North Star Borough | Fairbanks | (2) [on 2022.02.22 project was added.]; [on 2022.06.15 ADDLINFO changed.] | Chena Ridge Road and Chena Pump Road Resurfacing | Fairbanks | 2023-01-01 | NFHWY00570
Northern Region | PROJNAME | Richardson Hwy MP 167-173 | Richardson Highway MP 167-173 | (3) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.] | Richardson Highway MP 167-173 | Paxson | 2022-12-01 | Z631860000
Northern Region | PROJNAME | CHENA RIDGE ROAD AND CHENA PUMP ROAD RESURFACING | Chena Ridge Road and Chena Pump Road Resurfacing | (2) [on 2022.02.22 project was added.]; [on 2022.06.15 ADDLINFO changed.] | Chena Ridge Road and Chena Pump Road Resurfacing | Fairbanks | 2023-01-01 | NFHWY00570
Northern Region | PROJNAME | BUCKLAND AIRPORT IMPROVEMENTS | Buckland Airport Improvements | (3) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.] | Buckland Airport Improvements | Buckland | 2023-06-01 | NFAPT00604
Southcoast Region | (DELETED) |  |  | (3) [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 FEDNUM changed.] | PSG Mitkof Hwy MPt 10.8 Culvert Replacement - DEC 20 SE PR | Petersburg | 2022-07-01 | SFHWY00379 | SFHWY00379 | 93001 | Joel D Osburn | (907)465-4409 | This project is a Permanent Repair (PR) due to flooding that occurred during the December, 2020 storm event in the Southcoast Region of Alaska. The project need is to replace the existing 5.5' diameter culvert at Mitkof Highway milepoint (MPt) 10.8 to current standards and provide slope and road stability with a new 7' diameter culvert. Repairs may include, but are not limited to, asphalt, embankment, riprap, and drainage. This project repairs sites corresponding to Detailed Damage Inspection Report DDIR AK 2020 01 PTG001. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  |  | Lemon Creek Correctional Center ADA Compliance Upgrades | Statewide | 2022-08-01 | Z520450000 | Z520450000 | N/A | Jesse Campbell | (907)266-2723 | This State funded project will install required ADA upgrades to doors, gates, stairs / ramps, and elevator modernizations at the Lemon Creek Correctional Center located in Juneau, AK. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  | Cold Bay Airport Structure Removal | Cold Bay | 2022-09-01 | SFAPT00399 | SFAPT00399 | AIP 3-02-0065-XXX-2022 | Jesse Campbell | (907)266-2723 | This project is funded with the 2020 CARES grant for Statewide Rural Airports and demolishes two buildings on Cold Bay Airport property. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  | Kodiak Airport Structure Removal | Kodiak | 2022-09-01 | SFAPT00398 | SFAPT00398 | AIP 3-02-0158-XXX-2022 | Jesse Campbell | (907)266-2723 | This project is funded by and addendum to the 2020 CARES grant for Statewide Rural Airports and includes the demolition of two State building on Kodiak airport property and the associated environmental cleanup. |  | Between $200,000 and $500,000
Southcoast Region | ADDED |  |  |  | KTN WOLFE POINT SLOPE STABILITY IMPROVEMENTS | Ketchikan | 2023-01-01 | SFHWY00432 | SFHWY00432 | 920032 | James L Brown | (907)465-1796 | The project will repair unstable slopes from MP 3.0 to MP 3.9 on Tongass Highway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  | (1) [on 2022.04.15 the project was removed.] | HNS AIRPORT RESURFACING | Haines | 2023-05-01 | SFAPT00234 | SFAPT00234 | N/A | James L Brown | (907)465-1796 | The project will rehabilitate the Haines Airport runway and taxiways. Construction activities include, reclimation of paved surfaced, construction of a new taxilane, drainage modification, electrical and lighting replacement, constructing a new access point for the public helipad, and constructing a SREB foundation pad, | The project schedule and budget are being re-developed as the scope has changed. A new SREB building (Project Z68137000) will also be included with this project. | Between $20,000,000 and $30,000,000
Southcoast Region | ADDED |  |  | (1) [on 2022.04.15 the project was removed.] | HNS AIRPORT SRE BUILDING | Haines | 2023-05-01 | Z681370000 | Z681370000 | N/A | James L Brown | (907)465-1796 | This is an FAA funded project which involves the construction of a new 50' x 90' sand, chemical, and snow removal equipment storage building with adjacent parking lot at the location shown in the Haines Airport Master Plan. The work required would include but not limited to site prep, drainage, lighting, building construction, and surfacing. | This project will be advertised as part of Haines Airport Resurfacing, Project No. SFAPT00234. | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  | KING SALMON AIRPORT RWY 18-36 AND GA APRON PVMNT REHAB PROJ | King Salmon | 2023-07-01 | SFAPT00362 | SFAPT00362 | N/A | Peter J Jackson | (907)465-4439 | Repave Runway 18-36 and Taxiways C,D,M, Terminal and GA Apron. Remove aligned taxiway on runway 36 |  | Between $5,000,000 and $10,000,000
Southcoast Region | ANTADVDT | 2022-07-01 | 2022-08-01 | (5) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to June 2022.]; [on 2022.07.12 the ANTADVDT changed to July 2022.] | FFY18 VARIOUS PRIMARY/NON-PRIMARY EAS A/P VISUAL AID REPLCMN | Regionwide | 2022-08-01 | SFAPT00174
Southcoast Region | ANTADVDT | 2022-07-01 | 2022-08-01 | (6) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to June 2022.]; [on 2022.07.12 the ANTADVDT changed to July 2022.] | FFY19 VARIOUS PRIMARY/NON PRIMARY EAS AIRPORTS VISUAL AID RE | Regionwide | 2022-08-01 | SFAPT00203
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (5) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2022-09-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-10-01 | (3) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.03.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to August 2022.] | JNU DOUGLAS HIGHWAY SLOPE STABILIZATION | Juneau | 2022-10-01 | SFHWY00163
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-10-01 | (4) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.03.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.04.15 ENGEST changed.] | JNU DOUGLAS HWY STAGE 2 CONSTRUCTION | Juneau | 2022-10-01 | SFHWY00315
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (1) [on 2022.04.15 project was added.] | JNU N DGLS HWY: BONNIE BRAE-DEC 20 SE PR | Juneau | 2022-09-01 | SFHWY00411
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (3) [on 2022.04.15 project was added.]; [on 2022.07.12 ADDLINFO changed.]; [on 2022.07.12 PROJNAME changed.] | SGY DYEA ROAD 00049 - DEC 20 SE PR | Skagway | 2022-09-01 | SDRER00410
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-10-01 | (4) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2022-10-01 | Z680850000
Southcoast Region | ANTADVDT | 2023-01-01 | 2023-02-01 | (5) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.06.15 ENGEST changed.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-02-01 | SFHWY00058-3
Southcoast Region | DESCRIPTION | Remove and relocate primary wind cone and segmented circle at Yakutat Airport including gravel pad and access road work. | Remove and relocate primary wind cone and segmented circle at Yakutat Airport | (6) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to June 2022.]; [on 2022.07.12 the ANTADVDT changed to July 2022.] | FFY19 VARIOUS PRIMARY/NON PRIMARY EAS AIRPORTS VISUAL AID RE | Regionwide | 2022-08-01 | SFAPT00203
Southcoast Region | PHONENUM | None | (907)465-1796 | (6) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 PROJNAME changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 the ANTADVDT changed to June 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 PHONENUM changed.] | JNU FRANKLIN AND THANE RESURFACING: TRAM PARKING LOT TO MT. ROBERTS ST | Juneau | 2022-08-01 | SFHWY00263
Southcoast Region | PHONENUM | None | (907)465-1796 | (5) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-06-01 | SFHWY00359
Southcoast Region | PROJMAN | Darryl Lester | James L Brown | (6) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 PROJNAME changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 the ANTADVDT changed to June 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 PHONENUM changed.] | JNU FRANKLIN AND THANE RESURFACING: TRAM PARKING LOT TO MT. ROBERTS ST | Juneau | 2022-08-01 | SFHWY00263
Southcoast Region | PROJMAN | Darryl Lester | James L Brown | (5) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-06-01 | SFHWY00359
Southcoast Region | PROJNAME | KTN - WATER ST TRESTLE #1 IMPRVMNT | KTN - WATER STREET TRESTLE NO. 1 IMPROVEMENT | (2) [on 2022.04.15 the ANTADVDT changed to October 2022.]; [on 2022.04.15 DESCRIPTION changed.] | KTN - WATER STREET TRESTLE NO. 1 IMPROVEMENT | Ketchikan | 2022-10-01 | SFHWY00069