## 2022.09.13 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | KNIK GOOSE BAY RD RECONST, VINE TO SETTLER'S BAY (GF) | Wasilla | 2023-03-01 | Z517170000 | Z517170000 | N/A | Tom J Schmid | (907)269-0543 | Reconstruct Knik-Goose Bay Rd from its intersection with the Palmer-Wasilla Hwy (MP 0.740) to its intersection with Settlers Bay Drive (MP 8.090). Work may include widening the roadway to add additional thru traffic lanes, turning lanes, as well as new signals and associated drainage and safety improvements. | Project will be constructed in two phases. The first phase of construction (Fairview Loop Road to Centaur Ave., approx. 4mi) will be advertised under project CFHWY00599. This project will be part of the 2nd phase (Settlers Bay to Fairview Loop Road, approx. 4mi) will be constructed with project Z524640000. | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.04.15 project was added.] | KNIK-GOOSE BAY RD RECONST, PHASE 2 | Wasilla | 2023-03-01 | Z524640000 | Z524640000 | 525016 | Tom J Schmid | (907)269-0543 | Project will improve capacity of this segment of Knik-Goose Bay Road, likely requiring additional lanes. Includes constructing bike/pedestrian facilities and implementing appropriate safety engineering strategies and access management. | Project will be constructed in two phases. The first phase of construction (Fairview Loop Road to Centaur Ave., approx. 4mi) will be advertised under project CFHWY00599. The 2nd phase (Settlers Bay to Fairview Loop Road, approx. 4mi) will be constructed under project Z524640000 and project 51717. | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2023-04-01 | CFHWY00555 | CFHWY00555 | 1657 | Julia R Hanson | (907)269-0753 | This AMATS funded project will reconstructed the traffic signal and street lighting system on 4th Ave between A Street and Ingra Street. Work may included signing, Striping, ATRs, drainage, paving, pedestrian & ADA amenities, utility relocation, landscaping and roadside hardware.
Central Region | ADDED |  |  |  | Anchorage/Eagle River Snow Removal Truck Rental | Anchorage | 2022-09-01 | 22-25-1-020 | 22-25-1-020 | N/A | Vernon S Vreeland | (907)269-0778 | This State funded contract shall provide for the hourly rental of end dump trucks and side dump trucks with operators on an as-needed basis for the Anchorage/Eagle River Maintenance Area for winter snow removal operations. Basis of Award: Bids will be compared on the basis of adjusted basic bid amount after applying applicable bidder preferences. Contract award will be made in the amount of the unit prices for each item. The Department may opt to offer renewal of this contract for four (4) additional one (1) year periods. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | Glenn Highway Rehabilitation Kings River Bridge Section: MP 66.0 to MP 67.2 | Matanuska-Susitna Borough | 2022-09-01 | AKDOT 135(6) | AKDOT 135(6) | AKDOT 135(6) | Chris L Bentz | (907)269-0652 | Replace the existing Kings River Bridge and realign the Glenn Highway to match new bridge location. | This project will be advertised for bidding by Western Federal Lands, NOT on DOT&PF's website. Visit https://sam.gov/search/?index=opp&page=1&sort=-relevance&pageSize=25 for solicitation information. | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  | BETHEL TUNDRA RIDGE ROAD PAVING | Bethel | 2023-02-01 | Z542890000 | Z542890000 | 1207 | Kelly L Summers | (907)269-0546 | Resurface Tundra Ridge Rd, a distance of about 5,500 feet. Project does not include separated pathways or illumination. Local Match Exemption Approved 2/2/05 & 7/13/06. | Resurface Tundra Ridge Rd. Project does not include separated pathways or illumination. | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | Eagle River | 2023-03-01 | CFHWY00621 | CFHWY00621 | 1692 | Julia R Hanson | (907)269-0753 | This preventative maintenance project will resurface North Eagle River Access Road and may include as necessary; signing and striping, guardrail and other roadside hardware, signalization, lighting, drainage work, dig-outs, bridge repair, curb ramps, automated traffic recorders, and utility relocation. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  | CHEVAK AIRPORT REHABILITATION | Chevak | 2023-04-01 | Z537250000 | Z537250000 | 3-02-0468-00X-202X | Aaron C Hughes | (907)269-0523 | This project will rehabilitate the runway, taxiway, apron, and airport access road. The runway safety area will be expanded, and runway grades will be corrected to meet line-of-sight requirements. Additional improvements include replacement of airfield lighting, FAA navaids, wind cones, segmented circle, build a supplemental wind cone access, and apply dust palliative. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  | KENAI PENINSULA BRIDGE DECK REHABILITATIONS FY2023 | Kenai Peninsula | 2023-04-01 | CFHWY00946 | CFHWY00946 | 0A33033 | Galen K Jones | (907)269-0550 | This project proposes to make preservation-related improvements to bridges within Kenai Peninsula Borough to reduce future maintenance and extend their serviceable lifespan. Work includes bridge deck polyester concrete overlays, structural retrofits, miscellaneous structural repairs, expansion joints, bridge rail upgrades, guardrail and end terminals, paving, signing, and striping.
Central Region | ADDLINFO | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements and utilities. | <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00493/00493_Plans.pdf">Preliminary Plans (~14 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (4) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.] | FUNNY RIVER RD PAVEMENT PRESERVATION | Kenai | 2022-12-01 | CFHWY00493
Central Region | ADDLINFO |  | This construction contract will be for the installation of guardrail upgrades in the Anchorage area of Central Region following inventory and assessment efforts. Additional work may include; shoulder widening, slope flattening, bridge rail, signing, and other work associated or necessary for guardrail replacement. | (1) [on 2022.03.15 PROJMAN changed.] | HSIP: CR GUARDRAIL INVENTORY AND UPGRADE | Central | 2022-11-01 | CFHWY00564
Central Region | ADDLINFO |  | This construction contract will be for the installation of guardrail upgrades in the Mat-Su area of Central Region following inventory and assessment efforts. Additional work may include; shoulder widening, slope flattening, bridge rail, signing, and other work associated or necessary for guardrail replacement. | (3) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 FEDNUM changed.]; [on 2022.08.14 LOCATION changed.] | HSIP:CR Guardrail Inventory and Upgrade (North) | Matanuska-Susitna Borough | 2022-11-01 | CFHWY00939
Central Region | ADDLINFO |  | This construction contract will be for the installation of guardrail upgrades in the Kenai Peninsula area of Central Region following inventory and assessment efforts. Additional work may include; shoulder widening, slope flattening, bridge rail, signing, and other work associated or necessary for guardrail replacement. | (2) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 LOCATION changed.] | HSIP:CR Guardrail Inventory and Upgrade (South) | Kenai Peninsula | 2022-11-01 | CFHWY00938
Central Region | ADDLINFO | Replacement of the Takotna River Bridge (bridge #0463). May include bridge work, roadside hardware, drainage improvements, and utilities. Project will advertise with Z516210000 Takotna: Gold Creek Bridge & Tatalina Bridge Replacement. | Replacement of the Takotna River Bridge (bridge #0463). May include bridge work, roadside hardware, drainage improvements, and utilities. Project will advertise with Z516210000 Takotna: Gold Creek Bridge & Tatalina Bridge Replacement. <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00129_51621/00129_Plans.pdf">Preliminary Plans (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (8) [on 2022.02.22 the ANTADVDT changed to September 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.08.14 DESCRIPTION changed.] | TAKOTNA RIVER BRIDGE REPLACEMENT | Takotna | 2023-02-01 | CFHWY00129
Central Region | ADDLINFO | Replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge. Will advertise with CFHWY00129 Takotna River Bridge Replacement. | Replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge. Will advertise with CFHWY00129 Takotna River Bridge Replacement. <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00129_51621/51621_Plans.pdf">Preliminary Plans (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (6) [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.04.15 PROJMAN changed.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.] | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT | Takotna | 2023-02-01 | Z516210000
Central Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (1) [on 2022.08.14 project was added.] | ANC NORTH TERMINAL TICKET AND GATE CUPPS | Anchorage | 2022-09-01 | CSAPT00908
Central Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (3) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.] | Mchugh RWIS Tower Upgrade | Municipality Of Anchorage | 2022-09-01 | CFHWY00428
Central Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (8) [on 2022.05.16 project was added.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 FEDNUM changed.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 REGION changed.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-09-01 | SFAPT00363
Central Region | ANTADVDT | 2022-09-01 | 2022-11-01 | (3) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to September 2022.] | AMATS: HILAND RD MP 0 TO MP 3.2 PAVEMENT PRESERVATION | Eagle River | 2022-11-01 | CFHWY00568
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (1) [on 2022.08.14 project was added.] | ANC SUPPLY WAREHOUSE ROOF REPLACEMENT | Anchorage | 2022-10-01 | CSAPT00858
Central Region | ANTADVDT | 2022-10-01 | 2022-11-01 | (5) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.] | ANC TAXIWAY Z IMPROVEMENTS WEST - PHASE 1 | Anchorage | 2022-11-01 | CFAPT00465
Central Region | ANTADVDT | 2022-10-01 | 2022-12-01 | (4) [on 2022.01.18 the ANTADVDT changed to April 2022.]; [on 2022.02.22 the ANTADVDT changed to October 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.] | FUNNY RIVER RD PAVEMENT PRESERVATION | Kenai | 2022-12-01 | CFHWY00493
Central Region | ANTADVDT | 2022-11-01 | 2023-01-01 | (7) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2023-01-01 | CSAPT00931
Central Region | ANTADVDT | 2022-12-01 | 2023-06-01 | (1) [on 2022.08.14 the ANTADVDT changed to December 2022.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-06-01 | Z581060000
Central Region | ANTADVDT | 2023-01-01 | 2023-02-01 | (2) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 the ANTADVDT changed to January 2023.] | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | Anchorage | 2023-02-01 | CFHWY00286
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (3) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2023-03-01 | CFHWY00253
Central Region | ANTADVDT | 2023-02-01 | 2023-04-01 | (1) [on 2022.03.15 project was added.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-04-01 | CFHWY00012
Central Region | ANTADVDT | 2023-03-01 | 2023-08-01 | (2) [on 2022.04.15 project was added.]; [on 2022.06.15 PROJNAME changed.] | PARKS HWY MP 99 - 163 Drainage & Culvert Improvements | Matanuska-Susitna Borough | 2023-08-01 | CFHWY00592
Central Region | ANTADVDT | 2023-04-01 | 2023-05-01 | (1) [on 2022.08.14 project was added.] | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | Anchorage | 2023-05-01 | CFAPT00992
Central Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $5,000,000 and $10,000,000 | (1) [on 2022.03.15 PROJMAN changed.] | HSIP: CR GUARDRAIL INVENTORY AND UPGRADE | Central | 2022-11-01 | CFHWY00564
Central Region | ENGEST |  | Between $10,000,000 and $20,000,000 | (3) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 FEDNUM changed.]; [on 2022.08.14 LOCATION changed.] | HSIP:CR Guardrail Inventory and Upgrade (North) | Matanuska-Susitna Borough | 2022-11-01 | CFHWY00939
Central Region | ENGEST |  | Between $10,000,000 and $20,000,000 | (2) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 LOCATION changed.] | HSIP:CR Guardrail Inventory and Upgrade (South) | Kenai Peninsula | 2022-11-01 | CFHWY00938
Central Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $40,000,000 and $50,000,000 | (3) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2023-03-01 | CFHWY00253
Central Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 | (8) [on 2022.02.22 the ANTADVDT changed to September 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.08.14 DESCRIPTION changed.] | TAKOTNA RIVER BRIDGE REPLACEMENT | Takotna | 2023-02-01 | CFHWY00129
Central Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 | (6) [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.04.15 PROJMAN changed.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.] | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT | Takotna | 2023-02-01 | Z516210000
Central Region | FEDNUM | AIP 3-02-0122-020-2022 | AIP 3-02-0122-021-2023 | (6) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.07.12 DESCRIPTION changed.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2022-10-01 | CFAPT00491
Central Region | PROJMAN | Sean M Baski | Christina A Huber | (1) [on 2022.03.15 project was added.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-04-01 | CFHWY00012
Northern Region | (DELETED) |  |  | (3) [on 2022.07.12 project was added.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.08.14 ENGEST changed.] | Steele Creek Road Auxiliary Drainage Culvert | Fairbanks | 2022-08-01 | NSHWY00704 | NSHWY00704 | N/A | Daniel S Adamczak | (907)451-2294 | Install a 36" smooth wall steel pipe across Steele Creek Road at the Southwood approach to help manage drainage. After Installation the affected area of Steele Creek Road will be repaved and culvert shall have a thaw pipe, thaw wire and markers installed. |  | Between $200,000 and $500,000
Northern Region | (DELETED) |  |  | (4) [on 2022.02.22 PROJNAME changed.]; [on 2022.05.16 the ANTADVDT changed to June 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.] | Copper River Boat Launch Facilities Improvements (FLAP) | Mccarthy | 2022-09-01 | NFHWY00539 | NFHWY00539 | 851072 | Daniel S Adamczak | (907)451-2294 | Improve the Copper River Boat Launch facilities located at MP 1.5 on the McCarthy Road. Work includes roadside hardware and drainage improvements.
Northern Region | ENGEST |  | Between $2,500,000 and $5,000,000 | (1) [on 2022.08.14 project was added.] | HSIP: Old Steese Highway Shoulder Widening | Fox | 2023-02-01 | NFHWY00527
Northern Region | PROJNAME | EDGERTON HWY MP 24 - 29 RESURFACING | Edgerton Highway MP 24 - 29 Resurfacing | (1) [on 2022.06.15 ENGEST changed.] | Edgerton Highway MP 24 - 29 Resurfacing | Mccarthy | 2022-10-01 | NFHWY00587
Northern Region | PROJNAME | ALASKA HWY PASSING LANES | Alaska Highway Passing Lanes MP 1330-1400 | (2) [on 2022.05.16 project was added.]; [on 2022.08.14 ENGEST changed.] | Alaska Highway Passing Lanes MP 1330-1400 | Tok | 2023-02-01 | Z606320000
Northern Region | PROJNAME | HSIP: OLD STEESE HIGHWAY SHOULDER WIDENING | HSIP: Old Steese Highway Shoulder Widening | (1) [on 2022.08.14 project was added.] | HSIP: Old Steese Highway Shoulder Widening | Fox | 2023-02-01 | NFHWY00527
Southcoast Region | (DELETED) |  |  | (6) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2022-07-01 | SFHWY00186 | SFHWY00186 | 3244 | Nathan A Purves | (907)465-4521 | Provide additional illumination at the Stedman/Deermount intersection to achieve a level of luminance that meets current DOT&PF standards. Construct a concrete sidewalk bulbout on the Stedman side of the marked crosswalk. The bulbout will extend from the existing sidewalk to the edge of the traveled way. |  | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  | (6) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to June 2022.]; [on 2022.07.12 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.] | FFY18 VARIOUS PRIMARY/NON-PRIMARY EAS A/P VISUAL AID REPLCMN | Regionwide | 2022-08-01 | SFAPT00174 | SFAPT00174 | 3-02-0200-121-2018 | Peter J Jackson | (907)465-4439 | Replace lighted beacon at Yakutat Airport. | To be advertised with project SFAPT00203 (relocate Segmented Circle and Lighted Wind Cone). | Between $200,000 and $500,000
Southcoast Region | (DELETED) |  |  | (8) [on 2022.02.22 the ANTADVDT changed to February 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to June 2022.]; [on 2022.07.12 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.08.14 DESCRIPTION changed.] | FFY19 VARIOUS PRIMARY/NON PRIMARY EAS AIRPORTS VISUAL AID RE | Regionwide | 2022-08-01 | SFAPT00203 | SFAPT00203 | 3-02-0200-126-2019 | Peter J Jackson | (907)465-4439 | Remove and relocate primary wind cone and segmented circle at Yakutat Airport | To be advertised with Project SFAPT00174 | Between $200,000 and $500,000
Southcoast Region | (DELETED) |  |  | (8) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 PROJNAME changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 the ANTADVDT changed to June 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 PHONENUM changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.] | JNU FRANKLIN AND THANE RESURFACING: TRAM PARKING LOT TO MT. ROBERTS ST | Juneau | 2022-08-01 | SFHWY00263 | SFHWY00263 | 3250 | James L Brown | (907)465-1796 | Resurface Franklin Street from the Tram parking lot to the intersection of Thane Road and Mt. Roberts Street. Associated preventive maintenance activities may include minor structural section improvements, drainage repairs, striping, signs, and ADA improvements. | Pending funding availability. Advertisement may be delayed. | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (1) [on 2022.02.22 DESCRIPTION changed.] | JNU KAXDIGOOWU HEEN DEI IMP (BROTHERHOOD BRIDGE TRAIL IMP) | Juneau | 2022-09-01 | SFHWY00259 | SFHWY00259 | TA18010 | Peter J Jackson | (907)465-4439 | This project will design and improve the Kaxdigoowu Heen Dei (Kax) Trail from River Road to the edge of Brotherhood Meadow, where a re-route planned for construction in 2019 would end, and create a new segment of paved trail that connects from the edge of Brotherhood Meadow to the Wildmeadow Neighborhood and the newly constructed trail from Pederson Hill neighborhood. Work will primarily consist of selected areas of subgrade repair, repave the 8 foot wide trail, replace and add new culverts as needed, and build approximately 1,500 feet of new trail section. The new trail will be composed of fill, D-1, and 8 foot wide asphalt with 1 foot shoulders. the pedestrian bridge at Montana Creek will be replaced or modified to provide a larger span that allows for some natural stream movement and can withstand emergency and maintenance vehicle use once again, and the banks armored to increase the expected useful life of the bridge. Additional improvements include adding bike racks, installing interpretive signs, and increasing site distance along the trail. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (3) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.] | CRAIG ADA IMPROVEMENTS | Craig | 2023-03-01 | SFHWY00377 | SFHWY00377 | 3274 | Bran P Pollard | (907)465-4526 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit.
Southcoast Region | (DELETED) |  |  | (1) [on 2022.05.16 project was added.] | ANG AIRPORT INITIATION - CLEARING | Angoon | 2023-04-01 | SFAPT00086-C | SFAPT00086-C | N/A | David B Epstein | (907)465-4483 | Construction of a new airport and access roadways located 2.5 miles south of Angoon. CC: 24300114 LC: 33002332 |  | Between $50,000,000 and $60,000,000
Southcoast Region | (DELETED) |  |  | (4) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2023-05-01 | SFAPT00178 | SFAPT00178 | N/A | Gregory K Lockwood | (907)465-2393 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
Southcoast Region | ADDED |  |  |  | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2022-09-01 | SFAPT00144 | SFAPT00144 | 3-02-0158-0XX-202X | James L Brown | (907)465-1796 | Project will replace/upgrade access controls and gates to meet 49 CFR 1542 requirements. Replace existing fencing when needed. |  | Between $5,000,000 and $10,000,000
Southcoast Region | ADDED |  |  | (5) [on 2022.02.22 the ANTADVDT changed to December 2022.]; [on 2022.02.22 ENGEST changed.]; [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.05.16 the project was removed.] | HNH Harbor Way Pedestrian Improvements & Pitt Island Cemetery Walkway | Hoonah | 2023-02-01 | SFHWY00278 | SFHWY00278 | 3255 | Bran P Pollard | (907)465-4526 | The Hoonah Harbor Way Pedestrian Improvements & Pitt Island Cemetery Walkway project is designed to address two major issues for the community: 1) Provide safe and reliable access to the community's cemetery on Pitt Island; and 2) Alleviate tourist-related pedestrian congestion in the harbor area. The City of Hoonah plans to construct a 6-foot wide sidewalk/walkway from the Hoonah city center out to Pitt Island and the community cemetery. This 0.8 mile project will start at the intersection of Front Street and Harbor Way and end on Pitt Island. Approximately 0.5 miles of the sidewalk/walkway will be built atop the US Army Corps of Engineers' breakwater and a 175-foot long gangway will be installed from the shore to the breakwater. | CMGC anticipated. Not to be advertised. | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2023-08-01 | SFHWY00326 | SFHWY00326 | 3265 | Brett M Wells | (907)465-1607 | Design and replace two damaged culverts with new Aquatic Organism Passage structures across Trout Creek and Little Trout Creek in Cold Bay, AK. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  | (2) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2023-08-01 | Z686060000 | Z686060000 | 956028 | Gregory K Lockwood | (907)465-2393 | Reconstruction of Haines Highway from Milepost 20 to 25 including the Chilkat River bridge. | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise | Between $30,000,000 and $40,000,000
Southcoast Region | ADDED |  |  |  | HYG - HYDABURG SEAPLANE FACILITY REFURBISHMENT | Hydaburg | 2023-08-01 | SFAPT00328 | SFAPT00328 | N/A | Loren K Gehring | (907)465-8189 | Refurbish and/or replace existing seaplane float facility in Hydaburg, AK. Investigate replacement at a new location |  | Between $5,000,000 and $10,000,000
Southcoast Region | ADDED |  |  | (2) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.] | KING SALMON AIRPORT PERIMETER FENCING UPGRADES | King Salmon | 2023-08-01 | SFAPT00124 | SFAPT00124 | N/A | Loren K Gehring | (907)465-8189 | Replace/upgrade access controls/gates to meet 49 CFR 1542 requirements. Replace existing fencing as needed. | Construct perimeter fencing and gate upgrades. Upgrades include providing new automatic vehicle gates and pedestrian gates with electric lock gate systems. | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  | (1) [on 2022.04.15 the project was removed.] | KTN AIRPORT SEAPLANE RAMP AND HAUL OUT REFURBISHMENT | Ketchikan | 2023-08-01 | SFAPT00327 | SFAPT00327 | N/A | Loren K Gehring | (907)465-8189 | Refurbish and/or replace existing seaplane float and haul-out ramp facility at the Ketchikan Airport. Investigate replacement at a new location. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  |  | SR REGIONWIDE GUARDRAIL INVENTORY AND UPGRADE HSIP | Regionwide | 2023-08-01 | SFHWY00404 | SFHWY00404 | 3278 | Nathan A Purves | (907)465-4521 | Assess and correct guardrail safety deficiencies along Principal and Minor Arterial routes with posted speeds of 40 mph or higher. Typical deficiencies include, but are not limited to, steel washers on the face of rail, insufficient length of need, steel blockouts without backup plates, and break away cable terminals.
Southcoast Region | ADDLINFO |  | Remove and replace existing bridge structure. | (3) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2023-08-01 | SFHWY00070
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-11-01 | (5) [on 2022.01.18 the ANTADVDT changed to July 2022.]; [on 2022.02.22 the ANTADVDT changed to August 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 PHONENUM changed.] | JNU EGAN YANDUKIN INTERSECTION IMPROVEMENTS HSIP | Juneau | 2022-11-01 | SFHWY00307
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-09-01 | (1) [on 2022.08.14 project was added.] | Lemon Creek Correctional Center ADA Compliance Upgrades | Statewide | 2022-09-01 | Z520450000
Southcoast Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (6) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2022-10-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (4) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the ANTADVDT changed to September 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 ENGEST changed.] | POW HOLLIS HWY GUARDRAIL SAFETY IMPROVEMENTS HSIP | Prince Of Wales Island | 2022-10-01 | SFHWY00306
Southcoast Region | ANTADVDT | 2022-10-01 | 2023-01-01 | (5) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2023-01-01 | Z680850000
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-08-01 | (3) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2023-08-01 | SFHWY00070
Southcoast Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $500,000 and $1,000,000 | (5) [on 2022.01.18 the ANTADVDT changed to July 2022.]; [on 2022.02.22 the ANTADVDT changed to August 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 PHONENUM changed.] | JNU EGAN YANDUKIN INTERSECTION IMPROVEMENTS HSIP | Juneau | 2022-11-01 | SFHWY00307
Southcoast Region | PHONENUM | (907)465-1796 | (907)465-1607 | (2) [on 2022.04.15 the project was removed.]; [on 2022.08.14 project was added.] | HNS AIRPORT SRE BUILDING | Haines | 2023-05-01 | Z681370000
Southcoast Region | PHONENUM | (907)465-1796 | (907)465-1607 | (7) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-06-01 | SFHWY00359
Southcoast Region | PROJMAN | James L Brown | Brett M Wells | (2) [on 2022.04.15 the project was removed.]; [on 2022.08.14 project was added.] | HNS AIRPORT SRE BUILDING | Haines | 2023-05-01 | Z681370000
Southcoast Region | PROJMAN | James L Brown | Brett M Wells | (7) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-06-01 | SFHWY00359