## 2022.10.20 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (2) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to September 2022.] | ANC NORTH TERMINAL TICKET AND GATE CUPPS | Anchorage | 2022-09-01 | CSAPT00908 | CSAPT00908 | N/A | Jennifer C Pepin | (907)266-2549 | Modify or replace casework, including scales, for ADA compliance at North Terminal ticket lobby and passenger boarding areas. Install CUPPS equipment at each location. Install phones and public address system. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (4) [on 2022.01.18 the ANTADVDT changed to July 2022.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.08.14 DESCRIPTION changed.] | ANC Parking Garage PG111 Repairs and Improvement | Anchorage | 2022-09-01 | CSAPT00566 | CSAPT00566 | N/A | John W Turley | (907)266-2171 | This project will repair or replace deck membranes of building PG-111. Parking Garage and will make other repairs including blue light system and electric lighting.
Central Region | (DELETED) |  |  | (1) [on 2022.09.13 project was added.] | Anchorage/Eagle River Snow Removal Truck Rental | Anchorage | 2022-09-01 | 22-25-1-020 | 22-25-1-020 | N/A | Vernon S Vreeland | (907)269-0778 | This State funded contract shall provide for the hourly rental of end dump trucks and side dump trucks with operators on an as-needed basis for the Anchorage/Eagle River Maintenance Area for winter snow removal operations. Basis of Award: Bids will be compared on the basis of adjusted basic bid amount after applying applicable bidder preferences. Contract award will be made in the amount of the unit prices for each item. The Department may opt to offer renewal of this contract for four (4) additional one (1) year periods. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (1) [on 2022.09.13 project was added.] | Glenn Highway Rehabilitation Kings River Bridge Section: MP 66.0 to MP 67.2 | Matanuska-Susitna Borough | 2022-09-01 | AKDOT 135(6) | AKDOT 135(6) | AKDOT 135(6) | Chris L Bentz | (907)269-0652 | Replace the existing Kings River Bridge and realign the Glenn Highway to match new bridge location. | This project will be advertised for bidding by Western Federal Lands, NOT on DOT&PF's website. Visit https://sam.gov/search/?index=opp&page=1&sort=-relevance&pageSize=25 for solicitation information. | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (9) [on 2022.05.16 project was added.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 FEDNUM changed.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 REGION changed.]; [on 2022.09.13 the ANTADVDT changed to September 2022.] | Sitka Airport Snow Removal Equipment Building Rehabilitation | Sitka | 2022-09-01 | SFAPT00363 | SFAPT00363 | AIP 3-02-0268-031-2022 | Jesse Campbell | (907)266-2723 | Rehabilitation of existing combined use equipment building to include siding replacement, equipment bay door replacements, heating system replacement, and building envelope improvements |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (2) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to February 2023.] | FAIRVIEW LOOP PATHWAY AND SAFETY IMPROVEMENTS (GF/GO) | Wasilla | 2023-02-01 | Z560200000 | Z560200000 | N/A | Sean M Baski | (907)269-0566 | Revised scope 3/14: This project will construct a separated pathway along Fairview Loop Road from Top of the World Circle to Edlund Road. Construction of the pathway may be extended further east depending on the available funding. Safety improvements at selected intersections and drainage improvements not included the Fairview Loop Pavement Preservation project will also be included in the project. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  | Mt. Edgecumbe High School Building 1330 Girl's Restroom Renovations | City & Borough Of Sitka | 2022-11-01 | 25RC053605 | 25RC053605 | N/A | Christopher S Hodgin | (907)269-7484 | This state funded project includes demolition and replacement of the existing Girl’s restroom in Building 1330. New installed work includes renovated flooring, under and above floor plumbing and plumbing fixtures, restroom partitions and accessories, exhaust fan replacement, electric heating, lighting replacements, wall repairs, and all supportive work as required. |  | Less than $200,000
Central Region | ADDED |  |  |  | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2023-01-01 | CFAPT00983 | CFAPT00983 | 3-02-0016-XXX-20XX | Jennifer M Lombardo | (907)266-2731 | Remove and replace approximately 1,000 feet of security fence along the northeast edge of the airfield. Project includes clearing, grubbing, embankment extension and replacing swing gates. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | Anchorage District Paving | Anchorage | 2023-02-01 | 22-25-1-22 | 22-25-1-22 | N/A | Vernon S Vreeland | (907)269-0757 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Anchorage Maintenance District boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | Mat-Su District Paving | Matanuska-Susitna Borough | 2023-02-01 | 22-25-1-021 | 22-25-1-021 | N/A | Vernon S Vreeland | (907)269-0757 | This State-funded project is to perform asphalt paving and maintenance work on State of Alaska, Department of Transportation & Public Facilities roadways within the Matanuska-Susitna District boundaries, on an as-needed basis. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Central Region | 2023-07-01 | CFHWY00523 | CFHWY00523 | 1685 | Christina A Huber | (907)269-0572 | Pavement preservation, bridge work, roadside hardware, drainage improvements, and utilities. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  | HSIP: BOGARD AT ENGSTROM RD/GREEN FOREST DR INTER IMP | Wasilla | 2023-09-01 | CFHWY00453 | CFHWY00453 | 1630 | Chris L Bentz | (907)269-0652 | Reconstruction, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities.
Central Region | ADDED |  |  |  | SEWARD HWY: MP 25.5-36, TRAIL RIVER TO STERLING WYE REHAB | Kenai Peninsula | 2023-09-01 | Z546590000 | Z546590000 | 311031 | Chris L Bentz | (907)269-0652 | Restoring, resurfacing, and rehabilitation (3R) of the Seward Highway, from MP 25.5 to 36, Trail River to the Sterling Wye, to preserve and extend the service life of the highway, enhance safety, and provide passing lanes. The project may also include pedestrian amenities and traffic calming in the community of Moose Pass.This is a new project in the corridor to revisit the roadway rehabilitation, initially thru the development of an Environmental Document.
Central Region | ADDLINFO |  | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00253/00253.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (5) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2023-03-01 | CFHWY00253
Central Region | ADDLINFO |  | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00012/00012_Plans.pdf">Preliminary Plans (~150 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (3) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-06-01 | CFHWY00012
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (1) [on 2022.08.14 project was added.] | Cold Bay Airport Structure Removal | Cold Bay | 2022-10-01 | SFAPT00399
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (1) [on 2022.08.14 project was added.] | Kodiak Airport Structure Removal | Kodiak | 2022-10-01 | SFAPT00398
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (4) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to September 2022.] | MAT-SU BOROUGH ROAD REPAIRS - NOV 2018 EQ PERM REPAIRS (MSB) | Matanuska-Susitna Borough | 2022-10-01 | CFHWY00648
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (4) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.] | Mchugh RWIS Tower Upgrade | Municipality Of Anchorage | 2022-10-01 | CFHWY00428
Central Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (2) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2022-10-01 | 25RC053613
Central Region | ANTADVDT | 2022-10-01 | 2023-02-01 | (2) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to October 2022.] | ANC SUPPLY WAREHOUSE ROOF REPLACEMENT | Anchorage | 2023-02-01 | CSAPT00858
Central Region | ANTADVDT | 2022-10-01 | 2022-11-01 | (7) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.07.12 DESCRIPTION changed.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 FEDNUM changed.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2022-11-01 | CFAPT00491
Central Region | ANTADVDT | 2022-11-01 | 2023-01-01 | (6) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.] | ANC TAXIWAY Z IMPROVEMENTS WEST - PHASE 1 | Anchorage | 2023-01-01 | CFAPT00465
Central Region | ANTADVDT | 2022-11-01 | 2023-01-01 | (1) [on 2022.08.14 project was added.] | STERLING SAFETY CORRIDOR IMPROVEMENTS MP 82.5 TO 94 DESIGN BUILD | Sterling | 2023-01-01 | CFHWY00130
Central Region | ANTADVDT | 2022-12-01 | 2023-06-01 | (1) [on 2022.01.18 the ANTADVDT changed to December 2022.] | MEKORYUK AIRPORT REHABILITATION | Mekoryuk | 2023-06-01 | CFAPT00288
Central Region | ANTADVDT | 2023-01-01 | 2023-03-01 | (4) [on 2022.06.15 project was added.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.08.14 ENGEST changed.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-03-01 | CFAPT00682
Central Region | ANTADVDT | 2023-04-01 | 2023-06-01 | (3) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-06-01 | CFHWY00012
Central Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $40,000,000 and $50,000,000 | (6) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.] | ANC TAXIWAY Z IMPROVEMENTS WEST - PHASE 1 | Anchorage | 2023-01-01 | CFAPT00465
Central Region | PHONENUM | (907)269-0566 | (907)269-0572 | (3) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2023-06-01 | CFHWY00012
Central Region | REGION | Southcoast Region | Central Region | (1) [on 2022.08.14 project was added.] | Cold Bay Airport Structure Removal | Cold Bay | 2022-10-01 | SFAPT00399
Central Region | REGION | Southcoast Region | Central Region | (1) [on 2022.08.14 project was added.] | Kodiak Airport Structure Removal | Kodiak | 2022-10-01 | SFAPT00398
Marine Highways | ADDLINFO | Refurbish fender system at Berth 3 and conduct minor improvements to utilities at Berth 1. | Make improvements to AMHS KTN Berth III Ferry terminal: modify the fender system along the 120' float, install new gangway to access the offshore dolphin, make electrical improvements for the facility. | (5) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.08.14 DESCRIPTION changed.] | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | Ketchikan | 2022-11-01 | Z674660000
Marine Highways | ANTADVDT | 2022-10-01 | 2022-11-01 | (5) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.08.14 DESCRIPTION changed.] | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | Ketchikan | 2022-11-01 | Z674660000
Northern Region | (DELETED) |  |  | (9) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.02.22 ENGEST changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 LOCATION changed.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.08.14 ADDLINFO changed.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.08.14 ENGEST changed.] | Dalton Highway MP 18-37 Reconstruction | Livengood | 2022-09-01 | Z607350000 | Z607350000 | 652017 | Carl F Heim | (907)451-5359 | Reconstruct the Dalton Highway from Milepost 18 to 37. The project work includes bridge work, roadside hardware and drainage improvements. Bridge work includes Hess Creek Bridge #1213 replacement. | The department was previously uncertain on funding and permit timelines for this project and is now confident the project will advertise in September 2022. | Between $40,000,000 and $50,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.06.15 project was added.] | Parks Hwy MP 319-325 Reconstruction | Nenana | 2022-09-01 | Z606570000 | Z606570000 | 0A45028 | Jennifer J Wright | (907)371-8949 | Reconstruct the Parks Highway from MP 319-325. Project will include realignment, roadside hardware, drainage improvements and utilities. | Project will be advertised as CMGC RFP. Project website: https://dot.alaska.gov/nreg/parks305to325/ | Between $50,000,000 and $60,000,000
Northern Region | (DELETED) |  |  | (2) [on 2022.06.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to December 2022.] | Old Steese Highway Reconstruction | Fairbanks | 2022-12-01 | Z624870000 | Z624870000 | N/A | Russell M Johnson | (907)451-5059 | Revised Scope: Reconstruct the Old Steese Highway from 3rd Street to, and including, the intersection at Johansen Expressway. | Project will be advertised as CMGC RFP. Project website: https://dot.alaska.gov/nreg/oldsteese/ | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  | RICHARDSON HWY MILEPOST 233 BEAR CREEK BRIDGE #0593 REPLMNT | Delta Junction | 2023-04-01 | NFHWY00278 | NFHWY00278 | 714024 | Jennifer J Wright | (907)371-8949 | Reconstruct the Richardson Highway between Milepost 232 - 234.5 and replace Bear Creek Bridge #0593. Project will include drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDLINFO | Proposed work in 2023 includes, subject to funding availability: Aztec Road Service Area resurfacing (Holmes/Dennis Road area-FNSB) and City of Fairbanks 2nd Avenue dog park access road. | Proposed work in 2023 includes, subject to funding availability: Aztec Road Service Area resurfacing (Holmes/Dennis Road area-FNSB) and City of Fairbanks 2nd Avenue dog park access road. Possible College Road RRFB. | (2) [on 2022.03.15 project was added.]; [on 2022.06.15 ADDLINFO changed.] | FAST AREA SURFACE UPGRADES FFY2023 | Fairbanks North Star Borough | 2023-03-01 | NFHWY00633
Northern Region | ANTADVDT | 2022-10-01 | 2022-12-01 | (2) [on 2022.06.15 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.] | Edgerton Highway MP 24 - 29 Resurfacing | Mccarthy | 2022-12-01 | NFHWY00587
Northern Region | ANTADVDT | 2022-11-01 | 2023-02-01 | (3) [on 2022.07.12 project was added.]; [on 2022.08.14 the ANTADVDT changed to November 2022.]; [on 2022.08.14 ENGEST changed.] | Birch Hill Access Road Preventive maintenance | Northern Region | 2023-02-01 | NFHWY00703
Northern Region | ANTADVDT | 2022-11-01 | 2022-12-01 | (5) [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.05.16 FEDNUM changed.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.06.15 ENGEST changed.] | Richardson Highway MP 128-138 Rehabilitation | Tazlina | 2022-12-01 | NFHWY00265
Northern Region | ANTADVDT | 2022-12-01 | 2023-02-01 | (2) [on 2022.02.22 the ANTADVDT changed to December 2022.]; [on 2022.08.14 ENGEST changed.] | NOR REG VARIOUS AIRPORTS VISUAL AID REPLACEMENT FFY2020 | Regionwide | 2023-02-01 | NFAPT00537
Northern Region | ANTADVDT | 2022-12-01 | 2023-02-01 | (1) [on 2022.01.18 project was added.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-02-01 | Z607150000
Northern Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (2) [on 2022.03.15 project was added.]; [on 2022.06.15 ADDLINFO changed.] | FAST AREA SURFACE UPGRADES FFY2023 | Fairbanks North Star Borough | 2023-03-01 | NFHWY00633
Northern Region | ENGEST |  | Between $2,500,000 and $5,000,000 | (1) [on 2022.08.14 project was added.] | FAIRBANKS 5TH AVENUE RECONSTRUCTION | Fairbanks | 2023-05-01 | NFHWY00445
Northern Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 | (1) [on 2022.07.12 project was added.] | CHALKYITSIK AIRPORT IMPROVEMENTS | Chalkyitsik | 2023-06-01 | Z625970000
Northern Region | ENGEST |  | Between $5,000,000 and $10,000,000 | (1) [on 2022.07.12 project was added.] | LITTLE DIOMEDE HELIPAD IMPROVEMENTS | Diomede | 2023-06-01 | Z614700000
Northern Region | PROJNAME | Richardson Highway MP 167-173 | Richardson Highway MP 148-173 (CONST MP 167-173) | (4) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2022-12-01 | Z631860000
Northern Region | PROJNAME | RICHARDSON HWY MP 266-341 PASSING LANES | Richardson Highway MP 266-341 Passing Lanes | (1) [on 2022.01.18 project was added.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-02-01 | Z607150000
Southcoast Region | (DELETED) |  |  | (2) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to September 2022.] | Lemon Creek Correctional Center ADA Compliance Upgrades | Statewide | 2022-09-01 | Z520450000 | Z520450000 | N/A | Jesse Campbell | (907)266-2723 | This State funded project will install required ADA upgrades to doors, gates, stairs / ramps, and elevator modernizations at the Lemon Creek Correctional Center located in Juneau, AK. |  | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  | (7) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2022-10-01 | SFAPT00212 | SFAPT00212 | 3-02-0200-120-2018 | Peter J Jackson | (907)465-4439 | Remove and replace secondary wind cone and install new conduit and wire. Remove and replace primary wind cone and install new conduit and wire. Remove and replace rotating Airport Beacon. Phase 4 - CC 24300206 LC 33004012 |  | Between $200,000 and $500,000
Southcoast Region | (DELETED) |  |  | (3) [on 2022.04.15 the ANTADVDT changed to October 2022.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.08.14 PROJNAME changed.] | KTN - WATER STREET TRESTLE NO. 1 IMPROVEMENT | Ketchikan | 2022-10-01 | SFHWY00069 | SFHWY00069 | 3224 | Kirk D Miller | (907)465-1215 | Replace the Water Street Trestle No. 1 bridge structure with (No. 389) with MSE wall. Work includes new utilities, pavement and sidewalks. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (1) [on 2022.07.12 project was added.] | KTN HOADLEY CREEK BRIDGE REPLACEMENT | Ketchikan | 2023-06-01 | SFHWY00197 | SFHWY00197 | 902044 | Peter J Jackson | (907)465-4439 | Refurbish or replace Hoadley Creek Bridge (Bridge Number 725) and associated roadway approaches. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  | ANG AIRPORT INITIATION | Angoon | 2023-09-01 | SFAPT00086 | SFAPT00086 | N/A | David B Epstein | (907)465-4483 | Construction of a new airport and access roadways located 2.5 miles south of Angoon. CC: 24300114 LC: 33002332 |  | Greater than $100,000,000
Southcoast Region | ADDED |  |  | (2) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.] | KDK CHINIAK HIGHWAY REHABILITATION: MILE POST 15 TO 31 | Kodiak | 2023-09-01 | SFHWY00111 | SFHWY00111 | 391015 | James L Brown | (907)465-1796 | Rehabilitate the Chiniak Highway from Milepost 15 to just past 31 to improve and preserve the roadway subgrade and surface. Address lighting, guardrails, drainage, culverts and other highway appurtenances as needed. |  | Between $10,000,000 and $20,000,000
Southcoast Region | ANTADVDT | 2022-08-01 | 2022-11-01 | (5) [on 2022.01.18 project was added.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.07.12 PROJNAME changed.] | HNS MOSQUITO LAKE ROAD 00044 - DEC 20 SE PR | Haines | 2022-11-01 | SDRER00408
Southcoast Region | ANTADVDT | 2022-09-01 | 2022-11-01 | (2) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.] | JNU N DGLS HWY: BONNIE BRAE-DEC 20 SE PR | Juneau | 2022-11-01 | SFHWY00411
Southcoast Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (1) [on 2022.09.13 project was added.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2022-10-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2022-09-01 | 2022-10-01 | (4) [on 2022.04.15 project was added.]; [on 2022.07.12 ADDLINFO changed.]; [on 2022.07.12 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to September 2022.] | SGY DYEA ROAD 00049 - DEC 20 SE PR | Skagway | 2022-10-01 | SDRER00410
Southcoast Region | ANTADVDT | 2022-10-01 | 2023-02-01 | (5) [on 2022.01.18 ENGEST changed.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.] | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | Hoonah | 2023-02-01 | SFAPT00236
Southcoast Region | ANTADVDT | 2022-10-01 | 2022-11-01 | (5) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.03.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.] | JNU DOUGLAS HWY STAGE 2 CONSTRUCTION | Juneau | 2022-11-01 | SFHWY00315
Southcoast Region | ANTADVDT | 2023-01-01 | 2023-04-01 | (6) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2023-04-01 | Z680850000
Southcoast Region | ANTADVDT | 2023-02-01 | 2023-04-01 | (5) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2023-04-01 | SFAPT00412
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-09-01 | (2) [on 2022.04.15 the project was removed.]; [on 2022.08.14 project was added.] | HNS AIRPORT RESURFACING | Haines | 2023-09-01 | SFAPT00234
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-09-01 | (4) [on 2022.04.15 the project was removed.]; [on 2022.08.14 project was added.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.] | HNS AIRPORT SRE BUILDING | Haines | 2023-09-01 | Z681370000
Southcoast Region | ANTADVDT | 2023-06-01 | 2023-07-01 | (9) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-07-01 | SFHWY00359
Southcoast Region | DESCRIPTION | (1) Replace the electric vehicle gates, Gate #3 and Gate #9. Install up-to-date security systems on vehicle gates, Gate #3 and Gate #9; and (2) Install compatible/compliant security entry systems on pedestrian gates, Gate #4, #8, #11 and #13. | Replace 10 vehicle (nos. 1, 2, 3, 7, 8, 11, 13, 16, 17, and 20) and 4 pedestrian (nos. 4, 6, 12, and 15) access points. Provide card reader access to pedestrian gate nos. 4, 6, 12 and 15, and all three doors to the ARFF Building. Provide card reader access points to vehicle gates 2, 7, 13, and 16. Repair approximately 1200-1500 feet of fence line, permanently remove/fence over vehicle gate nos. 5, 10, 18, and 19. Permanently remove/fence over pedestrian gate nos. 9 and 14. | (5) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2023-04-01 | SFAPT00412
Southcoast Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $1,000,000 and $2,500,000 | (4) [on 2022.04.15 project was added.]; [on 2022.07.12 ADDLINFO changed.]; [on 2022.07.12 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to September 2022.] | SGY DYEA ROAD 00049 - DEC 20 SE PR | Skagway | 2022-10-01 | SDRER00410
Southcoast Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $1,000,000 and $2,500,000 | (1) [on 2022.09.13 project was added.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2023-08-01 | SFHWY00326
Southcoast Region | PHONENUM | (907)465-1796 | (907)465-1607 | (2) [on 2022.04.15 the project was removed.]; [on 2022.08.14 project was added.] | HNS AIRPORT RESURFACING | Haines | 2023-09-01 | SFAPT00234
Southcoast Region | PROJMAN | James L Brown | Brett M Wells | (2) [on 2022.04.15 the project was removed.]; [on 2022.08.14 project was added.] | HNS AIRPORT RESURFACING | Haines | 2023-09-01 | SFAPT00234