## 2022.11.17 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (5) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.] | MAT-SU BOROUGH ROAD REPAIRS - NOV 2018 EQ PERM REPAIRS (MSB) | Matanuska-Susitna Borough | 2022-10-01 | CFHWY00648 | CFHWY00648 | 92010 | Steven J Rzepka | (907)269-0592 | This project will design and construct repairs for the November 30, 2018 earthquake in the Central Region of Alaska on Point MacKenzie Road, Vine Road, and South Settlers Bay Drive. Repairs may include, but are not limited to, asphalt, embankment, roadside hardware, retaining walls, utilities, and drainage. |  | Between $5,000,000 and $10,000,000
Central Region | (DELETED) |  |  | (1) [on 2022.10.20 project was added.] | Mt. Edgecumbe High School Building 1330 Girl's Restroom Renovations | City & Borough Of Sitka | 2022-11-01 | 25RC053605 | 25RC053605 | N/A | Christopher S Hodgin | (907)269-7484 | This state funded project includes demolition and replacement of the existing Girl’s restroom in Building 1330. New installed work includes renovated flooring, under and above floor plumbing and plumbing fixtures, restroom partitions and accessories, exhaust fan replacement, electric heating, lighting replacements, wall repairs, and all supportive work as required. |  | Less than $200,000
Central Region | (DELETED) |  |  | (1) [on 2022.10.20 project was added.] | HSIP: BOGARD AT ENGSTROM RD/GREEN FOREST DR INTER IMP | Wasilla | 2023-09-01 | CFHWY00453 | CFHWY00453 | 1630 | Chris L Bentz | (907)269-0652 | Reconstruction, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities.
Central Region | (DELETED) |  |  | (1) [on 2022.10.20 project was added.] | SEWARD HWY: MP 25.5-36, TRAIL RIVER TO STERLING WYE REHAB | Kenai Peninsula | 2023-09-01 | Z546590000 | Z546590000 | 311031 | Chris L Bentz | (907)269-0652 | Restoring, resurfacing, and rehabilitation (3R) of the Seward Highway, from MP 25.5 to 36, Trail River to the Sterling Wye, to preserve and extend the service life of the highway, enhance safety, and provide passing lanes. The project may also include pedestrian amenities and traffic calming in the community of Moose Pass.This is a new project in the corridor to revisit the roadway rehabilitation, initially thru the development of an Environmental Document.
Central Region | ADDED |  |  |  | 1800 S. Knik Goose Bay Road Structures Removal | Wasilla | 2022-11-01 | Z524640000-A | Z524640000-A | N/A | Vadim Belozertsev | (907)269-0879 | This federally funded contract includes the removal and disposal or salvage of all buildings, fences, structures, abandoned utilities and any other obstructions and improvements at 1800 S. Knik Goose Bay Road, located in Wasilla, Alaska: |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | Adak Airport Maintenance Station Reskin Design\Build | Adak | 2022-11-01 | 25RC013614 | 25RC013614 | N/A | David R Hepler | (907)269-0815 | Design build project to replace the old metal siding and batt insulation with insulated metal panels. Replacing man doors and windows. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  | ANC North Terminal Circulation Finishes | Anchorage | 2022-11-01 | CSAPT00933 | CSAPT00933 | N/A | Jennifer C Pepin | (907)266-2549 | This state funded project replaces and updates the existing floor and wall finishes within the existing passenger north terminal at the Ted Stevens Anchorage International Airport. This project also includes two (2) additive alternates. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  | 500 Hollywood Drive Structures Removal | Central Region | 2023-01-01 | z537350000 | z537350000 | N/A | None | None | This federally funded contract includes the removal and disposal or salvage of all buildings, foundations, fences, structures, old pavements, and any other obstructions and improvements at 500 Hollywood Drive, located in Anchorage, Alaska: |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  | CHIGNIK AIRPORT SREB REHAB | Chignik | 2023-01-01 | SFAPT00368 | SFAPT00368 | N/A | Alyson K Wardell | (907)269-0869 | Damaged panels and doors are allowing weather and wildlife access to building interior, damaging equipment and shortening the life of the building. This project will replace the metal wall panels and the man door and its frame, to protect the snow removal equipment and extend the life of the building. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  | ANC NORTH TERMINAL BAGGAGE HANDLING SYSTEM IMPROVEMENTS | Anchorage | 2023-02-01 | CSAPT00932 | CSAPT00932 | N/A | Jennifer C Pepin | (907)266-2549 | Upgrade the baggage handling system (BHS) with an automatic sorter and up to three additional induction points. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  | WASILLA-FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVE PRESERV | Wasilla | 2023-10-01 | CFHWY00622 | CFHWY00622 | 1700 | Chris L Bentz | (907)269-0652 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities.
Central Region | ADDLINFO | Repair joints and concrete on hardstands 3 & 4. | Rehabilitate concrete joints and panels. | (3) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 PROJMAN changed.] | ANC RON 3 AND 4 REHABILITATION | Anchorage | 2023-01-01 | CSAPT00754
Central Region | ADDLINFO |  | <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/51221/51221_Plans.pdf">Preliminary Plans (~40 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/51221/51221_CrossSections.pdf">Preliminary Cross Sections (~5 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (3) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2023-02-01 | Z512210000
Central Region | ANTADVDT | 2022-10-01 | 2023-01-01 | (5) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.07.12 ENGEST changed.]; [on 2022.07.12 PROJMAN changed.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2023-01-01 | CFAPT00855
Central Region | ANTADVDT | 2022-10-01 | 2022-11-01 | (3) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 REGION changed.] | Cold Bay Airport Structure Removal | Cold Bay | 2022-11-01 | SFAPT00399
Central Region | ANTADVDT | 2022-10-01 | 2022-11-01 | (3) [on 2022.08.14 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 REGION changed.] | Kodiak Airport Structure Removal | Kodiak | 2022-11-01 | SFAPT00398
Central Region | ANTADVDT | 2022-10-01 | 2022-12-01 | (5) [on 2022.01.18 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.08.14 the ANTADVDT changed to August 2022.]; [on 2022.09.13 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.] | Mchugh RWIS Tower Upgrade | Municipality Of Anchorage | 2022-12-01 | CFHWY00428
Central Region | ANTADVDT | 2022-10-01 | 2022-12-01 | (3) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2022-12-01 | 25RC053613
Central Region | ANTADVDT | 2022-11-01 | 2023-02-01 | (4) [on 2022.03.15 the ANTADVDT changed to June 2022.]; [on 2022.05.16 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to November 2022.] | AMATS: HILAND RD MP 0 TO MP 3.2 PAVEMENT PRESERVATION | Eagle River | 2023-02-01 | CFHWY00568
Central Region | ANTADVDT | 2022-11-01 | 2023-01-01 | (8) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.07.12 DESCRIPTION changed.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 FEDNUM changed.]; [on 2022.10.20 the ANTADVDT changed to November 2022.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2023-01-01 | CFAPT00491
Central Region | ANTADVDT | 2023-01-01 | 2023-02-01 | (8) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2023-02-01 | CSAPT00931
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (10) [on 2022.02.22 the ANTADVDT changed to September 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 ENGEST changed.] | TAKOTNA RIVER BRIDGE REPLACEMENT | Takotna | 2023-03-01 | CFHWY00129
Central Region | ANTADVDT | 2023-02-01 | 2023-03-01 | (8) [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to February 2023.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.04.15 PROJMAN changed.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 ENGEST changed.] | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT | Takotna | 2023-03-01 | Z516210000
Central Region | ANTADVDT | 2023-03-01 | 2023-07-01 | (3) [on 2022.04.15 project was added.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.] | AMATS: EAGLE RIVER LOOP RD - EAGLE RIVER RD TO OLD GLENN HWY | Eagle River | 2023-07-01 | CFHWY00731
Central Region | ANTADVDT | 2023-03-01 | 2023-07-01 | (1) [on 2022.09.13 project was added.] | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | Eagle River | 2023-07-01 | CFHWY00621
Central Region | ANTADVDT | 2023-04-01 | 2023-08-01 | (1) [on 2022.09.13 project was added.] | CHEVAK AIRPORT REHABILITATION | Chevak | 2023-08-01 | Z537250000
Central Region | ANTADVDT | 2023-05-01 | 2023-06-01 | (2) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.] | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | Anchorage | 2023-06-01 | CFAPT00992
Central Region | DESCRIPTION | Rehabilitate the apron surface. Project will include striping. | Rehabilitate the apron surface. Project will include striping and drainage improvements. | (5) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.07.12 ENGEST changed.]; [on 2022.07.12 PROJMAN changed.] | ANC TW K and TL E Apron Rehabilitation | Anchorage | 2023-01-01 | CFAPT00855
Central Region | DESCRIPTION | The project proposes to rehabilitate the runway and runway safety area; remove terrain obstructions; rehabilitate Taxiways A & B; rehabilitate and expand the General Aviation apron; replace airfield lighting and signage; remove Taxiway D; and install a new turnaround taxiway at the east end of the runway. | The project proposes to rehabilitate the runway and runway safety area; remove terrain obstructing the Runway Object Free Area; rehabilitate Taxiways A, B, and a portion of Taxiway D; rehabilitate and expand the General Aviation apron; replace airfield lighting and signage; remove a portion of Taxiway D; and install a new turnaround taxiway at the east end of the runway. | (8) [on 2022.02.22 FEDNUM changed.]; [on 2022.05.16 ADDLINFO changed.]; [on 2022.07.12 the ANTADVDT changed to September 2022.]; [on 2022.07.12 DESCRIPTION changed.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 FEDNUM changed.]; [on 2022.10.20 the ANTADVDT changed to November 2022.] | HOMER AIRPORT IMPROVEMENTS | Homer | 2023-01-01 | CFAPT00491
Central Region | DESCRIPTION | Rehabilitate 3,000 feet of Postmark Drive from West Northern Lights Boulevard to approximately Taxiway Uniform Tug Road intersection. Project includes pavement planning, paving, and striping. | Rehabilitate the pavement on Postmark Drive from West Northern Lights Boulevard to approximately Taxiway Uniform Tug Road intersection. Project includes pavement planning, paving, and striping. | (1) [on 2022.08.14 project was added.] | ANC POSTMARK DRIVE REPAIRS 2023 | Anchorage | 2023-01-01 | CSAPT00984
Central Region | DESCRIPTION | Remove and replace approximately 15,000 feet of liquid joint seal and perform approximately 300 square feet of elastomeric concrete repairs on hardstands RON 3 and 4. | Rehabilitate concrete joints and panels. | (3) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 PROJMAN changed.] | ANC RON 3 AND 4 REHABILITATION | Anchorage | 2023-01-01 | CSAPT00754
Central Region | DESCRIPTION | Rehabilitate 9,600 ft of Aircraft and Lakeshore Dr from Voight Cir to the Lake Hood East property boundary south of runway 14/32. Project includes roadway reconditioning, structural section repairs, drainage improvements, and striping. | Rehabilitate the pavement of Aircraft and Lakeshore Dr from Voight Cir to the Lake Hood East property boundary south of runway 14/32. Project includes roadway reconditioning, structural section repairs, drainage improvements, and striping. | (8) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2023-01-01 | CFAPT00882
Central Region | FEDNUM | 3-02-0435-TBD | 3-02-0435-002-2023 | (5) [on 2022.06.15 project was added.]; [on 2022.07.12 ENGEST changed.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.08.14 ENGEST changed.]; [on 2022.10.20 the ANTADVDT changed to March 2023.] | KWETHLUK AIRPORT REHABILITATION | Kwethluk | 2023-03-01 | CFAPT00682
Central Region | PHONENUM | (907)269-0757 | (907)269-0778 | (1) [on 2022.10.20 project was added.] | Anchorage District Paving | Anchorage | 2023-02-01 | 22-25-1-22
Central Region | PHONENUM | (907)269-0757 | (907)269-0778 | (1) [on 2022.10.20 project was added.] | Mat-Su District Paving | Matanuska-Susitna Borough | 2023-02-01 | 22-25-1-021
Central Region | PROJNAME | ANC RON 3 AND 4 JOINT REPAIRS | ANC RON 3 AND 4 REHABILITATION | (3) [on 2022.03.15 project was added.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 PROJMAN changed.] | ANC RON 3 AND 4 REHABILITATION | Anchorage | 2023-01-01 | CSAPT00754
Marine Highways | (DELETED) |  |  | (7) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.06.15 ENGEST changed.]; [on 2022.06.15 PROJNAME changed.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.08.14 DESCRIPTION changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to November 2022.] | KTN FERRY TERMINAL IMPROVEMENTS PHASE II | Ketchikan | 2022-11-01 | Z674660000 | Z674660000 | 000S855 | Loren K Gehring | (907)465-8189 | The project would replace the ferry vessel fender system along the face of a 120’ long floating platform, install a new gangway and gangway landings, and make electrical and lighting improvements. All work on this project is at the AMHS Berth 3 Ferry Terminal in Ketchikan, Alaska. | Make improvements to AMHS KTN Berth III Ferry terminal: modify the fender system along the 120' float, install new gangway to access the offshore dolphin, make electrical improvements for the facility. | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  | (5) [on 2022.02.22 project was added.]; [on 2022.06.15 ADDLINFO changed.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 LOCATION changed.]; [on 2022.08.14 PROJNAME changed.] | Chena Ridge Road and Chena Pump Road Resurfacing | Fairbanks | 2023-01-01 | NFHWY00570 | NFHWY00570 | 645015 | John J Netardus | (907)451-5448 | Resurface Chena Ridge Road and Chena Pump Road. Project will include bridge work, drainage improvements, embankment stabilization, and roadside hardware. | Single chip seal overlay proposed. | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2022-01-01 | Z768840000 | Z768840000 | 2204 | Jonathan J Hutchinson | (907)451-5479 | SCOPE CHANGE: Construct a road from Kotzebue to Cape Blossom. Project work will include a new bridge over Sadie Creek (#1596), roadside hardware, drainage improvements, and utilities |  | Between $40,000,000 and $50,000,000
Northern Region | ADDED |  |  | (3) [on 2022.06.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the project was removed.] | Old Steese Highway Reconstruction | Fairbanks | 2022-11-01 | Z624870000 | Z624870000 | N/A | Russell M Johnson | (907)451-5059 | Reconstruct the Old Steese Highway between Kutter Road and the Johansen Expressway intersections and rehabilitate the Old Steese Highway between Kutter Road and 3rd Street intersections. Project work includes ADA improvements, drainage improvements, roadside hardware, and utilities. | Project will be advertised as CMGC RFP. Project website: https://dot.alaska.gov/nreg/oldsteese/ | Between $20,000,000 and $30,000,000
Northern Region | ADDED |  |  |  | Purple Heart Trail Signs FY2022 | Statewide | 2023-01-01 | 25RC999999 | 25RC999999 | N/A | Daniel S Adamczak | (907)451-2294 | This project consists of placing signs for the State of Alaska Purple Heart Trail, and to install interpretive waysides to provide further information and to extend the trail to include State traveled waterways. Existing signs will be updated. |  | Between $200,000 and $500,000
Northern Region | ADDED |  |  |  | Cordova - Orca Road Winter Storm Repairs | Cordova | 2023-02-01 | NSHWY00700 | NSHWY00700 | N/A | Daniel S Adamczak | (907)451-2294 | Repair sections of Orca Road in Cordova that were damaged due to the January 2, 2022 winter storm event. Work will include rebuilding and armoring the embankment with rip-rap, and replacing chevron signs. |  | Between $200,000 and $500,000
Northern Region | ADDED |  |  |  | HSIP: RICHARDSON HWY MP 351 INTERCHANGE | North Pole | 2023-09-01 | NFHWY00097 | NFHWY00097 | 0A24034 | David K Fischer | (907)451-5357 | REVISED SCOPE: Reconstruct the Old Richardson Highway and Richardson Highway intersection at MP 351 of the Richardson Highway. Work will include intersection improvements, bridge work, roadside hardware, drainage improvements, and utilities. Additional work includes construction of new frontage roads and reconstruction of a portion of Keeney Road. | Construct an overpass at the Old Richardson Hwy (12 Mile) and relocate the intersection of Old Rich and Richardson Hwy, including realigning access of Keeney Road. | Between $20,000,000 and $30,000,000
Northern Region | ANTADVDT | 2022-11-01 | 2022-12-01 | (1) [on 2022.08.14 project was added.] | Aurora Drive Noyes Slough Bridge #0209 Replacement | Fairbanks | 2022-12-01 | NFHWY00124
Northern Region | ANTADVDT | 2022-12-01 | 2023-01-01 | (3) [on 2022.06.15 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2022.10.20 the ANTADVDT changed to December 2022.] | Edgerton Highway MP 24 - 29 Resurfacing | Mccarthy | 2023-01-01 | NFHWY00587
Northern Region | DESCRIPTION | Replace visual aids at the following airports: Beaver, Birch Creek, Elim, and Koyuk. | Replace visual aid (segmented circle) at the following airport: Elim, Alaska. | (3) [on 2022.02.22 the ANTADVDT changed to December 2022.]; [on 2022.08.14 ENGEST changed.]; [on 2022.10.20 the ANTADVDT changed to February 2023.] | NOR REG VARIOUS AIRPORTS VISUAL AID REPLACEMENT FFY2020 | Regionwide | 2023-02-01 | NFAPT00537
Northern Region | DESCRIPTION | REV 9/4/20: Rehabilitate the rock revetment, helipad surface and the lighting system, and replace the windcone and rotating beacon. | Rehabilitate the rock revetment, helipad surface and the lighting system, and replace the windcone and rotating beacon. | (2) [on 2022.07.12 project was added.]; [on 2022.10.20 ENGEST changed.] | Little Diomede Helipad Improvements | Diomede | 2023-06-01 | Z614700000
Northern Region | FEDNUM | N/A | PENDING | (2) [on 2022.05.16 project was added.]; [on 2022.08.14 the ANTADVDT changed to December 2022.] | Northern Region ADA Improvements - Fairbanks: College Road | Fairbanks | 2022-12-01 | NFHWY00591
Northern Region | FEDNUM | N/A | 3-02-0200-132-2020 | (3) [on 2022.02.22 the ANTADVDT changed to December 2022.]; [on 2022.08.14 ENGEST changed.]; [on 2022.10.20 the ANTADVDT changed to February 2023.] | NOR REG VARIOUS AIRPORTS VISUAL AID REPLACEMENT FFY2020 | Regionwide | 2023-02-01 | NFAPT00537
Northern Region | FEDNUM | N/A | 3-02-0399-___-____ | (2) [on 2022.07.12 project was added.]; [on 2022.10.20 ENGEST changed.] | Little Diomede Helipad Improvements | Diomede | 2023-06-01 | Z614700000
Northern Region | PROJNAME | LITTLE DIOMEDE HELIPAD IMPROVEMENTS | Little Diomede Helipad Improvements | (2) [on 2022.07.12 project was added.]; [on 2022.10.20 ENGEST changed.] | Little Diomede Helipad Improvements | Diomede | 2023-06-01 | Z614700000
Southcoast Region | (DELETED) |  |  | (1) [on 2022.08.14 project was added.] | KTN WOLFE POINT SLOPE STABILITY IMPROVEMENTS | Ketchikan | 2023-01-01 | SFHWY00432 | SFHWY00432 | 920032 | James L Brown | (907)465-1796 | The project will repair unstable slopes from MP 3.0 to MP 3.9 on Tongass Highway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (3) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2023-08-01 | Z686060000 | Z686060000 | 956028 | Gregory K Lockwood | (907)465-2393 | Reconstruction of Haines Highway from Milepost 20 to 25 including the Chilkat River bridge. | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise | Between $30,000,000 and $40,000,000
Southcoast Region | ADDED |  |  |  | Lemon Creek Correctional Center Structural Repairs CM/GC | Juneau | 2022-12-01 | 25C2023065 | 25C2023065 | N/A | Jesse Campbell | (907)266-2723 | This State funded project will provide structural repairs, drainage improvements, interior renovations, and ancillary systems upgrades at the Lemon Creek Correctional Center in Juneau, AK. An optional second phase to provide a new maximum security housing module may be included if funding becomes available. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  | NECK LAKE ROAD RECONSTRUCTION SEGMENT 2 WFLHD | Prince Of Wales Island | 2023-02-01 | SFHWY00375 | SFHWY00375 | AK PFH 58(2) | Gregory K Lockwood | (907)465-2393 | This project is to provide funding for state support and review of Neck Lake Road Segment 2 design developed under FHWA, Western Federal Lands Highway Division. | Phase 1 of Neck Lake Road Reconstruction will consist of approximately 3.96 miles of road reconstruction on Neck Lake Road beginning at the intersection of NPOWI Highway. The project will be advertised by Western Federal Lands.
Southcoast Region | ADDED |  |  | (5) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2023-09-01 | SFAPT00227 | SFAPT00227 | N/A | David A Pyeatt | (907)465-4490 | ADQ airport ARFF Access improvements and Rehabilitation of Taxiway C, D and F. Project includes the non-private portion of the Apron. | PFAS Investigation may cause delay depending on results and how to manage waste material | Between $50,000,000 and $60,000,000
Southcoast Region | ADDED |  |  | (2) [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.] | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | Kodiak | 2023-10-01 | SFHWY00260 | SFHWY00260 | 3247 | Bran P Pollard | (907)465-4526 | Resurface Rezanoff Drive from Marine Way to the airport. Associated preventative maintenance activities may include minor structural section improvements, drainage repairs, lighting and signals, striping, signs, and ADA improvements. Project Location and Length: Rezanoff Drive from Marine Way to the airport for an approximate length of 4.70 miles. | (Design by Northern Region)
Southcoast Region | ADDED |  |  | (2) [on 2022.02.22 project was added.]; [on 2022.04.15 the project was removed.] | SIT AIRPORT UTILITY IMPROVEMENT | Sitka | 2023-10-01 | SFAPT00371 | SFAPT00371 | N/A | Bran P Pollard | (907)465-4526 | Replace and relocate the water and sewer lines serving the Sitka Rocky Gutierrez Airport and along airport road where infrastructure serves lease lots. The water and sewer lines have reached their useful life and are at failure. | Construction funding uncertain.
Southcoast Region | ANTADVDT | 2022-10-01 | 2022-11-01 | (2) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2022-11-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2022-10-01 | 2022-11-01 | (6) [on 2022.04.15 project was added.]; [on 2022.07.12 ADDLINFO changed.]; [on 2022.07.12 PROJNAME changed.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.10.20 ENGEST changed.] | SGY DYEA ROAD 00049 - DEC 20 SE PR | Skagway | 2022-11-01 | SDRER00410
Southcoast Region | ANTADVDT | 2023-04-01 | 2023-05-01 | (7) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2023-05-01 | Z680850000
Southcoast Region | ANTADVDT | 2023-07-01 | 2023-08-01 | (10) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2023-08-01 | SFHWY00359
Southcoast Region | ANTADVDT | 2023-08-01 | 2023-05-01 | (2) [on 2022.09.13 project was added.]; [on 2022.10.20 ENGEST changed.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2023-05-01 | SFHWY00326