## 2024.09.17 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (1) [on 2024.05.16 project was added.] | TUNUNAK AIRPORT REHABILITATION | Tununak | 2025-04-01 | CFAPT00854 | CFAPT00854 | 3-02-0486-003-2024 | Kim D Satterfield | (907)269-0623 | This project proposes to rehabilitate and resurface the operational surfaces at the Tununak Airport to correct cracks, ruts, uneven surfaces, dips (over 6"), soft spots, and ponding. Dust palliative will be applied for fines preservation to bind aggregate and prevent loss of fines. Drainage improvements may include special ditching and culvert realignment where needed. Lighting and visual aids will be repaired or replaced where they have been damaged or displaced by subsidence. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (1) [on 2024.08.15 the ANTADVDT changed to August 2024.] | (4) [on 2023.11.15 project was added.]; [on 2024.06.19 DESCRIPTION changed.]; [on 2024.06.19 FEDNUM changed.]; [on 2024.08.15 the ANTADVDT changed to August 2024.] | CHENEGA BAY AIRPORT LIGHTING IMPROVEMENTS | Chenega Bay | 2024-08-01 | CFAPT01021 | CFAPT01021 | 3-02-0419-006-2024 | Kim D Satterfield | (907)269-0623 | Replace runway and taxiway lighting systems, the segmented circle and lighted primary wind cone, the rotating beacon, and the lighted supplemental wind cone. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.08.15 project was added.] | WASILLA-FISHHOOK - MAIN STREET REHABILITATION | Wasilla | 2025-02-01 | Z600770000 | Z600770000 | 1408 | Clint J Adler | (907)707-1911 | Construct a one-way couplet in downtown Wasilla bounded by Bogard Road, KGB/Main Street, Yenlo/Talkeetna Street and the Palmer Wasilla Highway. The exact location of the couplet will be determined during the environmental and preliminary design phase. Improvements to Bogard Road will be necessary to make the couplet functional. Work will consist of new road construction, lane reconfigurations, signals, new pavement, signing and striping, and sidewalks. |  | Between $40,000,000 and $50,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.02.14 project was added.] | OLD GLENN HWY OUTER SPRINGER LP & INNER SPRINGER LP PAVEMENT | Palmer | 2025-01-01 | CFHWY00887 | CFHWY00887 | 1748 | Kristina H Busch | (907)269-0567 | This pavement preservation project will resurface Old Glenn Hwy, Outer Springer Loop and Inner Springer Loop. Additional improvements may also include: utility relocation, roadsidehardward, vegetation clearing, dig-outs, drainage, signs, striping, bridge repairs, ADA improvements, and safety improvements. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  |  | (5) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2023.06.15 the project was removed.]; [on 2024.06.19 project was added.] | SEWARD AIRPORT IMPROVEMENTS | Seward | 2025-05-01 | Z548570000 | Z548570000 | N/A | Joy A Vaughn | None | Shift, raise and reconstruct R/W 16/34. Construct Armor protection. Rehabilitate aprons, replace airport lighting, and construct pads for NAVAIDS. Close R/W 13/31, Taxiways A, D, and E. Miscellaneous fencing, signing, etc... |  | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  | (2) [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to November 2024.] | (7) [on 2024.04.15 project was added.]; [on 2024.05.16 ADDLINFO changed.]; [on 2024.05.16 DESCRIPTION changed.]; [on 2024.05.16 ENGEST changed.]; [on 2024.05.16 PROJNAME changed.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to November 2024.] | Nenana Station Shop Roof Improvements | Nenana | 2024-11-01 | 2501000065A | 2501000065A | N/A | Lauren A Staft | (907)451-5424 | Perform structural upgrades and replace Nenana DOT Maintenance Station shop roof. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (4) [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | (5) [on 2023.11.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | ANC FIRING RANGE MAINTENANCE | Anchorage | 2024-09-01 | CSAPT01152 | CSAPT01152 | N/A | Jennifer M Lombardo | (907)266-2731 | Perform deferred maintenance on the active firing/shooting range at ANC by removing lead bullets and bullet fragments. Amend remaining affected soil with a heavy metal fixation reagent to prevent leaching of lead. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  |  | VICTORY ROAD PAVEMENT PRESERVATION | Chickaloon | 2025-04-01 | CFHWY00672 | CFHWY00672 | 1726 | Kristina H Busch | (907)269-0567 | This pavement preservation project will resurface Victory Road. Additional improvements may also include: utility relocation, roadside hardware, vegetation clearing, dig-outs, drainage, signs, and striping. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  | (4) [on 2023.07.14 project was added.]; [on 2023.08.21 the project was removed.]; [on 2024.07.24 project was added.]; [on 2024.08.15 the project was removed.] | GLENN HIGHWAY: AIRPORT HEIGHTS TO PARK HIGHWAY REHAB | Anchorage | 2025-08-01 | CFHWY00545 | CFHWY00545 | 1656 | Chris L Bentz | (907)707-1912 | This project will rehabilitate the Glenn Highway from the intersection with Airport Heights ( MP 0.0) to the Parks Highway Interchange ( MP 33.0). The project may include Bridge work, roadside hardware, drainage Improvements, interchange improvements, ADA improvements, utilities and safety improvements. | Project likely to be phased for construction. | Greater than $100,000,000
Central Region | ADDED |  |  | (1) [on 2023.07.14 the ANTADVDT changed to April 2024.] | (6) [on 2022.05.16 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to April 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 the project was removed.] | HSIP: 5TH AVE: CONCRETE ST TO KARLUK ST PEDESTRIAN IMPROVMNT | Anchorage | 2025-08-01 | CFHWY00856 | CFHWY00856 | 421102 | Noah C King | (907)269-0657 | This HSIP project will construct a median barrier on 5th Avenue between Concrete Street and the couplet of 5th and 6th Avenues (Karluk Street). Work may include roadside hardware, drainage, improvements, and utilities. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | HSIP: TUDOR RD: BAXTER RD TO PATTERSON ST CHANNELIZATION | Anchorage | 2025-08-01 | CFHWY01073 | CFHWY01073 | 544023 | Rori A Van Nortwick | (907)269-0587 | Install a non-traversable median and roadside barriers on Tudor Road between Baxter Road and Patterson Street. The proposed median targets head-on and access-related crashes by providing physical separation between vehicles, identifying specific left turn locations, and promoting through trips. This median may be raised concrete curb, concrete barrier, or a combination of both median types. |  | Pending
Central Region | ADDED |  |  |  | (2) [on 2022.08.14 project was added.]; [on 2023.06.15 the project was removed.] | KWIGILLINGOK AIRPORT IMPROVEMENTS | Kwigillingok | 2025-08-01 | Z525710000 | Z525710000 | N/A | Steven J Rzepka | (907)269-0619 | Reconstruct and extend Kwigillingok Airport to community class standards. Will acquire ROW, improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building(s). | Reconstruct and extend Kwigillingok Airport to community class standards. Improve safety, upgrade runway & taxiway, install runway and taxiway lighting, construct a new apron that meets design setbacks, and construct a new snow removal equipment building. Actual Advertising Date contingent upon federal funding availability. Check back often for updates. | Pending
Central Region | ADDED |  |  |  |  | MAT-SU AREA REPAIRS GROUP B - NOV 2018 EQ PERMANENT REPAIRS | Matanuska-Susitna Borough | 2025-08-01 | CFHWY00706 | CFHWY00706 | 92012 | Steven J Rzepka | (907)269-0619 | This project will construct repairs for the November 2018 earthquake in the Central Region of Alaska for DDIRs AK 2019 02 041, AK 2019 02 070 and AK 2019 02 102. Repairs may include, but are not limited to, asphalt, embankment, bridge, roadside hardware, retaining walls, utilities, and drainage. |  | Pending
Central Region | ADDED |  |  |  |  | BIG LAKE RD: MP 0-3.6 AND CHURCH RD PAVEMENT PRESERVATION | Big Lake | 2025-02-01 | CFHWY00906 | CFHWY00906 | 511009 | Kristina H Busch | (907)269-0567 | Resurface Big Lake Road from the Parks Highway (MP 0.0) to North Shore Drive (MP 3.6) and its adjacent shared-use pathway near Big Lake, AK as well as resurface Church Road from the Parks Highway to Schrock Road and its adjacent shared-use pathway in Wasilla, AK. The pathway adjacent to Church Road extends from the Parks Highway to Spruce Avenue. The proposed project work includes pavement resurfacing of the roadways and adjacent shared-use pathways, structural dig-outs, striping, roadside hardware improvements, drainage improvements, vegetation clearing and grubbing, utilities relocations, and ADA curb ramps. |  | Between $20,000,000 and $30,000,000
Central Region | ADDED |  |  |  |  | SEWARD HIGHWAY MP 14 RAILROAD CROSSING RECONSTRUCTION | Seward | 2025-07-01 | CFHWY00947 | CFHWY00947 | 311037 | Rori A Van Nortwick | (907)269-0587 | Project will reconstruct Seward Highway MP 14 Railroad Crossing (#4054) to accommodate ARRC's project to raise railroad grade. Work will also include drainage improvements, roadside hardware, and utilities as needed. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | STERLING HWY: MP 169 TO 175 PAVEMENT PRESERVATION | Sterling | 2025-07-01 | CFHWY00857 | CFHWY00857 | 211066 | Julia R Hanson | (907)269-0753 | This is a pavement preservation project for Sterling Highway from Homer Hill to Kachemak Bay Drive. This project includes resurfacing, roadside hardware, drainage improvements, ADA improvements, and utilities as necessary. |  | Pending
Central Region | ADDED |  |  |  |  | KACHEMAK DRIVE MP 0-3.5 PAVEMENT PRESERVATION | Homer | 2025-06-01 | CFHWY00602 | CFHWY00602 | 1701 | Steven J Rzepka | (907)269-0619 | Resurface Kachemak Drive from Sterling Highway to East End Road. This project will include: Pavement Preservation Roadside Hardware, Drainage improvements, Intersection improvements, ADA improvements (to include curb ramps) and Utilities. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | TAKOTNA RIVER BRIDGE REPLACEMENT - REBID | Takotna | 2025-06-01 | CFHWY00129-A | CFHWY00129-A | 1569 | Ryan R Hammel | (907)269-0571 | This Project replaces the Takotna River Bridge (bridge #0463). Project includes bridge work, roadway resurfacing, roadside hardware, drainage improvements, and utilities. | Replacement of the Takotna River Bridge (bridge #0463). May include bridge work, roadside hardware, drainage improvements, and utilities. Project will advertise with Z516210000 Takotna: Gold Creek Bridge & Tatalina Bridge Replacement. <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00129_51621/00129_Plans.pdf">Preliminary Plans (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
Central Region | ADDED |  |  |  |  | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT - REBID | Takotna | 2025-06-01 | Z516210000-A | Z516210000-A | 000S783 | Ryan R Hammel | (907)269-0571 | The Alaska Department of Transportation and Public Facilities (DOT&PF) in cooperation with the Federal Highway Administration (FHWA) proposes to replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge #462. | Replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge. Will advertise with CFHWY00129 Takotna River Bridge Replacement. <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00129_51621/51621_Plans.pdf">Preliminary Plans (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | Juneau state office building North Parking Garage Restoration/Renovation | Central Region | 2024-11-01 | SPFAC00429 | SPFAC00429 | N/A | Levi D Overbeck | (907)720-3787 | Project to address structural and functional issues within the JSOB north parking garage. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | Juneau Second St & Gold St Parking Garage Repairs | Central Region | 2024-09-01 | SPFAC00540 | SPFAC00540 | N/A | Levi D Overbeck | (907)720-3787 | Rehabilitate the Parking Garage at Second St and Gold St. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | Old Glenn Highway Brush Cutting | Matanuska-Susitna Borough | 2024-09-01 | 24-25-1-011 | 24-25-1-011 | N/A | Vernon S Vreeland | (907)269-0778 | This contract shall provide for all materials, equipment, supervision, labor, maintenance, fuel, mobilization, and demobilization necessary to clear brush within the DOT&PF right of way along the Old Glenn Highway within the Matanuska-Susitna Maintenance District. |  | Between $500,000 and $1,000,000
Central Region | ANTADVDT | 2025-04-01 | 2024-11-01 | (1) [on 2024.08.15 the ANTADVDT changed to April 2025.] | (3) [on 2023.11.15 project was added.]; [on 2024.08.15 the ANTADVDT changed to April 2025.]; [on 2024.08.15 ENGEST changed.] | AMATS: VFW ROAD - EAGLE RIVER LP TO EAGLE RIVER RD PP | Eagle River | 2024-11-01 | CFHWY00732
Central Region | ANTADVDT | 2024-08-01 | 2024-11-01 | (8) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.] | (11) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.02.14 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.] | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | Anchorage | 2024-11-01 | CFAPT00930
Central Region | ANTADVDT | 2024-08-01 | 2024-10-01 |  | (1) [on 2024.08.15 project was added.] | Seward Highway MP 98.5 – 118 Signage Project | Anchorage | 2024-10-01 | CSHWY01203
Central Region | ANTADVDT | 2025-01-01 | 2025-04-01 |  | (5) [on 2022.05.16 project was added.]; [on 2022.07.12 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.02.14 project was added.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2025-04-01 | CFHWY00394
Central Region | ANTADVDT | 2025-01-01 | 2025-07-01 |  | (1) [on 2024.05.16 project was added.] | PALMER-FISHHOOK ROAD MILEPOSTS 7-17 | Matanuska-Susitna Borough | 2025-07-01 | CFHWY00405
Central Region | ANTADVDT | 2025-03-01 | 2025-06-01 |  | (1) [on 2024.04.15 project was added.] | TAKOTNA AIRPORT REHABILITATION | Central | 2025-06-01 | CFAPT00805
Central Region | ANTADVDT | 2024-11-01 | 2025-01-01 |  | (1) [on 2024.06.19 project was added.] | STERLING HWY: MP 157-169 RECON - PHASE I | Kenai Peninsula | 2025-01-01 | CFHWY01210
Central Region | ANTADVDT | 2024-10-01 | 2024-12-01 | (6) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.]; [on 2024.07.24 the ANTADVDT changed to October 2024.] | (12) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.]; [on 2023.07.14 the project was removed.]; [on 2024.04.15 project was added.]; [on 2024.07.24 the ANTADVDT changed to October 2024.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2024-12-01 | CFHWY00253
Central Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (14) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | (21) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | Anchorage | 2024-10-01 | CSAPT00931
Central Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $2,500,000 and $5,000,000 | (1) [on 2024.08.15 the ANTADVDT changed to April 2025.] | (3) [on 2023.11.15 project was added.]; [on 2024.08.15 the ANTADVDT changed to April 2025.]; [on 2024.08.15 ENGEST changed.] | AMATS: VFW ROAD - EAGLE RIVER LP TO EAGLE RIVER RD PP | Eagle River | 2024-11-01 | CFHWY00732
Central Region | FEDNUM | 3-02-0195-002-2024 | 3-02-0195-003-2024 | (3) [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to October 2024.] | (9) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.11.15 ENGEST changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to October 2024.]; [on 2024.07.24 FEDNUM changed.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-10-01 | CFAPT00572
Central Region | PHONENUM | (907)269-0592 | (907)269-0619 |  | (1) [on 2024.05.16 project was added.] | ANCHOR POINT ROAD MP 0-1.3 PAVEMENT PRESERVATION | Anchor Point | 2025-04-01 | CFHWY00601
Central Region | PHONENUM | (907)269-0592 | (907)269-0619 | (1) [on 2024.08.15 the ANTADVDT changed to February 2025.] | (2) [on 2024.05.16 project was added.]; [on 2024.08.15 the ANTADVDT changed to February 2025.] | PETERS CREEK BRIDGE (1367) EMERGENCY REPAIRS | Peters Creek | 2025-02-01 | CDRER01160
Central Region | PHONENUM | (907)269-0567 | (907)707-1922 |  | (5) [on 2022.05.16 project was added.]; [on 2022.07.12 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.02.14 project was added.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2025-04-01 | CFHWY00394
Central Region | PROJMAN | Kristina H Busch | Jacob A Dilley |  | (5) [on 2022.05.16 project was added.]; [on 2022.07.12 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.02.14 project was added.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2025-04-01 | CFHWY00394
Marine Highways | (DELETED) |  |  |  | (2) [on 2024.04.15 project was added.]; [on 2024.08.15 PHONENUM changed.] | M/V Columbia CPP System Replacement | Statewide | 2024-03-01 | SAMHS00147_C | SAMHS00147_C | 9500143 | Troy J Sherrill | None | The scope of work for this federally funded contract includes the installation of a new Owner-Furnished Controlled Pitch Propeller (CPP) System on the M/V Columbia, including Alarm and Monitoring systems installation, Fire Detection system, testing, and demonstration of acceptable operation to regulatory agencies and the owner. Work includes necessary remediation of contaminated materials, limited engineering, documentation, and State funded annual overhaul work as outlined in the plans and specifications. |  | Pending
Northern Region | (DELETED) |  |  | (3) [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.] | (4) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.] | Glenn/Richardson Highway Right of Way Reconciliation | Glennallen | 2024-08-01 | HSHWY00018 | HSHWY00018 | N/A | Carl F Heim | (907)451-5359 | Reconcile right of way and encroachment conflicts along the Glenn and Richardson Highways near Glennallen Alaska, to allow for completion of future federal projects. This work may include right of way research, appraisals, purchases and other activities necessary to eliminate conflicts. Completion of a highway wayside as part of the conflict elimination will also be included as part of this effort. |  | Between $500,000 and $1,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2024.08.15 project was added.] | Northern Region Preservation Maintenance FFY2024 | Yukon River | 2024-08-01 | NFAPT0094A | NFAPT0094A | N/A | Daniel A Phillips | (907)451-2926 | Complete surface preservation maintenance work at the following airports: Allakaket, Fort Yukon, Huslia, Nulato, and Tanana |  | Pending
Northern Region | (DELETED) |  |  | (4) [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | (13) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.09.15 the project was removed.]; [on 2024.01.16 project was added.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2025-01-01 | Z631860000 | Z631860000 | 713010 | Russell M Johnson | (907)451-5059 | Reconstruct the Richardson Highway between MP 167 and 173. Project includes roadside hardware, drainage improvements and utility relocations. | Reconstruct the Richardson Highway between mileposts 167-173. | Between $30,000,000 and $40,000,000
Northern Region | (DELETED) |  |  | (2) [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | (3) [on 2024.04.15 project was added.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | City of Fairbanks Systemic Signal Upgrades - Stage 1 (HSIP) | Fairbanks | 2024-09-01 | NFHWY00905 | NFHWY00905 | N/A | Ethan E Graetz | (907)451-2281 | Reconstruct eleven signalized intersections at multiple locations in the City of Fairbanks. Work includes intersection improvements and roadside hardware. | This project will advertise with NFHWY00904. | Less than $200,000
Northern Region | (DELETED) |  |  | (2) [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | (3) [on 2024.04.15 project was added.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | Northern Region Systemic Signal Upgrades - Stage 1 (HSIP) | Regionwide | 2024-09-01 | NFHWY00904 | NFHWY00904 | N/A | Ethan E Graetz | (907)451-2281 | Reconstruct seven signalized intersections at multiple locations in the Fairbanks and Parks Highway Nenana Canyon area. Work includes intersection improvements and roadside hardware. | This project will advertise with NFHWY00905. | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  |  | Northern Region ADA Improvements - Nome: Steadman Street | Nome | 2025-04-01 | NFHWY00505 | NFHWY00505 | 0002(444) | Ivet Hall | (907)451-5386 | The proposed project consist of replacing the sidewalk, curb ramps, approaches and curb and gutters with ADA compliant features along a segment of Steadman Street in Nome, AK. In order to replace the sidewalks, the project will reconstruct the roadway to address the embankment settlement issues and improve drainage. |  | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  |  | ODIAK SLOUGH CULVERT REPLACEMENT | Cordova | 2025-07-01 | NFHWY00737 | NFHWY00737 | N/A | John J Netardus | (907)451-5448 | Replace deep culvert at Odiak Slough near Milepost 1.3 on the Copper River Highway in Cordova. Project work includes pavement preservation, roadside hardware, drainage improvements, ADA improvements and utilities. |  | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  |  | FAST AREA SURFACE UPGRADES FFY2025 | Fairbanks North Star Borough | 2025-03-01 | NFHWY00913 | NFHWY00913 | N/A | John J Netardus | (907)451-5448 | Perform pavement resurfacing, replace pavement markings, replace sidewalk curb with Americans with Disabilities Act (ADA) compliant curb ramps at street corners, improve sidewalks and pedestiran facilities, improve intersections, and install cross culverts on various streets and sidewalks in Fairbanks and North Pole. |  | Pending
Northern Region | ADDED |  |  |  |  | COPPER RIVER HIGHWAY MP 2.4 DRAINAGE IMPROVEMENTS | Cordova | 2025-05-01 | NFHWY00984 | NFHWY00984 | N/A | David K Fischer | (907)451-5357 | Copper River Highway MP 2.4 drainage improvements work also includes roadside hardware and utilities. |  | Pending
Northern Region | ADDLINFO | 2-year construction, 2025-2026 | 2-year construction, 2026-2027 | (2) [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to October 2024.] | (7) [on 2023.08.21 project was added.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 PROJNAME changed.]; [on 2024.06.19 ADDLINFO changed.]; [on 2024.06.19 the ANTADVDT changed to October 2024.]; [on 2024.08.15 PROJNAME changed.] | Pearl Creek Elementary School Access Improvements and Plug-ins (CMAQ) | Fairbanks | 2025-07-01 | NFHWY00712
Northern Region | ANTADVDT | 2024-10-01 | 2025-07-01 | (2) [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to October 2024.] | (7) [on 2023.08.21 project was added.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 PROJNAME changed.]; [on 2024.06.19 ADDLINFO changed.]; [on 2024.06.19 the ANTADVDT changed to October 2024.]; [on 2024.08.15 PROJNAME changed.] | Pearl Creek Elementary School Access Improvements and Plug-ins (CMAQ) | Fairbanks | 2025-07-01 | NFHWY00712
Northern Region | ANTADVDT | 2024-10-01 | 2024-11-01 | (1) [on 2024.02.14 the ANTADVDT changed to October 2024.] | (3) [on 2023.07.14 project was added.]; [on 2023.09.15 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to October 2024.] | Ruby Slough Road Rehabilitation | Ruby | 2024-11-01 | NFHWY00630
Northern Region | ENGEST | Pending | Between $5,000,000 and $10,000,000 |  | (1) [on 2024.04.15 project was added.] | HSIP: CHENA SMALL TRACTS ROUNDABOUT | Fairbanks North Star Borough | 2025-03-01 | NFHWY00699
Southcoast Region | (DELETED) |  |  | (9) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.] | (22) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 DESCRIPTION changed.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-08-01 | SFHWY00359 | SFHWY00359 | 3267 | Brett M Wells | (907)465-1607 | The work includes excavation, grading, chip seal, culvert replacement, seeding, rock armoring, and stream channel restoration. |  | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  |  | (2) [on 2024.01.16 project was added.]; [on 2024.04.15 ENGEST changed.] | KOKHANOK AIRPORT RESURFACING AND FENCING | Kokhanok | 2024-12-01 | SFAPT00361 | SFAPT00361 | N/A | David B Epstein | (907)465-4483 | Resurfacing and grading the runway, regrading ditches and safety areas, replacement of inoperative culverts and drainage repairs. Installation of new AWOS. CC 24300447 LC 33008462 Phase: T02FA1 LC & CC Description: SFAPT00361-2P-Resurf. |  | Between $10,000,000 and $20,000,000
Southcoast Region | ADDED |  |  |  |  | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-12-01 | SFHWY00440-HNS001 | SFHWY00440-HNS001 | 93006 | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS00l, AK 2021 01 HNS002, AK 2021 01 HNS003, and AK 2021 01 HNS004. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway. |  | Between $200,000 and $500,000
Southcoast Region | ADDLINFO |  | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS001 - HNS004. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway between Milepost (MP) 1 - 9. This project is funded by FHWA. | (4) [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.] | (6) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2025-01-01 | SFHWY00440
Southcoast Region | ADDLINFO |  | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS006 - HNS008 & HNS010 - HNS011. Repairs may include, but are not limited to asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway & Lutak Road. | (6) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | (9) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 FEDNUM changed.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2025-04-01 | SFHWY00446
Southcoast Region | ADDLINFO |  | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK 2021 01 JNS002, and JNS004 - JNS006. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Glacier Highway/Lemon Road, Egan Drive/Glacier Highway, and Glacier Highway/Twin Lakes Drive. This project is funded by FHWA. | (5) [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | (9) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2025-03-01 | SFHWY00438
Southcoast Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (6) [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.] | (13) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 ADDLINFO changed.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-09-01 | Z686060000
Southcoast Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (11) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.] | (17) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-09-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (5) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.] | (12) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.]; [on 2024.05.16 ENGEST changed.]; [on 2024.08.15 PHONENUM changed.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-09-01 | SFHWY00070
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-01-01 | (4) [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.] | (6) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2025-01-01 | SFHWY00440
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-03-01 | (5) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.] | (8) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.]; [on 2024.07.24 DESCRIPTION changed.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2025-03-01 | SFHWY00481
Southcoast Region | ANTADVDT | 2025-01-01 | 2025-03-01 | (7) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | (9) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2025-03-01 | SDRER00436
Southcoast Region | ANTADVDT | 2025-01-01 | 2025-04-01 | (6) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | (9) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 FEDNUM changed.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2025-04-01 | SFHWY00446
Southcoast Region | ANTADVDT | 2025-01-01 | 2025-04-01 | (5) [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.08.15 the ANTADVDT changed to January 2025.] | (6) [on 2023.06.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.08.15 the ANTADVDT changed to January 2025.] | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2025-04-01 | SDRER00445
Southcoast Region | ANTADVDT | 2025-01-01 | 2025-03-01 | (5) [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | (9) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2025-03-01 | SFHWY00438
Southcoast Region | ANTADVDT | 2025-05-01 | 2025-08-01 |  | (1) [on 2024.06.19 project was added.] | HSIP: JNU VANDERBILT CONTINUOUS GREEN T | Juneau | 2025-08-01 | SFHWY00524
Southcoast Region | ANTADVDT | 2024-10-01 | 2025-01-01 | (9) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to October 2024.] | (14) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to October 2024.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2025-01-01 | SFHWY00103
Southcoast Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (3) [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | (5) [on 2023.10.25 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.06.19 DESCRIPTION changed.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | Ketchikan | 2024-10-01 | SFHWY00536
Southcoast Region | DESCRIPTION | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS005, AK 2021 01 HNS006, AK 2021 01 HNS007, AK 2021 01 HNS008, AK 2021 01 HNS009, AK 2021 01 HNS010, AK 2021 01 HNS011, and AK 2021 01 HNS012. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway & Lutak Road. | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS005, AK 2021 01 HNS006, AK 2021 01 HNS007, AK 2021 01 HNS008, AK 2021 01 HNS009, AK 2021 01 HNS010, AK 2021 01 HNS011, and AK 2021 01 HNS012. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway & Lutak Road. | (6) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | (9) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 FEDNUM changed.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2025-04-01 | SFHWY00446
Southcoast Region | DESCRIPTION | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | (6) [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.02.14 the ANTADVDT changed to July 2024.]; [on 2024.04.15 the ANTADVDT changed to September 2024.]; [on 2024.07.24 the ANTADVDT changed to October 2024.]; [on 2024.08.15 the ANTADVDT changed to June 2025.] | (19) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to July 2024.]; [on 2024.04.15 the ANTADVDT changed to September 2024.]; [on 2024.07.24 the ANTADVDT changed to October 2024.]; [on 2024.08.15 the ANTADVDT changed to June 2025.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2025-06-01 | SFAPT00178
Southcoast Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $2,500,000 and $5,000,000 | (5) [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.08.15 the ANTADVDT changed to January 2025.] | (6) [on 2023.06.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.08.15 the ANTADVDT changed to January 2025.] | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2025-04-01 | SDRER00445
Southcoast Region | PHONENUM | None | (907)465-1215 | (5) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.] | (12) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.]; [on 2024.05.16 ENGEST changed.]; [on 2024.08.15 PHONENUM changed.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-09-01 | SFHWY00070