## 2024.10.14 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (5) [on 2023.07.14 project was added.]; [on 2023.08.21 the project was removed.]; [on 2024.07.24 project was added.]; [on 2024.08.15 the project was removed.]; [on 2024.09.17 project was added.] | GLENN HIGHWAY: AIRPORT HEIGHTS TO PARK HIGHWAY REHAB | Anchorage | 2025-08-01 | CFHWY00545 | CFHWY00545 | 1656 | Chris L Bentz | (907)707-1912 | This project will rehabilitate the Glenn Highway from the intersection with Airport Heights ( MP 0.0) to the Parks Highway Interchange ( MP 33.0). The project may include Bridge work, roadside hardware, drainage Improvements, interchange improvements, ADA improvements, utilities and safety improvements. | Project likely to be phased for construction. | Greater than $100,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.05.16 project was added.] | ANC GATES N2 &N4 REHABILITATION | Anchorage | 2025-01-01 | CFAPT01205 | CFAPT01205 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate and extend the life of the aprons at Gates N2 and N4 to include joint seal replacement and concrete rehabilitation |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  |  | (5) [on 2022.03.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.08.14 project was added.]; [on 2023.06.15 the project was removed.]; [on 2024.08.15 project was added.] | ANC TAXIWAY Z IMPROVEMENTS EAST | Anchorage | 2025-07-01 | CFAPT00835 | CFAPT00835 | N/A | Philip W Cheasebro | (907)269-0606 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron. |  | Pending
Central Region | (DELETED) |  |  |  | (7) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.09.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.07.24 project was added.] | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2025-06-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Noah C King | (907)269-0657 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards. |  | Pending
Central Region | (DELETED) |  |  |  | (10) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.09.15 ENGEST changed.]; [on 2023.09.15 PHONENUM changed.]; [on 2023.09.15 PROJMAN changed.]; [on 2023.10.25 the project was removed.]; [on 2024.07.24 project was added.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2025-06-01 | CFHWY00503 | CFHWY00503 | 1644 | Noah C King | (907)269-0657 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.06.19 project was added.] | AMATS: FISH CREEK TRAIL CONNECTION | Anchorage | 2025-05-01 | CFHWY00587 | CFHWY00587 | 1696 | Noah C King | (907)269-0657 | This project will construct a multi-use path between Northern Lights Boulevard and the Tony Knowles Coastal Trail in the vicinity of Fish Creek. Work may include roadside hardware, ADA improvements, utilities, lighting, bridge work, and drainage improvements. |  | Pending
Central Region | (DELETED) |  |  |  | (1) [on 2024.06.19 project was added.] | HSIP: VINE RD AT HOLLYWOOD INTERSECTION IMPROVEMENTS | Wasilla | 2025-05-01 | CFHWY00463 | CFHWY00463 | 1627 | Alex L Read | (907)269-0641 | Project will construct either a single lane roundabout or a traffic signal to mitigate crashes at the intersection of Vine and Hollywood. Project is included in the HSIP program. |  | Pending
Central Region | (DELETED) |  |  | (1) [on 2024.09.17 the ANTADVDT changed to October 2024.] | (2) [on 2024.08.15 project was added.]; [on 2024.09.17 the ANTADVDT changed to October 2024.] | Seward Highway MP 98.5 – 118 Signage Project | Anchorage | 2024-10-01 | CSHWY01203 | CSHWY01203 | N/A | Sean M Baski | (907)269-0566 | This project will replace existing signs that do not meet ATM standards, install signs in advance of pullouts and recreation sites, and install additional mile points to help with wayfinding and reduce crashes. |  | Pending
Central Region | (DELETED) |  |  | (2) [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | (6) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | Wasilla | 2024-09-01 | CFHWY00723 | CFHWY00723 | 1703 | Chris L Bentz | (907)707-1912 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.09.17 project was added.] | Old Glenn Highway Brush Cutting | Matanuska-Susitna Borough | 2024-09-01 | 24-25-1-011 | 24-25-1-011 | N/A | Vernon S Vreeland | (907)269-0778 | This contract shall provide for all materials, equipment, supervision, labor, maintenance, fuel, mobilization, and demobilization necessary to clear brush within the DOT&PF right of way along the Old Glenn Highway within the Matanuska-Susitna Maintenance District. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | AMATS: 88TH AVE: LAKE OTIS PKWY- ABBOTT RD PAVE PRESERVATION | Anchorage | 2025-04-01 | CFHWY00752 | CFHWY00752 | 1751 | Julia R Hanson | (907)269-0753 | Plan, design, and construct 88th Avenue, generally from Lake Otis Parkway to Abbott Road. Project will resurface and re-stripe the existing roadway, and upgrade curb ramps in accordance with the Americans With Disabilities Act (ADA). The project may also include structural section improvements, minor upgrades to signal, lighting, and/or traffic recording equipment, utility relocations or adjustments. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  | (2) [on 2024.08.15 project was added.]; [on 2024.09.17 the project was removed.] | WASILLA-FISHHOOK - MAIN STREET REHABILITATION | Wasilla | 2025-08-01 | Z600770000 | Z600770000 | 1408 | Clint J Adler | (907)707-1911 | Construct a one-way couplet in downtown Wasilla bounded by Bogard Road, KGB/Main Street, Yenlo/Talkeetna Street and the Palmer Wasilla Highway. The exact location of the couplet will be determined during the environmental and preliminary design phase. Improvements to Bogard Road will be necessary to make the couplet functional. Work will consist of new road construction, lane reconfigurations, signals, new pavement, signing and striping, and sidewalks. |  | Between $40,000,000 and $50,000,000
Central Region | ADDED |  |  |  |  | ANC Runway 7R Concrete Keel Joint Repairs | Anchorage | 2025-02-01 | CSAPT01267 | CSAPT01267 | N/A | Jennifer M Lombardo | (907)266-2731 | Remove and replace joint sealant and perform concrete repairs on Runway 7R concrete keel. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | ANC TAXILANE V GATE RECONSTRUCTION | Anchorage | 2025-03-01 | CFAPT01278 | CFAPT01278 | 3-02-0016-XXX-2025 | Jennifer M Lombardo | (907)266-2731 | Reconstruct the taxilane Victor gate to increase the reliability and security and reduce the maintenance burden of the pilot controlled (radio signal activated) aircraft access gate. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | ANC Gates B5 and B7 Passenger Boarding Bridge (PBB) Replacements | Anchorage | 2024-11-01 | CSAPT01277 | CSAPT01277 | N/A | Ashley B Devore | (907)266-2171 | Design build project to remove and replace two existing passenger boarding bridges (PBBs) at Ted Stevens Anchorage International Airport. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | ANC Old AFM Gate Rebid | Anchorage | 2024-11-01 | CSAPT01150B | CSAPT01150B | N/A | Jennifer M Lombardo | (907)266-2731 | This state funded contract will install pivot gates, access controls, bi-level card reader pedestals, loop detectors, and chain link fence at the old Airfield Maintenance Facility at the Ted Stevens Anchorage International Airport. Also included in the scope is installation of access control and an exit card reader at the North Terminal employee parking lot. Work includes saw cutting and removing existing pavement, trenching, installing new conduit and conductors, and reestablishing pavement. | Will advertise with CSAPT00931 - ANC Access Gate and HBO Installation. | Between $200,000 and $500,000
Central Region | ADDLINFO |  | Consultant is providing preliminary design information. |  | (1) [on 2024.04.15 project was added.] | ANC C Concourse Plaza Renovation Design | Anchorage | 2025-04-01 | CSAPT01196
Central Region | ADDLINFO | Two PS&Es will be advertised on year apart with roughly equal amounts in 2025 and 2026. The amount shown is for the first contract. | A second construction stages will be tentatively advertised in April 2026 with an engineer's estimate range of $20,000,000 and $30,000,000. The engineer's estimate range shown here is for the first stage only. |  | (1) [on 2024.04.15 project was added.] | HSIP: ANCHORAGE FLASHING YLW ARROW & SIGNAL HEAD DISPLAY IMP | Anchorage | 2025-08-01 | CFHWY00944
Central Region | ANTADVDT | 2025-04-01 | 2025-07-01 | (1) [on 2024.09.17 the ANTADVDT changed to April 2025.] | (8) [on 2022.05.16 project was added.]; [on 2022.07.12 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.02.14 project was added.]; [on 2024.09.17 the ANTADVDT changed to April 2025.]; [on 2024.09.17 PHONENUM changed.]; [on 2024.09.17 PROJMAN changed.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2025-07-01 | CFHWY00394
Central Region | ANTADVDT | 2025-04-01 | 2025-07-01 |  | (1) [on 2024.09.17 project was added.] | VICTORY ROAD PAVEMENT PRESERVATION | Chickaloon | 2025-07-01 | CFHWY00672
Central Region | ANTADVDT | 2025-02-01 | 2025-04-01 |  | (1) [on 2024.09.17 project was added.] | BIG LAKE RD: MP 0-3.6 AND CHURCH RD PAVEMENT PRESERVATION | Big Lake | 2025-04-01 | CFHWY00906
Central Region | ANTADVDT | 2025-01-01 | 2025-04-01 |  | (1) [on 2024.04.15 project was added.] | ANC C Concourse Plaza Renovation Design | Anchorage | 2025-04-01 | CSAPT01196
Central Region | ANTADVDT | 2025-01-01 | 2025-02-01 | (7) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.02.14 the ANTADVDT changed to January 2025.] | (13) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 FEDNUM changed.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to January 2025.]; [on 2024.02.14 DESCRIPTION changed.] | ANC TAXIWAY K TUG ROAD IMPROVEMENTS | Anchorage | 2025-02-01 | CFAPT00992
Central Region | ANTADVDT | 2025-01-01 | 2025-03-01 | (2) [on 2024.04.15 the ANTADVDT changed to November 2024.]; [on 2024.08.15 the ANTADVDT changed to January 2025.] | (6) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2023.08.21 project was added.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to November 2024.]; [on 2024.08.15 the ANTADVDT changed to January 2025.] | HSIP: PALMER-FISHHOOK RD & TRUNK RD ROUNDABOUT | Palmer | 2025-03-01 | CFHWY00829
Central Region | ANTADVDT | 2025-07-01 | 2025-08-01 | (1) [on 2024.09.17 the ANTADVDT changed to July 2025.] | (2) [on 2024.05.16 project was added.]; [on 2024.09.17 the ANTADVDT changed to July 2025.] | PALMER-FISHHOOK ROAD MILEPOSTS 7-17 | Matanuska-Susitna Borough | 2025-08-01 | CFHWY00405
Central Region | ANTADVDT | 2025-06-01 | 2025-07-01 | (1) [on 2024.09.17 the ANTADVDT changed to June 2025.] | (2) [on 2024.04.15 project was added.]; [on 2024.09.17 the ANTADVDT changed to June 2025.] | TAKOTNA AIRPORT REHABILITATION | Central | 2025-07-01 | CFAPT00805
Central Region | ANTADVDT | 2025-06-01 | 2024-11-01 |  | (1) [on 2024.09.17 project was added.] | TAKOTNA RIVER BRIDGE REPLACEMENT - REBID | Takotna | 2024-11-01 | CFHWY00129-A
Central Region | ANTADVDT | 2025-06-01 | 2024-11-01 |  | (1) [on 2024.09.17 project was added.] | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT - REBID | Takotna | 2024-11-01 | Z516210000-A
Central Region | ANTADVDT | 2025-03-01 | 2025-05-01 | (10) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to October 2024.]; [on 2024.07.24 the ANTADVDT changed to March 2025.] | (15) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to October 2024.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.07.24 the ANTADVDT changed to March 2025.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2025-05-01 | CFHWY00260
Central Region | ANTADVDT | 2025-03-01 | 2025-08-01 |  | (1) [on 2024.04.15 project was added.] | HSIP: ANCHORAGE FLASHING YLW ARROW & SIGNAL HEAD DISPLAY IMP | Anchorage | 2025-08-01 | CFHWY00944
Central Region | ANTADVDT | 2024-11-01 | 2025-06-01 |  | (5) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 PROJNAME changed.]; [on 2023.09.15 the project was removed.]; [on 2023.12.15 project was added.] | AMATS: DOWNTOWN TRAIL CONNECTION | Anchorage | 2025-06-01 | CFHWY00586
Central Region | ANTADVDT | 2024-11-01 | 2024-12-01 | (2) [on 2024.08.15 the ANTADVDT changed to April 2025.]; [on 2024.09.17 the ANTADVDT changed to November 2024.] | (5) [on 2023.11.15 project was added.]; [on 2024.08.15 the ANTADVDT changed to April 2025.]; [on 2024.08.15 ENGEST changed.]; [on 2024.09.17 the ANTADVDT changed to November 2024.]; [on 2024.09.17 ENGEST changed.] | AMATS: VFW ROAD - EAGLE RIVER LP TO EAGLE RIVER RD PP | Eagle River | 2024-12-01 | CFHWY00732
Central Region | ANTADVDT | 2024-10-01 | 2024-11-01 | (15) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.]; [on 2024.09.17 the ANTADVDT changed to October 2024.] | (22) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.]; [on 2024.09.17 the ANTADVDT changed to October 2024.] | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | Anchorage | 2024-11-01 | CSAPT00931
Central Region | ANTADVDT | 2024-10-01 | 2025-01-01 | (6) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.]; [on 2024.08.15 the ANTADVDT changed to October 2024.] | (9) [on 2023.08.21 project was added.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.]; [on 2024.08.15 the ANTADVDT changed to October 2024.]; [on 2024.08.15 FEDNUM changed.] | ANC WEST PERIMETER ROAD | Anchorage | 2025-01-01 | CFAPT01136
Central Region | ANTADVDT | 2024-09-01 | 2024-10-01 |  | (1) [on 2024.09.17 project was added.] | Juneau Second St & Gold St Parking Garage Repairs | Central Region | 2024-10-01 | SPFAC00540
Central Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (8) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | (13) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-10-01 | CFHWY01083
Central Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (4) [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | (9) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-10-01 | CFHWY01084
Central Region | DESCRIPTION | Adjust drive lanes at the entrance to provide enough width for maintenance equipment to plow in the vicinity of the access points. Project could include pavement removal and replacement, curb removal and replacement, landscaping, and utility relocations. | Adjust drive lanes at the entrance to provide enough width for maintenance equipment to plow in the vicinity of the access points and rehabilitate the pavement in the parking garage exit area. Project could include pavement removal and replacement, curb removal and replacement, landscaping, and utility relocations. |  | (1) [on 2024.04.15 project was added.] | ANC South Terminal Parking Area Improvements | Anchorage | 2025-01-01 | CSAPT01183
Central Region | DESCRIPTION | Rehabilitate approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, pavement rehabilitation, drainage improvements and pavement markings. | Rehabilitate approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, pavement rehabilitation, and pavement markings. Replacing ditch drainage with a pipe system between tug road and Taxiway Kilo. | (7) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.02.14 the ANTADVDT changed to January 2025.] | (13) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 FEDNUM changed.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to January 2025.]; [on 2024.02.14 DESCRIPTION changed.] | ANC TAXIWAY K TUG ROAD IMPROVEMENTS | Anchorage | 2025-02-01 | CFAPT00992
Central Region | DESCRIPTION | Resurface the runway, taxiway, apron, and access road to correct deep cracks, uneven surfaces, soft spots, and areas where subbase is exposed. Replace lighting, NAVAIDS, and improve drainage. | This federally funded project proposes to rehabilitate the runway, taxiway, apron, and access road. Drainage improvements will include special ditching, culvert replacement, and regrading ditches. Other improvements include airport lighting, visual aids, signs, and aircraft tie-downs. | (1) [on 2024.09.17 the ANTADVDT changed to June 2025.] | (2) [on 2024.04.15 project was added.]; [on 2024.09.17 the ANTADVDT changed to June 2025.] | TAKOTNA AIRPORT REHABILITATION | Central | 2025-07-01 | CFAPT00805
Central Region | DESCRIPTION | Rehabilitate the Parking Garage at Second St and Gold St. | This state funded project includes corrosion removal with metal coating, patching, and painting; steel and concrete repairs and replacement; painted traffic/parking markings; electrical power, lighting, and signal repairs; and deck drain installation to extend the useful life of the parking garage at Second St & Gold St in Juneau, Alaska. |  | (1) [on 2024.09.17 project was added.] | Juneau Second St & Gold St Parking Garage Repairs | Central Region | 2024-10-01 | SPFAC00540
Central Region | ENGEST | Pending | Between $2,500,000 and $5,000,000 |  | (2) [on 2024.05.16 project was added.]; [on 2024.09.17 PHONENUM changed.] | ANCHOR POINT ROAD MP 0-1.3 PAVEMENT PRESERVATION | Anchor Point | 2025-04-01 | CFHWY00601
Central Region | ENGEST | Pending | Between $2,500,000 and $5,000,000 |  | (1) [on 2024.09.17 project was added.] | HSIP: TUDOR RD: BAXTER RD TO PATTERSON ST CHANNELIZATION | Anchorage | 2025-08-01 | CFHWY01073
Central Region | ENGEST | Pending | Between $30,000,000 and $40,000,000 |  | (3) [on 2022.08.14 project was added.]; [on 2023.06.15 the project was removed.]; [on 2024.09.17 project was added.] | KWIGILLINGOK AIRPORT IMPROVEMENTS | Kwigillingok | 2025-08-01 | Z525710000
Central Region | ENGEST | Pending | Between $2,500,000 and $5,000,000 |  | (1) [on 2024.09.17 project was added.] | MAT-SU AREA REPAIRS GROUP B - NOV 2018 EQ PERMANENT REPAIRS | Matanuska-Susitna Borough | 2025-08-01 | CFHWY00706
Central Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $2,500,000 and $5,000,000 |  | (1) [on 2024.04.15 project was added.] | ANC RON 12-14 Rehabilitation | Anchorage | 2025-01-01 | CFAPT01192
Central Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 |  | (1) [on 2024.08.15 project was added.] | KENAI SPUR HIGHWAY MP 29-38 PAVEMENT PRESERVATION | Kenai | 2025-07-01 | CFHWY00852
Central Region | ENGEST | Pending | Between $10,000,000 and $20,000,000 | (1) [on 2024.09.17 the ANTADVDT changed to July 2025.] | (2) [on 2024.05.16 project was added.]; [on 2024.09.17 the ANTADVDT changed to July 2025.] | PALMER-FISHHOOK ROAD MILEPOSTS 7-17 | Matanuska-Susitna Borough | 2025-08-01 | CFHWY00405
Central Region | ENGEST | Pending | Between $10,000,000 and $20,000,000 |  | (1) [on 2024.09.17 project was added.] | STERLING HWY: MP 169 TO 175 PAVEMENT PRESERVATION | Sterling | 2025-07-01 | CFHWY00857
Central Region | ENGEST | Pending | Between $10,000,000 and $20,000,000 | (1) [on 2024.09.17 the ANTADVDT changed to June 2025.] | (2) [on 2024.04.15 project was added.]; [on 2024.09.17 the ANTADVDT changed to June 2025.] | TAKOTNA AIRPORT REHABILITATION | Central | 2025-07-01 | CFAPT00805
Central Region | ENGEST | Pending | Between $5,000,000 and $10,000,000 |  | (1) [on 2024.04.15 project was added.] | HSIP: ANCHORAGE FLASHING YLW ARROW & SIGNAL HEAD DISPLAY IMP | Anchorage | 2025-08-01 | CFHWY00944
Central Region | FEDNUM | 3-02-0016-XXX-2024 | 3-02-0016-XXX-2025 | (7) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.02.14 the ANTADVDT changed to January 2025.] | (13) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 FEDNUM changed.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to January 2025.]; [on 2024.02.14 DESCRIPTION changed.] | ANC TAXIWAY K TUG ROAD IMPROVEMENTS | Anchorage | 2025-02-01 | CFAPT00992
Central Region | FEDNUM | 3-02-0013-XXX-2024 | 3-02-0013-XXX-2025 | (10) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (20) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the project was removed.]; [on 2024.02.14 project was added.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2025-01-01 | CFAPT00882
Central Region | FEDNUM | N/A | 0A42013 | (8) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | (13) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-10-01 | CFHWY01083
Central Region | FEDNUM | N/A | 0A42014 | (4) [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | (9) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.08.15 the ANTADVDT changed to September 2024.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-10-01 | CFHWY01084
Central Region | PHONENUM | (907)269-0619 | (907)269-0587 |  | (2) [on 2024.05.16 project was added.]; [on 2024.09.17 PHONENUM changed.] | ANCHOR POINT ROAD MP 0-1.3 PAVEMENT PRESERVATION | Anchor Point | 2025-04-01 | CFHWY00601
Central Region | PHONENUM | (907)269-0619 | (907)269-0587 |  | (1) [on 2024.09.17 project was added.] | KACHEMAK DRIVE MP 0-3.5 PAVEMENT PRESERVATION | Homer | 2025-06-01 | CFHWY00602
Central Region | PHONENUM | (907)269-0571 | (907)269-0587 |  | (1) [on 2024.09.17 project was added.] | TAKOTNA RIVER BRIDGE REPLACEMENT - REBID | Takotna | 2024-11-01 | CFHWY00129-A
Central Region | PHONENUM | (907)269-0571 | (907)269-0587 |  | (1) [on 2024.09.17 project was added.] | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT - REBID | Takotna | 2024-11-01 | Z516210000-A
Central Region | PHONENUM | (907)269-0641 | (907)269-0567 | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (5) [on 2023.03.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 the project was removed.]; [on 2024.06.19 project was added.] | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | Big Lake | 2025-05-01 | CFHWY00392
Central Region | PROJMAN | Steven J Rzepka | Rori A Van Nortwick |  | (2) [on 2024.05.16 project was added.]; [on 2024.09.17 PHONENUM changed.] | ANCHOR POINT ROAD MP 0-1.3 PAVEMENT PRESERVATION | Anchor Point | 2025-04-01 | CFHWY00601
Central Region | PROJMAN | Steven J Rzepka | Rori A Van Nortwick |  | (1) [on 2024.09.17 project was added.] | KACHEMAK DRIVE MP 0-3.5 PAVEMENT PRESERVATION | Homer | 2025-06-01 | CFHWY00602
Central Region | PROJMAN | Ryan R Hammel | Rori A Van Nortwick |  | (1) [on 2024.09.17 project was added.] | TAKOTNA RIVER BRIDGE REPLACEMENT - REBID | Takotna | 2024-11-01 | CFHWY00129-A
Central Region | PROJMAN | Ryan R Hammel | Rori A Van Nortwick |  | (1) [on 2024.09.17 project was added.] | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT - REBID | Takotna | 2024-11-01 | Z516210000-A
Central Region | PROJMAN | Alex L Read | Kristina H Busch | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (5) [on 2023.03.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 the project was removed.]; [on 2024.06.19 project was added.] | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | Big Lake | 2025-05-01 | CFHWY00392
Central Region | PROJNAME | ANC South Terminal Employee Entrance Improvements | ANC South Terminal Parking Area Improvements |  | (1) [on 2024.04.15 project was added.] | ANC South Terminal Parking Area Improvements | Anchorage | 2025-01-01 | CSAPT01183
Central Region | PROJNAME | ANC TAXIWAY KILO TUG ROAD REHABILITATION | ANC TAXIWAY K TUG ROAD IMPROVEMENTS | (7) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.02.14 the ANTADVDT changed to January 2025.] | (13) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 FEDNUM changed.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to January 2025.]; [on 2024.02.14 DESCRIPTION changed.] | ANC TAXIWAY K TUG ROAD IMPROVEMENTS | Anchorage | 2025-02-01 | CFAPT00992
Marine Highways | (DELETED) |  |  |  | (6) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the project was removed.]; [on 2024.04.15 project was added.]; [on 2024.06.19 DESCRIPTION changed.]; [on 2024.06.19 ENGEST changed.] | AMHS AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | Juneau | 2025-02-01 | SAMHS00419 | SAMHS00419 | 933048 | Misty L Butler | (907)465-4546 | Work includes: Removal of 5 mooring/berthing dolphins and replacing with 6 new mooring/berthing dolphins, removal and replacement of 5 catwalks, removal and replacement of 2 gangways, and electrical upgrades to dolphin and walkway lighting systems. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  |  | FIA Terminal North Apron Improvements | Fairbanks North Star Borough | 2025-08-01 | NFAPT00890 | NFAPT00890 | N/A | RJ Stumpf | (907)474-2587 | Project will strengthen a portion of the north terminal apron to support jet aircraft. |  | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  | (3) [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the project was removed.] | RICHARDSON HWY MP 82-115 RESURFACING (CONST MP 97-106.5) | Valdez | 2025-03-01 | NFHWY00218 | NFHWY00218 | 712035 | Russell M Johnson | (907)451-5059 | Resurface the Richardson Highway from MP 97 - 106.5. Improvements include bridge work, drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  | (2) [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to November 2024.] | (8) [on 2024.04.15 project was added.]; [on 2024.05.16 ADDLINFO changed.]; [on 2024.05.16 DESCRIPTION changed.]; [on 2024.05.16 ENGEST changed.]; [on 2024.05.16 PROJNAME changed.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to November 2024.]; [on 2024.09.17 the project was removed.] | Nenana Station Shop Roof Improvements | Nenana | 2024-11-01 | 2501000065A | 2501000065A | N/A | Lauren A Staft | (907)451-5424 | Replace Nenana DOT Maintenance Station Shop roof and perform structural repairs. |  | Between $500,000 and $1,000,000
Northern Region | ANTADVDT | 2024-11-01 | 2025-04-01 |  | (1) [on 2024.05.16 project was added.] | GLENN HIGHWAY MP 143-154 RESURFACING | Northern Region | 2025-04-01 | NFHWY00719
Northern Region | ANTADVDT | 2024-11-01 | 2025-04-01 | (3) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to November 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 PROJNAME changed.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to November 2024.] | Seppala Drive Upgrade | Nome | 2025-04-01 | Z620030000
Northern Region | ENGEST | Pending | Between $10,000,000 and $20,000,000 |  | (1) [on 2024.07.24 project was added.] | DALTON HIGHWAY MP 245-274 RESURFACING | Coldfoot | 2025-02-01 | NFHWY00764
Northern Region | FEDNUM | Pending | 641004 | (1) [on 2024.04.15 the ANTADVDT changed to November 2024.] | (3) [on 2024.01.16 project was added.]; [on 2024.04.15 the ANTADVDT changed to November 2024.]; [on 2024.08.15 FEDNUM changed.] | Cowles Street Reconstruction - Airport Way to East Cowles | Fairbanks | 2024-11-01 | NFHWY00883
Southcoast Region | (DELETED) |  |  |  | (1) [on 2024.09.17 project was added.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-12-01 | SFHWY00440-HNS001 | SFHWY00440-HNS001 | 93006 | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS00l, AK 2021 01 HNS002, AK 2021 01 HNS003, and AK 2021 01 HNS004. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway. |  | Between $200,000 and $500,000
Southcoast Region | (DELETED) |  |  |  | (3) [on 2022.08.14 project was added.]; [on 2023.03.15 the project was removed.]; [on 2024.08.15 project was added.] | KING SALMON AIRPORT RWY 18-36 AND GA APRON PVMNT REHAB PROJ | King Salmon | 2025-07-01 | SFAPT00362 | SFAPT00362 | N/A | Peter J Jackson | (907)465-4439 | Repave Runway 18-36 and Taxiways C,D,M, Terminal and GA Apron. Remove aligned taxiway on runway 36 |  | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  | (3) [on 2024.02.14 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to March 2025.]; [on 2024.07.24 the ANTADVDT changed to June 2025.] | (6) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2023.12.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to March 2025.]; [on 2024.07.24 the ANTADVDT changed to June 2025.] | HNS LUTAK ROAD 437114 - DEC 20 SE PR | Haines | 2025-06-01 | SDRER00448 | SDRER00448 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Damage Inventory Numbers 461224, 461227, 461237 - 461239, 461243 - 461250, 784625 - 784632, and 786036. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Lutak Road. This project is funded by FEMA. |  | Between $2,500,000 and $5,000,000
Southcoast Region | (DELETED) |  |  | (7) [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.]; [on 2024.09.17 the ANTADVDT changed to September 2024.] | (14) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 ADDLINFO changed.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.]; [on 2024.09.17 the ANTADVDT changed to September 2024.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-09-01 | Z686060000 | Z686060000 | 956028 | Gregory K Lockwood | (907)465-2393 | Reconstruction of Haines Highway from Milepost 20 to 25 including the Chilkat River bridge. | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise. New draft plans were posted on 11-22-2023 | Between $40,000,000 and $50,000,000
Southcoast Region | (DELETED) |  |  | (12) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.]; [on 2024.09.17 the ANTADVDT changed to September 2024.] | (18) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.]; [on 2024.08.15 the ANTADVDT changed to August 2024.]; [on 2024.09.17 the ANTADVDT changed to September 2024.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-09-01 | SFHWY00186 | SFHWY00186 | 3244 | Nathan A Purves | (907)465-4521 | Provide additional illumination at the Stedman/Deermount intersection to achieve a level of luminance that meets current DOT&PF standards. Construct a concrete sidewalk bulbout on the Stedman side of the marked crosswalk. The bulbout will extend from the existing sidewalk to the edge of the traveled way. |  | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  | (6) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.]; [on 2024.09.17 the ANTADVDT changed to September 2024.] | (14) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.]; [on 2024.05.16 ENGEST changed.]; [on 2024.08.15 PHONENUM changed.]; [on 2024.09.17 the ANTADVDT changed to September 2024.]; [on 2024.09.17 PHONENUM changed.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-09-01 | SFHWY00070 | SFHWY00070 | 3225 | Kirk D Miller | (907)465-1215 | This project will replace or rehabilitate the Sayles/Gorge Street Viaduct (#1841). | Remove and replace existing bridge structure. | Between $5,000,000 and $10,000,000
Southcoast Region | ADDED |  |  |  |  | JNU MENDENHLL LOOP RESRFCE: VALLEY-FLYD DRYDN & FLYD-STPHN | Juneau | 2025-08-01 | SFHWY00532 | SFHWY00532 | 966031 | Nathan A Purves | (907)465-4521 | Resurface Mendenhall Loop Road between Stephen Richards and Floyd Dryden roundabouts and between Floyd Dryden Roundabout and Valley Blvd intersection. Phase T02015 CC 24300499 LC 33009412 |  | Pending
Southcoast Region | ADDED |  |  |  |  | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-10-01 | SFHWY00186_A | SFHWY00186_A | 3244 | Nathan A Purves | (907)465-4521 | Provide additional illumination at the Stedman/Deermount intersection to achieve a level of luminance that meets current DOT&PF standards. Construct a concrete sidewalk bulbout on the Stedman side of the marked crosswalk. The bulbout will extend from the existing sidewalk to the edge of the traveled way. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDLINFO | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS001 - HNS004. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway between Milepost (MP) 1 - 9. This project is funded by FHWA. | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS001 - HNS004. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway between Milepost (MP) 1 - 9. This project is funded by FHWA. | (5) [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.]; [on 2024.09.17 the ANTADVDT changed to January 2025.] | (8) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.]; [on 2024.09.17 ADDLINFO changed.]; [on 2024.09.17 the ANTADVDT changed to January 2025.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2025-02-01 | SFHWY00440
Southcoast Region | ANTADVDT | 2025-08-01 | 2025-09-01 | (1) [on 2024.09.17 the ANTADVDT changed to August 2025.] | (2) [on 2024.06.19 project was added.]; [on 2024.09.17 the ANTADVDT changed to August 2025.] | HSIP: JNU VANDERBILT CONTINUOUS GREEN T | Juneau | 2025-09-01 | SFHWY00524
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-04-01 |  | (1) [on 2024.02.14 project was added.] | KDK ADQ AIRPORT TAXIWAYS C AND D RECNSTN | Kodiak | 2025-04-01 | SFAPT00558
Southcoast Region | ANTADVDT | 2025-01-01 | 2025-02-01 | (5) [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.]; [on 2024.09.17 the ANTADVDT changed to January 2025.] | (8) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.]; [on 2024.09.17 ADDLINFO changed.]; [on 2024.09.17 the ANTADVDT changed to January 2025.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2025-02-01 | SFHWY00440
Southcoast Region | ANTADVDT | 2025-03-01 | 2025-04-01 | (8) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.]; [on 2024.09.17 the ANTADVDT changed to March 2025.] | (10) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.]; [on 2024.09.17 the ANTADVDT changed to March 2025.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2025-04-01 | SDRER00436
Southcoast Region | ANTADVDT | 2025-03-01 | 2025-04-01 | (6) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.]; [on 2024.09.17 the ANTADVDT changed to March 2025.] | (9) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.]; [on 2024.07.24 the ANTADVDT changed to December 2024.]; [on 2024.07.24 DESCRIPTION changed.]; [on 2024.09.17 the ANTADVDT changed to March 2025.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2025-04-01 | SFHWY00481
Southcoast Region | ANTADVDT | 2025-03-01 | 2025-04-01 | (6) [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.]; [on 2024.09.17 the ANTADVDT changed to March 2025.] | (11) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.]; [on 2024.07.24 the ANTADVDT changed to January 2025.]; [on 2024.09.17 ADDLINFO changed.]; [on 2024.09.17 the ANTADVDT changed to March 2025.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2025-04-01 | SFHWY00438
Southcoast Region | ANTADVDT | 2024-11-01 | 2025-02-01 | (3) [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | (8) [on 2023.05.15 project was added.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2023.12.15 PHONENUM changed.]; [on 2023.12.15 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2025-02-01 | SFHWY00312
Southcoast Region | ANTADVDT | 2024-10-01 | 2024-11-01 | (4) [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.]; [on 2024.09.17 the ANTADVDT changed to October 2024.] | (6) [on 2023.10.25 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.06.19 DESCRIPTION changed.]; [on 2024.07.24 the ANTADVDT changed to September 2024.]; [on 2024.09.17 the ANTADVDT changed to October 2024.] | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | Ketchikan | 2024-11-01 | SFHWY00536