## 2023.08.21 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (5) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.04.14 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.] | (6) [on 2022.01.18 the ANTADVDT changed to December 2022.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.04.14 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.] | MEKORYUK AIRPORT REHABILITATION | Mekoryuk | 2023-08-01 | CFAPT00288 | CFAPT00288 | 3-02-0176-003-2023 | Philip W Cheasebro | (907)269-0606 | Rehabilitate/reconstruct runway, taxiway, and access road. Install new lighting. Install new heated two-bay SREB and install dust palliative. | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/6_00288%20-%20Mekoryuk%20Airport%20Rehabilitation%20Pre%20PSE-TAS.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  | (3) [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.] | (7) [on 2022.01.18 PHONENUM changed.]; [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.02.24 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.] | MEKORYUK AIRPORT SNOW REMOVAL EQUIPMENT BUILDING | Mekoryuk | 2023-08-01 | CFAPT00269 | CFAPT00269 | AIP 3-02-0176-003-2022 | Matthew R Epp | (907)764-4881 | Project will construct a new heated 2-bay SREB, vehicle fueling station.. | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/6_00288%20-%20Mekoryuk%20Airport%20Rehabilitation%20Pre%20PSE-TAS.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2023.02.24 project was added.]; [on 2023.03.15 PHONENUM changed.]; [on 2023.03.15 PROJMAN changed.] | SELDOVIA AIRPORT IMPROVEMENTS | Seldovia | 2024-01-01 | CFAPT00937 | CFAPT00937 | 3-02-0258-XXX-202X | Kim D Satterfield | (907)269-0623 | Rehabilitate the runway, apron, and segmented circle access. Construct a new taxilane to the east of the existing apron. Replace culverts and improve drainage as needed. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (3) [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | (5) [on 2022.09.13 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | KENAI PENINSULA BRIDGE DECK REHABILITATIONS FY2023 | Kenai Peninsula | 2023-07-01 | CFHWY00946 | CFHWY00946 | 0A33033 | Galen K Jones | (907)269-0550 | This project proposes to make preservation-related improvements to bridges within Kenai Peninsula Borough to reduce future maintenance and extend their serviceable lifespan. Work includes bridge deck polyester concrete overlays, structural retrofits, miscellaneous structural repairs, expansion joints, bridge rail upgrades, guardrail and end terminals, paving, signing, and striping. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (9) [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.] | (10) [on 2022.04.15 project was added.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.] | Mt. Edgecumbe High School Building 290 Kitchen Make-up Air & Exhaust Fan Replacement | Sitka | 2023-07-01 | 25RC053613 | 25RC053613 | N/A | Christopher S Hodgin | (907)269-7484 | This state funded project includes the demolition of the existing kitchen make-up air and exhaust systems and replacement with new systems, at the Mt. Edgecumbe High School Campus in Sitka, Alaska |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  |  | (1) [on 2023.07.14 project was added.] | GLENN HIGHWAY: AIRPORT HEIGHTS TO PARK HIGHWAY REHAB | Anchorage | 2024-06-01 | CFHWY00545 | CFHWY00545 | 1656 | Chris L Bentz | (907)269-0652 | This project will rehabilitate the Glenn Highway from the intersection with Airport Heights ( MP 0.0) to the Parks Highway Interchange ( MP 33.0). The project may include Bridge work, roadside hardware, drainage Improvements, interchange improvements, ADA improvements, utilities and safety improvements. |  | Greater than $100,000,000
Central Region | ADDED |  |  |  |  | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | Hope | 2024-04-01 | CFHWY00928 | CFHWY00928 | 498002 | Galen K Jones | (907)269-0550 | Replace failing culverts on the Hope Highway at MP 7.9 and MP 12.9. Additional improvements may include, as necessary, resurfacing, erosion protection, guardrail, signs, and striping. | MP 12.9 only. MP 7.9 will be advertised under a separate contract in April 2025 | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | DOT&PF Annex Building Earthquake Repairs | Anchorage | 2023-08-01 | NPFAC00547 | NPFAC00547 | N/A | Vadim Belozertsev | (907)269-0879 | Project includes replacement of the West wing and repairs of other damage at the DOT&PF Annex Building, resulting from the November 30, 2018 earthquake. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | ANC RON 2 Rehabilitation | Anchorage | 2023-12-01 | CFAPT01104 | CFAPT01104 | 3-02-0016-XXX-2024 | Jennifer M Lombardo | (907)266-2731 | Remove and replace liquid joint sealant and perform cementitious and elastomeric concrete repairs on hardstand RON 2. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  |  | ANC TAXIWAY R TUG ROAD IMPROVEMENTS | Anchorage | 2024-01-01 | CSAPT01127 | CSAPT01127 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate approximately 7,000 feet of the tug road from Taxiway Victor to Alaska Cargo Port. Project includes pavement planning, paving, and striping |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | AMATS: DR. MARTIN LUTHER KING JR. AVENUE EXTENSION | Anchorage | 2024-07-01 | CFHWY00585 | CFHWY00585 | 1668 | Noah C King | (907)269-0657 | This is a Reconstruction project including Roadside Hardware, Drainage Improvements, Intersection Improvements, ADA Improvements & Utilities.
Central Region | ADDED |  |  |  | (2) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.] | HSIP: PALMER-FISHHOOK ROAD & TRUNK ROAD ROUNDABOUT | Palmer | 2024-07-01 | CFHWY00829 | CFHWY00829 | 441010 | Galen K Jones | (907)269-0550 | The project will reconstruct the three-leg intersection of Palmer-Fishhook Rd and Trunk Rd. This project may also include roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. | PIH 75% review estimate. | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  | (4) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2024-07-01 | CFHWY00503 | CFHWY00503 | 1644 | Cynthia L Ferguson | (907)269-0693 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements.
Central Region | ADDED |  |  |  |  | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-03-01 | CSAPT01146 | CSAPT01146 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate 3,300 feet of Postmark Drive from Rockwell Avenue to Dehavilland Avenue. Project includes pavement planning, paving, and striping. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | ANC WEST PERIMETER ROAD | Anchorage | 2024-03-01 | CFAPT01136 | CFAPT01136 | 3-02-0016-XXX-2024 | Jennifer M Lombardo | (907)266-2731 | Construct a perimeter road along the northwest edge of the security fence. The road will begin just south of the fuel farm and continue around northwest to follow the existing security fence. Project includes structural section, paving, and security fencing. |  | Between $500,000 and $1,000,000
Central Region | ADDLINFO | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/23-04-24_2022_FINAL_Safety%20Corridors%20Audit_DOTPF_DPS.pdf">Safety Corridors Audit 2022 (~10 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (1) [on 2023.07.14 the ANTADVDT changed to August 2023.] | (5) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2023-08-01 | CFHWY00130A
Central Region | ANTADVDT | 2023-08-01 | 2023-10-01 | (5) [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.] | (6) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.] | ANC SUPPLY WAREHOUSE ROOF REPLACEMENT | Anchorage | 2023-10-01 | CSAPT00858
Central Region | ANTADVDT | 2023-07-01 | 2023-09-01 | (2) [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | (7) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.03.15 PHONENUM changed.]; [on 2023.03.15 PROJMAN changed.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 ADDLINFO changed.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-09-01 | CFAPT00993
Central Region | ANTADVDT | 2023-07-01 | 2023-12-01 | (8) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | (16) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2023-12-01 | CFAPT00882
Central Region | ANTADVDT | 2023-07-01 | 2023-09-01 | (3) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | (9) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2023-09-01 | Z512210000
Central Region | ANTADVDT | 2023-06-01 | 2023-10-01 | (3) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (4) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2023-10-01 | 25RC053608
Central Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (1) [on 2023.05.15 the ANTADVDT changed to November 2023.] | (3) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Central Region | 2024-01-01 | CFHWY00523
Central Region | ANTADVDT | 2023-10-01 | 2024-01-01 | (7) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.] | (12) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2024-01-01 | CSAPT00931
Central Region | ANTADVDT | 2023-10-01 | 2024-01-01 |  | (4) [on 2022.11.17 project was added.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.07.14 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.] | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | Wasilla | 2024-01-01 | CFHWY00622
Central Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 | (1) [on 2023.05.15 the ANTADVDT changed to November 2023.] | (3) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Central Region | 2024-01-01 | CFHWY00523
Central Region | PROJNAME | AMATS: DOWNTOWN TRAIL CONNECTION | AMATS: DOWNTOWN TRAIL CONNECTION |  | (2) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.] | AMATS: DOWNTOWN TRAIL CONNECTION | Anchorage | 2024-03-01 | CFHWY00586
Northern Region | (DELETED) |  |  |  | (2) [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.] | RICHARDSON HWY MP 82-115 RESURFACING (CONST MP 97-115) | Valdez | 2023-12-01 | NFHWY00218 | NFHWY00218 | 712035 | Russell M Johnson | (907)451-5059 | Resurface the Richardson Highway from MP 97 - 115. Improvements include bridge work, drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  | (1) [on 2023.06.15 the ANTADVDT changed to July 2023.] | (5) [on 2022.07.12 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.02.24 PROJNAME changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | Chalkyitsik Airport Improvements | Chalkyitsik | 2023-07-01 | Z625970000 | Z625970000 | 3-02-0046-___-____ | Jonathan J Hutchinson | (907)451-5479 | Resurface the runway, taxiway, apron, and access road and place a dust palliative. Replace airport lighting system and elctrical building. Replace segmented circle and windcone. Construct a new snow removal equipment building. Improve airport drainage and remove obstructions. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  |  | Fairbanks Bike Lane Striping and Signing (TAP) | Fairbanks | 2024-04-01 | NFHWY00835 | NFHWY00835 | TA23001 | Ivet Hall | (907)451-5386 | Signing and striping on paved Fairbanks city streets to designate space for seasonal bicycle use. Project will include ADA improvements. |  | Between $200,000 and $500,000
Northern Region | ADDED |  |  |  |  | Northenr Region ADA Improvements - Fairbanks: 4th and 11th Avenues | Fairbanks | 2024-04-01 | NFHWY00840 | NFHWY00840 | N/A | Ivet Hall | (907)451-5386 | Reconstruct pedestrian facilities and adjacent areas on 4th Avenue and 11 Avenue in Fairbanks. Project includes drainage improvements, roadside hardware, and utilities. |  | Between $1,000,000 and $2,500,000
Northern Region | ADDED |  |  |  |  | Richardson Highway MP 330 Emergency Flooding Repair May 2023 | Salcha | 2023-08-01 | NDRER00825 | NDRER00825 | N/A | Daniel S Adamczak | (907)451-2294 | Project will install 450ft of guardrail including 2 parallel guardrail terminals to protect against the reduced clear zone caused by the loss of embankment due to May 2023 flooding. |  | Less than $200,000
Northern Region | ADDED |  |  |  |  | Alaska Hwy MP 1235-1268 Rehabilitation (Const MP 1252-1268) | Northway | 2024-01-01 | Z607520000 | Z607520000 | 0A11014 | David K Fischer | (907)451-5357 | CLARIFY SCOPE: Rehabilitate the Alaska Highway and construct new passing lanes. Project work will include bridge work, roadside hardware, drainage, intersection improvements and utilities. |  | Between $30,000,000 and $40,000,000
Northern Region | ADDED |  |  |  |  | PEARL CREEK ELEMENTARY SCHOOL ACCESS IMP AND PLUG-INS (CMAQ) | Fairbanks | 2024-01-01 | NFHWY00712 | NFHWY00712 | 2519 | John J Netardus | (907)451-5448 | Reconfigure existing parking lot and access roads at Pearl Creek Elementary School in Fairbanks in order to improve vehicle circulation and reduce vehicle idling. Parking lot work includes installation of new vehicle electrical plug-ins, ADA improvements, drainage improvements, paving, and roadside hardware. |  | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  |  | North Pole Woll Road Resurfacing and Widening | North Pole | 2024-03-01 | NFHWY00448 | NFHWY00448 | 2451 | Ivet Hall | (907)451-5386 | Resurface and widen the state-maintained portion of Woll Road in North Pole. Work also includes drainage improvements, roadside hardware, and utilities. |  | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  |  | CHENA RIDGE ROAD RESURFACING- KENTSHIRE DRIVE TO FRIAR'S WAY | Fairbanks North Star Borough | 2023-11-01 | NFHWY00838 | NFHWY00838 | N/A | John J Netardus | (907)451-5448 | Resurface Chena Ridge Road from Kentshire Drive to Friar's Way. Project includes drainage improvements and roadside hardware. |  | Between $2,500,000 and $5,000,000
Northern Region | ANTADVDT | 2023-07-01 | 2023-08-01 | (2) [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.] | (3) [on 2023.05.15 project was added.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.] | FIA Response Center Sleeping Quarters FY2023 | Fairbanks North Star Borough | 2023-08-01 | NSAPT00791
Northern Region | ANTADVDT | 2023-07-01 | 2023-08-01 | (5) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | (9) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-08-01 | Z768840000
Northern Region | ANTADVDT | 2023-07-01 | 2023-08-01 | (2) [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.] | (5) [on 2022.08.14 project was added.]; [on 2023.01.17 FEDNUM changed.]; [on 2023.01.17 PROJNAME changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.] | Marshall Airport Improvements | Marshall | 2023-08-01 | NFAPT00371
Northern Region | ANTADVDT | 2023-11-01 | 2023-12-01 |  | (1) [on 2023.06.15 project was added.] | COPPER CENTER VISITOR CENTER PAVEMENT PRESERVATION | Copper Center | 2023-12-01 | NFHWY00720
Northern Region | ANTADVDT | 2023-11-01 | 2023-12-01 | (2) [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.] | (9) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2023-12-01 | Z631860000
Northern Region | PROJNAME | HSIP: CITY OF FAIRBANKS SYSTEMIC SIGNAL UPGRADES | HSIP: City of Fairbanks Systemic Signal Upgrades |  | (1) [on 2023.07.14 project was added.] | HSIP: City of Fairbanks Systemic Signal Upgrades | Fairbanks | 2024-03-01 | NFHWY00592
Northern Region | PROJNAME | HSIP: NORTHERN REGION SYSTEMIC SIGNAL UPGRADES | HSIP: Northern Region Systemic Signal Upgrades |  | (1) [on 2023.07.14 project was added.] | HSIP: Northern Region Systemic Signal Upgrades | Fairbanks North Star Borough | 2024-03-01 | NFHWY00531
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.03.15 project was added.] | FFY20 VAR NON-PRIMARY VISUAL AID REPLACEMENT | Regionwide | 2023-08-01 | SFAPT00250 | SFAPT00250 | 3-02-0200-132-2020 | Peter J Jackson | (907)465-4439 | Remove the existing airport beacon and tower and replace with new beacon and tip down tower.
Southcoast Region | (DELETED) |  |  |  | (3) [on 2022.09.13 project was added.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 FEDNUM changed.] | SR REGIONWIDE GUARDRAIL INVENTORY AND UPGRADE HSIP | Regionwide | 2023-08-01 | SFHWY00404 | SFHWY00404 | 3278 | Nathan A Purves | (907)465-4521 | Assess and correct guardrail safety deficiencies along Principal and Minor Arterial routes with posted speeds of 40 mph or higher. Typical deficiencies include, but are not limited to, steel washers on the face of rail, insufficient length of need, steel blockouts without backup plates, and break away cable terminals.
Southcoast Region | (DELETED) |  |  |  | (2) [on 2023.02.24 project was added.]; [on 2023.07.14 FEDNUM changed.] | KTN AIRPORT FERRY CAPACITY MODIFICATIONS (GRAVINA) | Ketchikan | 2024-01-01 | SFHWY00184 | SFHWY00184 | 3233 | Kirk D Miller | (907)465-1215 | Modify existing airport ferry vessel to expand passenger and vehicle space. | Modify Airport Ferry Shuttle to accommodate more passengers. Project construction not funded. This project is cancelled. | Between $200,000 and $500,000
Southcoast Region | (DELETED) |  |  | (2) [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (5) [on 2022.02.22 DESCRIPTION changed.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | JNU KAXDIGOOWU HEEN DEI IMP (BROTHERHOOD BRIDGE TRAIL IMP) | Juneau | 2023-06-01 | SFHWY00259 | SFHWY00259 | TA18010 | Peter J Jackson | (907)465-4439 | This project will design and improve the Kaxdigoowu Heen Dei (Kax) Trail from River Road to the edge of Brotherhood Meadow, where a re-route planned for construction in 2019 would end, Work will primarily consist of selected areas of subgrade repair, repave the trail, The pedestrian bridge at Montana Creek will be replaced to provide a larger span that allows for some natural stream movement and can withstand emergency and maintenance vehicle use, and the banks armored to increase the expected useful life of the bridge. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  |  | (3) [on 2022.10.20 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.07.14 project was added.] | ANG AIRPORT INITIATION | Angoon | 2024-06-01 | SFAPT00086 | SFAPT00086 | N/A | David B Epstein | (907)465-4483 | Construction of a new airport and access roadways located 2.5 miles south of Angoon. CC: 24300114 LC: 33002332 |  | Greater than $100,000,000
Southcoast Region | ADDED |  |  |  | (7) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2023-12-01 | SFAPT00227 | SFAPT00227 | N/A | David A Pyeatt | None | ADQ airport ARFF Access improvements and Rehabilitation of Taxiway C, D and F. Project includes the non-private portion of the Apron. | PFAS Investigation may cause delay depending on results and how to manage waste material. This project will be done in three phases; TA dates and estimate shown are for Phase 1 work (reconstruction of apron and Taxiway F). | Between $20,000,000 and $30,000,000
Southcoast Region | ADDED |  |  | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (6) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.06.15 the project was removed.] | CRAIG ADA IMPROVEMENTS | Craig | 2024-07-01 | SFHWY00377 | SFHWY00377 | 3274 | Bran P Pollard | (907)465-4526 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  |  | Sheldon Jackson Museum Door Replacement | Southcoast Region | 2024-06-01 | 25RC053622 | 25RC053622 | N/A | David R Hepler | (907)269-0815 | Replacing main entry doors on the Sheldon Jackson Muesum. |  | Less than $200,000
Southcoast Region | ADDLINFO | Construction funding uncertain. | No construction funding allocated to date. Project uncertain. | (3) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.] | (10) [on 2022.01.18 ENGEST changed.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.] | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | Hoonah | 2024-05-01 | SFAPT00236
Southcoast Region | ANTADVDT | 2023-08-01 | 2023-12-01 | (1) [on 2022.09.13 the ANTADVDT changed to August 2023.] | (6) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2023-12-01 | SFHWY00070
Southcoast Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (10) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.] | (14) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2024-02-01 | Z680850000
Southcoast Region | ANTADVDT | 2023-07-01 | 2023-08-01 | (7) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | (10) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2023-08-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2023-07-01 | 2023-10-01 | (4) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.] | (10) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2023-10-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2023-06-01 | 2023-09-01 | (4) [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.] | (11) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.06.15 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-09-01 | SFHWY00058-3
Southcoast Region | ANTADVDT | 2023-06-01 | 2023-08-01 | (5) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (7) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.06.15 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 FEDNUM changed.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2023-08-01 | Z680910000
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 | (1) [on 2023.06.15 the ANTADVDT changed to March 2024.] | (2) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2024-05-01 | SDRER00436
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 |  | (1) [on 2023.06.15 project was added.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-05-01 | SFHWY00446
Southcoast Region | ANTADVDT | 2023-05-01 | 2023-09-01 | (2) [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.] | (7) [on 2022.11.17 project was added.]; [on 2022.12.17 ADDLINFO changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 DESCRIPTION changed.]; [on 2023.06.15 PROJNAME changed.] | POW NECK LAKE RD RECNTN STAGES 1 & 2 - WFLHD | Prince Of Wales Island | 2023-09-01 | SFHWY00375
Southcoast Region | ANTADVDT | 2023-10-01 | 2024-03-01 | (9) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.] | (10) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2024-03-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2023-10-01 | 2023-11-01 | (3) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.] | (8) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2023-11-01 | SFHWY00103
Southcoast Region | DESCRIPTION | Work required for this project includes reconstructing and resurfacing Douglas Highway from Egan Drive to about 700 feet south of Cordova Street. Other work includes ADA improvements, storm drain system repairs, and signing and striping improvements. A list of anticipated work items are listed below: • Pavement removal and roadway excavation • Pavement cold planing • Removal and installation of concrete gutter and curb & gutters • Removal and installation of asphalt and concrete sidewalks • Reconstruction of existing accessible sidewalk ramps • Replacement and lining of existing culverts and storm drains • Construction of riprap aprons • Installation of new curb inlets • Removal and installation of storm drain manholes • Replacement of existing signs • Addition of new signs • New pavement markings • Replacement of existing guardrail and bridge transition rail | Work required for this project includes reconstructing and resurfacing Douglas Highway from Egan Drive to about 700 feet south of Cordova Street. Other work includes ADA improvements, storm drain system repairs, and signing and striping improvements. A list of anticipated work items are: pavement removal and roadway excavation, pavement cold planning, removal and installation of concrete gutter and curb & gutters, removal and installation of asphalt and concrete sidewalks, reconstruction of existing accessible sidewalk ramps, replacement and lining of existing culverts and storm drains, construction of riprap aprons, installation of new curb inlets, removal and installation of storm drain manholes, replacement of existing signs, addition of new signs, new pavement markings, and replacement of existing guardrail and bridge transition rail. | (4) [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.] | (11) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.06.15 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-09-01 | SFHWY00058-3
Southcoast Region | ENGEST | Between $200,000 and $500,000 | Between $500,000 and $1,000,000 | (1) [on 2023.06.15 the ANTADVDT changed to December 2023.] | (3) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.] | JNU WAYDELICH CREEK: LOWER WALL REPAIRS | Juneau | 2023-12-01 | SFHWY00485
Southcoast Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 | (5) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.] | (7) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.06.15 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 FEDNUM changed.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2023-08-01 | Z680910000
Southcoast Region | ENGEST | Between $10,000,000 and $20,000,000 | Between $5,000,000 and $10,000,000 |  | (7) [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.06.15 the project was removed.]; [on 2023.07.14 project was added.] | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | Kodiak | 2024-06-01 | SFHWY00260