## 2023.09.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (1) [on 2023.07.14 the ANTADVDT changed to April 2024.] | (5) [on 2022.05.16 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to April 2024.]; [on 2023.07.14 FEDNUM changed.] | HSIP: 5TH AVE: CONCRETE ST TO KARLUK ST PEDESTRIAN IMPROVMNT | Anchorage | 2024-04-01 | CFHWY00856 | CFHWY00856 | 421102 | Cynthia L Ferguson | (907)269-0693 | This HSIP project will construct a median barrier on 5th Avenue between Concrete Street and the couplet of 5th and 6th Avenues (Karluk Street). Work may include roadside hardware, drainage, improvements, and utilities.
Central Region | (DELETED) |  |  |  | (1) [on 2023.08.21 project was added.] | AMATS: DR. MARTIN LUTHER KING JR. AVENUE EXTENSION | Anchorage | 2024-07-01 | CFHWY00585 | CFHWY00585 | 1668 | Noah C King | (907)269-0657 | This is a Reconstruction project including Roadside Hardware, Drainage Improvements, Intersection Improvements, ADA Improvements & Utilities.
Central Region | (DELETED) |  |  |  | (3) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 PROJNAME changed.] | AMATS: DOWNTOWN TRAIL CONNECTION | Anchorage | 2024-03-01 | CFHWY00586 | CFHWY00586 | 1662 | Kristina H Busch | (907)269-0567 | Project will construct a connection between the Tony Knowles Coastal Trail to the Ship Creek Trail in downtown Anchorage. Major Project Elements include Bridge Work (Pedestrian), Roadside Hardware, Drainage Improvements, Intersection Improvements and ADA Improvements.
Central Region | (DELETED) |  |  | (6) [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | (7) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | ANC SUPPLY WAREHOUSE ROOF REPLACEMENT | Anchorage | 2023-10-01 | CSAPT00858 | CSAPT00858 | N/A | Jennifer C Pepin | (907)266-2549 | This project will replace the roof on the 14,400 sf, 1970's era supply warehouse (WH107). Aging and failing roofing will be replaced with new roofing and additional insulation to meet the current requirements. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | ANC RUNWAY 7L25R LIGHTING DUCT DRAINAGE IMPROVEMENTS | Anchorage | 2024-04-01 | CFAPT01149 | CFAPT01149 | 3-02-0016-XXX-2024 | Jennifer M Lombardo | (907)266-2731 | Provide a drainage system for the lighting duct near the east end of Runway (RW) 7L25R. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  | (4) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.] | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2024-08-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Cynthia L Ferguson | (907)269-0693 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards.
Central Region | ADDED |  |  |  |  | ANC OLD AFM GATE | Anchorage | 2024-03-01 | CSAPT01150 | CSAPT01150 | N/A | Jennifer M Lombardo | (907)266-2731 | Install a vertical pivot gate to secure the M&O yard at the Old AFM complex. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  |  | ANC VISUAL PAGING SYSTEM INSTALLATION | Anchorage | 2023-10-01 | CFAPT00930 | CFAPT00930 | N/A | Bonnie G Allen | (907)266-2510 | Install an estimated 70 monitors and 70 input stations with associated hardware, software, and accessories to provide visual paging throughout the South Terminal, Connector, and North Terminal Lobby to meet Americans with Disabilities Act (ADA) requirements.
Central Region | ADDLINFO | Replacing 10 critical culverts along the Parks Highway. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/01083/CFHWY01083_Plans.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (1) [on 2023.06.15 the ANTADVDT changed to November 2023.] | (5) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2023-11-01 | CFHWY01083
Central Region | ADDLINFO | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00012/00012_Plans.pdf">Preliminary Plans (~150 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Tentative Ad Date and Estimate amount are based on information in Draft STIP August 2023, and are subject to change per the Final STIP when available. | (4) [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.] | (10) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2022.10.20 PHONENUM changed.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2024-02-01 | CFHWY00012
Central Region | ADDLINFO | Reconstruct and upgrade 12 miles of the Sterling Hwy along the existing corridor from Anchor Pt to Baycrest Hill. Replacement of North Fork Anchor River and Anchor River Bridges. Project upgrades include widening, construction of passing lanes, resurfacing, drainage improvements, minor realignment, and configuration to current AASHTO geometric standards. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/58106/Z581060000_Sterling_Hwy_Preliminary%20Plan.pdf">Preliminary Plans (~133 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (4) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to November 2023.] | (9) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-12-01 | Z581060000
Central Region | ANTADVDT | 2023-08-01 | 2023-10-01 |  | (1) [on 2023.08.21 project was added.] | DOT&PF Annex Building Earthquake Repairs | Anchorage | 2023-10-01 | NPFAC00547
Central Region | ANTADVDT | 2023-08-01 | 2023-11-01 | (7) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.] | (10) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2023-11-01 | CFHWY00395
Central Region | ANTADVDT | 2023-08-01 | 2023-09-01 | (1) [on 2023.07.14 the ANTADVDT changed to August 2023.] | (6) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2023-09-01 | CFHWY00130A
Central Region | ANTADVDT | 2024-01-01 | 2024-04-01 | (2) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.] | (5) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Central Region | 2024-04-01 | CFHWY00523
Central Region | ANTADVDT | 2023-11-01 | 2024-02-01 | (4) [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.] | (10) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2022.10.20 PHONENUM changed.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2024-02-01 | CFHWY00012
Central Region | ANTADVDT | 2023-11-01 | 2023-12-01 | (4) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to November 2023.] | (9) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-12-01 | Z581060000
Central Region | ANTADVDT | 2023-10-01 | 2023-11-01 | (2) [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.] | (7) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2023-11-01 | CFHWY00943
Central Region | ANTADVDT | 2023-09-01 | 2023-10-01 | (3) [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.] | (8) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.03.15 PHONENUM changed.]; [on 2023.03.15 PROJMAN changed.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-10-01 | CFAPT00993
Central Region | ANTADVDT | 2023-09-01 | 2023-11-01 | (6) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.] | (9) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2023-11-01 | CFHWY00260
Central Region | DESCRIPTION | Rehabilitate approximately 7,000 feet of the tug road from Taxiway Victor to Alaska Cargo Port. Project includes pavement planning, paving, and striping | Rehabilitate approximately 7,000 feet of the tug road from Taxiway Victor to Alaska Cargo Port. Project includes pavement planning, paving, and striping. |  | (1) [on 2023.08.21 project was added.] | ANC TAXIWAY R TUG ROAD IMPROVEMENTS | Anchorage | 2024-01-01 | CSAPT01127
Central Region | ENGEST |  | Between $10,000,000 and $20,000,000 |  | (5) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.08.21 project was added.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2024-07-01 | CFHWY00503
Central Region | ENGEST | Greater than $100,000,000 | Between $30,000,000 and $40,000,000 | (4) [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.] | (10) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2022.10.20 PHONENUM changed.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2024-02-01 | CFHWY00012
Central Region | PHONENUM | (907)269-0693 | (907)269-0657 |  | (5) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.08.21 project was added.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2024-07-01 | CFHWY00503
Central Region | PROJMAN | Cynthia L Ferguson | Noah C King |  | (5) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.08.21 project was added.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2024-07-01 | CFHWY00503
Northern Region | (DELETED) |  |  | (3) [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | (4) [on 2023.05.15 project was added.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | FIA Response Center Sleeping Quarters FY2023 | Fairbanks North Star Borough | 2023-08-01 | NSAPT00791 | NSAPT00791 | N/A | RJ Stumpf | (907)474-2587 | Construct permanent sleeping quarters in the Airport Response Center building. |  | Between $200,000 and $500,000
Northern Region | (DELETED) |  |  | (3) [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | (6) [on 2022.08.14 project was added.]; [on 2023.01.17 FEDNUM changed.]; [on 2023.01.17 PROJNAME changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | Marshall Airport Improvements | Marshall | 2023-08-01 | NFAPT00371 | NFAPT00371 | 3-02-0363-___-____ | Christopher F Johnston | (907)451-2322 | Rehabilitate the runway, taxiway, apron, airport access road, and the snow removal equipment building, replace airport lighting and segmented circle, and apply dust palliative. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.08.21 project was added.] | Richardson Highway MP 330 Emergency Flooding Repair May 2023 | Salcha | 2023-08-01 | NDRER00825 | NDRER00825 | N/A | Daniel S Adamczak | (907)451-2294 | Project will install 450ft of guardrail including 2 parallel guardrail terminals to protect against the reduced clear zone caused by the loss of embankment due to May 2023 flooding. |  | Less than $200,000
Northern Region | (DELETED) |  |  | (3) [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | (10) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2023-12-01 | Z631860000 | Z631860000 | 713010 | Russell M Johnson | (907)451-5059 | Reconstruct the Richardson Highway between MP 167 and 173. Project includes roadside hardware, drainage improvements and utility relocations. | Reconstruct the Richardson Highway between mileposts 167-173. | Between $30,000,000 and $40,000,000
Northern Region | (DELETED) |  |  | (6) [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to September 2023.] | (11) [on 2022.01.18 project was added.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2022.10.20 PROJNAME changed.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 ADDLINFO changed.]; [on 2023.04.14 ADDLINFO changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.05.15 FEDNUM changed.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to September 2023.] | Richardson Highway MP 266-341 Passing Lanes | Fairbanks North Star Borough | 2023-09-01 | Z607150000 | Z607150000 | 0A23(021) | Carl F Heim | (907)451-5359 | Construct passing lanes at multiple locations between Milepost 266 and 341 on the Richardson Highway. Work includes roadside hardware, drainage improvements, intersection improvements and utilities. |  | Between $30,000,000 and $40,000,000
Northern Region | ADDED |  |  |  |  | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT FFY2021 | Regionwide | 2024-05-01 | NFAPT00563 | NFAPT00563 | N/A | Daniel A Phillips | (907)451-2926 | REVISED SCOPE: Acquire snow removal equipment (rotary plow & broom) for the Valdez Airport. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  |  | Gulkana River Boat Launch Fencing | Gulkana | 2023-09-01 | NSHWY00497a | NSHWY00497a | N/A | Scott L Maybrier | (907)451-5380 | Construct fencing along the boat launch on the Gulkana River. |  | Less than $200,000
Northern Region | ANTADVDT | 2023-08-01 | 2023-09-01 | (6) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | (10) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-09-01 | Z768840000
Northern Region | ANTADVDT | 2023-11-01 | 2023-09-01 | (4) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to November 2023.] | (10) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 FEDNUM changed.]; [on 2023.06.15 PROJNAME changed.]; [on 2023.07.14 the ANTADVDT changed to November 2023.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-09-01 | NFHWY00527
Northern Region | ENGEST |  | Between $5,000,000 and $10,000,000 |  | (1) [on 2023.06.15 project was added.] | KOTZEBUE AIRPORT CROSSWIND RUNWAY IMPROVEMENTS | Kotzebue | 2024-05-01 | NFAPT00600
Northern Region | FEDNUM | N/A | 3-02-0160-___-____ |  | (1) [on 2023.06.15 project was added.] | KOTZEBUE AIRPORT CROSSWIND RUNWAY IMPROVEMENTS | Kotzebue | 2024-05-01 | NFAPT00600
Northern Region | FEDNUM | N/A | Pending |  | (1) [on 2023.08.21 project was added.] | Chena Ridge Road Resurfacing- Kentshire Drive To Friar's Way | Fairbanks | 2023-11-01 | NFHWY00838
Northern Region | LOCATION | Fairbanks North Star Borough | Fairbanks |  | (1) [on 2023.08.21 project was added.] | Chena Ridge Road Resurfacing- Kentshire Drive To Friar's Way | Fairbanks | 2023-11-01 | NFHWY00838
Northern Region | PHONENUM | (907)451-5359 | (907)374-3743 | (4) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to November 2023.] | (10) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 FEDNUM changed.]; [on 2023.06.15 PROJNAME changed.]; [on 2023.07.14 the ANTADVDT changed to November 2023.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-09-01 | NFHWY00527
Northern Region | PROJMAN | Carl F Heim | David D Jensen | (4) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to November 2023.] | (10) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 FEDNUM changed.]; [on 2023.06.15 PROJNAME changed.]; [on 2023.07.14 the ANTADVDT changed to November 2023.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-09-01 | NFHWY00527
Northern Region | PROJNAME | Northenr Region ADA Improvements - Fairbanks: 4th and 11th Avenues | Northern Region ADA Improvements - Fairbanks: 4th and 11th Avenues |  | (1) [on 2023.08.21 project was added.] | Northern Region ADA Improvements - Fairbanks: 4th and 11th Avenues | Fairbanks | 2024-04-01 | NFHWY00840
Northern Region | PROJNAME | RUBY SLOUGH ROAD REHABILITATION | Ruby Slough Road Rehabilitation |  | (1) [on 2023.07.14 project was added.] | Ruby Slough Road Rehabilitation | Ruby | 2024-03-01 | NFHWY00630
Northern Region | PROJNAME | CHENA RIDGE ROAD RESURFACING- KENTSHIRE DRIVE TO FRIAR'S WAY | Chena Ridge Road Resurfacing- Kentshire Drive To Friar's Way |  | (1) [on 2023.08.21 project was added.] | Chena Ridge Road Resurfacing- Kentshire Drive To Friar's Way | Fairbanks | 2023-11-01 | NFHWY00838
Southcoast Region | ADDED |  |  |  | (2) [on 2023.03.15 project was added.]; [on 2023.08.21 the project was removed.] | FFY20 VAR NON-PRIMARY VISUAL AID REPLACEMENT | Regionwide | 2024-08-01 | SFAPT00250 | SFAPT00250 | 3-02-0200-132-2020 | Peter J Jackson | (907)465-4439 | Remove the existing airport beacon and tower and replace with new beacon and tip down tower.
Southcoast Region | ADDED |  |  |  |  | KTN N.TONGASS HWY RESURFACE: A/P F.T. TO WARD CREEK BRIDGE | Ketchikan | 2024-06-01 | SFHWY00181 | SFHWY00181 | 920031 | Brett M Wells | (907)465-1607 | Resurface North Tongass from the Airport Ferry Terminal (milepoint 0.717) to (and including) the Ward Cove (milepoint 4.485). Replace culverts and guardrail at the end of useful life. Correct erosion and clear brush at Cannery Creek Bridge No. 746. |  | Between $10,000,000 and $20,000,000
Southcoast Region | ANTADVDT | 2023-08-01 | 2023-09-01 | (8) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | (11) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2023-09-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2023-08-01 | 2023-09-01 | (6) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.] | (9) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.06.15 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.08.21 ENGEST changed.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2023-09-01 | Z680910000