## 2023.10.25 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (5) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.09.15 project was added.] | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2024-08-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Cynthia L Ferguson | (907)269-0693 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards.
Central Region | (DELETED) |  |  | (5) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.09.15 the ANTADVDT changed to December 2023.] | (11) [on 2022.08.14 the ANTADVDT changed to December 2022.]; [on 2022.09.13 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.05.15 ENGEST changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to December 2023.] | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Kenai Peninsula | 2023-12-01 | Z581060000 | Z581060000 | 211052 | Aaron L Hunting | (907)269-0546 | Reconstruction and upgrading of 12 miles of Sterling Highway along existing corridor. Project upgrades include widening, construction of passing lanes, resurfacing, scenic turnouts, drainage improvements, minor realignment, and configuration to current AASHTO geometric standards. Also, rehabilitation/replacement of the North Fork Anchor River and Anchor River Bridges. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/58106/Z581060000_Sterling_Hwy_Preliminary%20Plan.pdf">Preliminary Plans (~133 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $90,000,000 and $100,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2022.05.16 project was added.]; [on 2022.07.12 the project was removed.]; [on 2023.03.15 project was added.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2024-02-01 | CFHWY00394 | CFHWY00394 | 0A15039 | Kristina H Busch | (907)269-0567 | Resurface the Glenn Highway from Kings River bridge to Cascade. Additional improvements may include bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities as necessary. Project construction may be phased. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (5) [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.09.15 the ANTADVDT changed to February 2024.] | (13) [on 2022.03.15 project was added.]; [on 2022.09.13 the ANTADVDT changed to April 2023.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2022.10.20 the ANTADVDT changed to June 2023.]; [on 2022.10.20 PHONENUM changed.]; [on 2023.04.14 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to February 2024.]; [on 2023.09.15 ENGEST changed.] | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | Anchorage | 2024-02-01 | CFHWY00012 | CFHWY00012 | 537008 | Christina A Huber | (907)269-0572 | This federally funded project will reconstruct the Seward Highway between O'Malley Road and Dimond Blvd. Work may include: new north and south bound lanes and auxiliary lanes, a new interchange connecting 92nd Avenue to Academy Drive, reconstruction of the existing interchanges within the project limits, construction and reconstruction of frontage roads, pathway and sidewalk improvements, noise walls and drainage improvements. | Tentative Ad Date and Estimate amount are based on information in Draft STIP August 2023, and are subject to change per the Final STIP when available. | Between $30,000,000 and $40,000,000
Central Region | (DELETED) |  |  |  | (8) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.09.15 ENGEST changed.]; [on 2023.09.15 PHONENUM changed.]; [on 2023.09.15 PROJMAN changed.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2024-07-01 | CFHWY00503 | CFHWY00503 | 1644 | Noah C King | (907)269-0657 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (4) [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.]; [on 2023.03.15 the ANTADVDT changed to September 2023.] | (6) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.]; [on 2023.03.15 the ANTADVDT changed to September 2023.]; [on 2023.07.14 FEDNUM changed.] | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | Anchorage | 2023-09-01 | CFHWY00286 | CFHWY00286 | 510007 | Jon W Knowles | (907)269-0643 | Pavement Preservation of DeArmoun Rd. from East 140th Avenue to Hillside Drive including improvements to drainage, intersections, ADA, roadside hardware, and utilities. High Friction Surface Treatment may be reapplied. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-01-01 | CFAPT00983A | CFAPT00983A | 3-02-0016-XXX-2023 | Jennifer M Lombardo | (907)266-2731 | Remove and replace approximately 1,000 feet of security fence along the northeast edge of the airfield. Project includes clearing, grubbing, embankment extension and replacing swing gates. | Project will advertise with Taxiway R North and Taxilane U Rehabilitation. | Between $200,000 and $500,000
Central Region | ANTADVDT | 2023-12-01 | 2024-01-01 |  | (1) [on 2023.08.21 project was added.] | ANC RON 2 Rehabilitation | Anchorage | 2024-01-01 | CFAPT01104
Central Region | ANTADVDT | 2023-12-01 | 2024-01-01 | (9) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | (17) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2024-01-01 | CFAPT00882
Central Region | ANTADVDT | 2024-01-01 | 2024-06-01 | (4) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.] | (5) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.] | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | Anchorage | 2024-06-01 | CFAPT00992
Central Region | ANTADVDT | 2024-01-01 | 2024-03-01 |  | (2) [on 2023.08.21 project was added.]; [on 2023.09.15 DESCRIPTION changed.] | ANC TAXIWAY R TUG ROAD IMPROVEMENTS | Anchorage | 2024-03-01 | CSAPT01127
Central Region | ANTADVDT | 2024-01-01 | 2024-05-01 | (1) [on 2023.08.21 the ANTADVDT changed to January 2024.] | (5) [on 2022.11.17 project was added.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.07.14 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.] | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | Wasilla | 2024-05-01 | CFHWY00622
Central Region | ANTADVDT | 2024-06-01 | 2024-09-01 |  | (3) [on 2022.05.16 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.07.14 project was added.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2024-09-01 | CFHWY00555
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (1) [on 2023.08.21 project was added.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-04-01 | CSAPT01146
Central Region | ANTADVDT | 2023-11-01 | 2024-02-01 | (7) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.] | (10) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2024-02-01 | CFHWY00260
Central Region | ANTADVDT | 2023-11-01 | 2024-02-01 | (8) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.] | (11) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2024-02-01 | CFHWY00395
Central Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (1) [on 2023.06.15 the ANTADVDT changed to November 2023.] | (6) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-01-01 | CFHWY01083
Central Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (3) [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.] | (8) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2024-01-01 | CFHWY00943
Central Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (1) [on 2023.06.15 the ANTADVDT changed to November 2023.] | (3) [on 2023.05.15 project was added.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 ENGEST changed.] | SEWARD HWY: MP 75-90 ROAD&BRIDGE REHAB PHASE III | Anchorage | 2024-01-01 | Z581050000
Central Region | ANTADVDT | 2023-10-01 | 2023-11-01 | (4) [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to October 2023.] | (9) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.03.15 PHONENUM changed.]; [on 2023.03.15 PROJMAN changed.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to October 2023.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-11-01 | CFAPT00993
Central Region | ANTADVDT | 2023-10-01 | 2024-02-01 | (2) [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.] | (9) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2024-02-01 | CFHWY00883
Central Region | ANTADVDT | 2023-10-01 | 2023-12-01 | (4) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | (5) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2023-12-01 | 25RC053608
Central Region | ANTADVDT | 2023-09-01 | 2023-12-01 | (4) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.] | (10) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2023-12-01 | Z512210000
Central Region | ANTADVDT | 2023-09-01 | 2023-11-01 | (2) [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | (7) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2023-11-01 | CFHWY00130A
Central Region | ENGEST | Between $500,000 and $1,000,000 | Between $1,000,000 and $2,500,000 |  | (1) [on 2023.08.21 project was added.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-04-01 | CSAPT01146
Central Region | ENGEST |  | Between $1,000,000 and $2,500,000 |  | (1) [on 2023.09.15 project was added.] | ANC VISUAL PAGING SYSTEM INSTALLATION | Anchorage | 2023-10-01 | CFAPT00930
Central Region | FEDNUM | N/A | AIP 3-02-0016-XXX-2024 |  | (3) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.] | ANC TAXIWAY R NORTH IMPROVEMENTS | Anchorage | 2024-03-01 | CFAPT00880
Central Region | FEDNUM | N/A | AIP 3-02-0016-228-2024 | (4) [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to October 2023.] | (9) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.03.15 PHONENUM changed.]; [on 2023.03.15 PROJMAN changed.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to October 2023.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-11-01 | CFAPT00993
Central Region | PHONENUM | None | (907)419-4903 | (4) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | (5) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2023-12-01 | 25RC053608
Central Region | PROJMAN | None | Lance Mearig | (4) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | (5) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2023-12-01 | 25RC053608
Northern Region | (DELETED) |  |  |  | (7) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 FEDNUM changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2023.03.15 the project was removed.]; [on 2023.07.14 project was added.] | Buckland Airport Improvements | Buckland | 2024-06-01 | NFAPT00604 | NFAPT00604 | 3-02-0399-___-____ | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate the runway and taxiway, stabilize the embankments, resurface the airport access road, apply dust palliative, and replace the airport lighting system. |  | Between $5,000,000 and $10,000,000
Northern Region | (DELETED) |  |  | (1) [on 2022.02.22 the ANTADVDT changed to July 2022.] | (5) [on 2022.02.22 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2023.03.15 the project was removed.]; [on 2023.07.14 project was added.] | Deering Airport Improvements | Deering | 2024-06-01 | NFAPT00249 | NFAPT00249 | 3-02-0400-XX-202X | Jonathan J Hutchinson | (907)451-5479 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.06.15 project was added.] | Deadhorse Airport Improvements | Deadhorse | 2024-05-01 | NFAPT00549 | NFAPT00549 | 3-02-0339-___-____ | Jonathan J Hutchinson | (907)451-5479 | Construct drainage improvements at the Deadhorse Airport and along Deadhorse Drive and fill in-fields adjacent to the runway and apron. Construct a wildlife perimeter fence with a service road around the airfield. |  | Between $20,000,000 and $30,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.09.15 project was added.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT FFY2021 | Regionwide | 2024-05-01 | NFAPT00563 | NFAPT00563 | N/A | Daniel A Phillips | (907)451-2926 | REVISED SCOPE: Acquire snow removal equipment (rotary plow & broom) for the Valdez Airport. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  | (5) [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 the ANTADVDT changed to November 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | (13) [on 2022.08.14 project was added.]; [on 2022.09.13 ENGEST changed.]; [on 2022.09.13 PROJNAME changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 FEDNUM changed.]; [on 2023.06.15 PROJNAME changed.]; [on 2023.07.14 the ANTADVDT changed to November 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.09.15 PHONENUM changed.]; [on 2023.09.15 PROJMAN changed.] | Old Steese Highway Shoulder Widening (HSIP) | Fox | 2023-09-01 | NFHWY00527 | NFHWY00527 | 0002(472) | David D Jensen | (907)374-3743 | Reconstruct the Old Steese Highway between Gold Dredge #8 and the Fox Intersection. Work includes roadside hardware, drainage improvements, intersection improvements, and utilities. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  |  | Shishmaref Sanitation Road Erosion Control | Shishmaref | 2024-06-01 | NFHWY00687 | NFHWY00687 | 2514 | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate sections of the Shishmaref Sanitation Road and construct erosion control features. Project will include drainage improvements and roadside hardware. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  |  | RICHARDSON HWY MP 106.5-115 RESURFACING | Tazlina | 2023-11-01 | NFHWY00834 | NFHWY00834 | N/A | Russell M Johnson | (907)451-5059 | Resurface the Richardson Highway from MP 106.5 - 115. Improvements include drainage improvements and roadside hardware. |  | Between $10,000,000 and $20,000,000
Northern Region | ANTADVDT | 2023-11-01 | 2023-12-01 |  | (4) [on 2023.08.21 project was added.]; [on 2023.09.15 FEDNUM changed.]; [on 2023.09.15 LOCATION changed.]; [on 2023.09.15 PROJNAME changed.] | Chena Ridge Road Resurfacing - Kentshire Drive to Friar's Way | Fairbanks | 2023-12-01 | NFHWY00838
Northern Region | ANTADVDT | 2023-09-01 | 2024-05-01 |  | (1) [on 2023.09.15 project was added.] | Gulkana River Boat Launch Fencing | Gulkana | 2024-05-01 | NSHWY00497a
Northern Region | ANTADVDT | 2023-09-01 | 2023-10-01 | (7) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | (11) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-10-01 | Z768840000
Northern Region | ANTADVDT | 2023-09-01 | 2023-10-01 |  | (3) [on 2022.11.17 project was added.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PROJNAME changed.] | Richardson Highway MP 351 Interchange | North Pole | 2023-10-01 | NFHWY00097
Northern Region | DESCRIPTION | SCOPE CHANGE: Construct a new three bay snow removal equipment buidling including space for lighting controls and backup generators and a new deicing material storage building. | Construct a new three bay snow removal equipment building including space for lighting controls and backup generators and a new deicing material storage building. |  | (1) [on 2023.05.15 project was added.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez | 2024-04-01 | Z618600000
Northern Region | DESCRIPTION | CLARIFY SCOPE: Rehabilitate the Alaska Highway and construct new passing lanes. Project work will include bridge work, roadside hardware, drainage, intersection improvements and utilities. | Rehabilitate the Alaska Highway and construct new passing lanes. Project work will include bridge work, roadside hardware, drainage, intersection improvements and utilities. |  | (1) [on 2023.08.21 project was added.] | Alaska Hwy MP 1235-1268 Rehabilitation (Const MP 1252-1268) | Northway | 2024-01-01 | Z607520000
Northern Region | LOCATION | Livengood | Fox | (1) [on 2023.03.15 the ANTADVDT changed to January 2024.] | (7) [on 2022.06.15 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.02.24 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.03.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.07.14 PROJNAME changed.] | Elliott Highway MP 18 - 29 Resurfacing | Fox | 2024-01-01 | NFHWY00588
Northern Region | PROJNAME | North Pole Woll Road Resurfacing and Widening | Woll Road Resurfacing and Widening |  | (1) [on 2023.08.21 project was added.] | Woll Road Resurfacing and Widening | North Pole | 2024-03-01 | NFHWY00448
Northern Region | PROJNAME | KOTZEBUE AIRPORT CROSSWIND RUNWAY IMPROVEMENTS | Kotzebue Airport Crosswind Runway Imporvements |  | (3) [on 2023.06.15 project was added.]; [on 2023.09.15 ENGEST changed.]; [on 2023.09.15 FEDNUM changed.] | Kotzebue Airport Crosswind Runway Imporvements | Kotzebue | 2024-05-01 | NFAPT00600
Northern Region | PROJNAME | Chena Ridge Road Resurfacing- Kentshire Drive To Friar's Way | Chena Ridge Road Resurfacing - Kentshire Drive to Friar's Way |  | (4) [on 2023.08.21 project was added.]; [on 2023.09.15 FEDNUM changed.]; [on 2023.09.15 LOCATION changed.]; [on 2023.09.15 PROJNAME changed.] | Chena Ridge Road Resurfacing - Kentshire Drive to Friar's Way | Fairbanks | 2023-12-01 | NFHWY00838
Southcoast Region | (DELETED) |  |  |  | (3) [on 2023.03.15 project was added.]; [on 2023.08.21 the project was removed.]; [on 2023.09.15 project was added.] | FFY20 VAR NON-PRIMARY VISUAL AID REPLACEMENT | Regionwide | 2024-08-01 | SFAPT00250 | SFAPT00250 | 3-02-0200-132-2020 | Peter J Jackson | (907)465-4439 | Remove the existing airport beacon and tower and replace with new beacon and tip down tower.
Southcoast Region | (DELETED) |  |  | (4) [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 the ANTADVDT changed to February 2024.] | (9) [on 2022.09.13 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 FEDNUM changed.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2024-02-01 | SFHWY00326 | SFHWY00326 | 3265 | Brett M Wells | (907)465-1607 | Replace two damaged culverts with new Aquatic Organism Passage structures across Trout Creek and Little Trout Creek in Cold Bay, AK. |  | Between $2,500,000 and $5,000,000
Southcoast Region | (DELETED) |  |  |  | (4) [on 2023.03.15 project was added.]; [on 2023.05.15 ENGEST changed.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 FEDNUM changed.] | JNU L00P RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | Juneau | 2024-02-01 | SFHWY00403 | SFHWY00403 | 966030 | Nathan A Purves | (907)465-4521 | Construct a single-lane roundabout at the Loop Road - Mendenhall Boulevard - Valley Boulevard intersection. |  | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.06.15 project was added.] | FFY2020 EAS YAKUTAT OBSTRUCTION REMOVAL | Yakutat | 2023-07-01 | SFAPT00204 | SFAPT00204 | 3-02-0200-135-2020 | Spencer M Gates | (907)465-1014 | Cut 16 acres of trees on the south side of runway 29. |  | Between $200,000 and $500,000
Southcoast Region | (DELETED) |  |  | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (7) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.06.15 the project was removed.]; [on 2023.08.21 project was added.] | CRAIG ADA IMPROVEMENTS | Craig | 2024-07-01 | SFHWY00377 | SFHWY00377 | 3274 | Bran P Pollard | (907)465-4526 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit. |  | Between $2,500,000 and $5,000,000
Southcoast Region | (DELETED) |  |  |  | (8) [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.06.15 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.08.21 ENGEST changed.] | KDK REZANOFF DR RESURFACE: W.MARINE WAY TO AIRPORT | Kodiak | 2024-06-01 | SFHWY00260 | SFHWY00260 | 3247 | Bran P Pollard | (907)465-4526 | Resurface Rezanoff Drive from Marine Way to the airport. Associated preventative maintenance activities may include minor structural section improvements, drainage repairs, lighting and signals, striping, signs, and ADA improvements. Project Location and Length: Rezanoff Drive from Marine Way to the airport for an approximate length of 4.70 miles. |  | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.09.15 project was added.] | KTN N.TONGASS HWY RESURFACE: A/P F.T. TO WARD CREEK BRIDGE | Ketchikan | 2024-06-01 | SFHWY00181 | SFHWY00181 | 920031 | Brett M Wells | (907)465-1607 | Resurface North Tongass from the Airport Ferry Terminal (milepoint 0.717) to (and including) the Ward Cove (milepoint 4.485). Replace culverts and guardrail at the end of useful life. Correct erosion and clear brush at Cannery Creek Bridge No. 746. |  | Between $10,000,000 and $20,000,000
Southcoast Region | (DELETED) |  |  | (3) [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.] | (11) [on 2022.01.18 ENGEST changed.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 ADDLINFO changed.]; [on 2022.04.15 the ANTADVDT changed to August 2022.]; [on 2022.07.12 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.08.21 ADDLINFO changed.] | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | Hoonah | 2024-05-01 | SFAPT00236 | SFAPT00236 | N/A | Loren K Gehring | (907)465-8189 | Relocation of an existing stream bed and conduct dredging under the seaplane mooring float to restore sufficient water depths and/or relocation of the seaplane float structure to deeper water at the same location. Phase: T02000 - Par - All Costs | No construction funding allocated to date. Project uncertain. | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.06.15 project was added.] | HNS LUTAK ROAD 437114 - DEC 20 SE PR | Haines | 2024-05-01 | SDRER00448 | SDRER00448 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Damage Inventory Numbers 461224, 461227, 461237 - 461239, 461243 - 461250, 784625 - 784632, and 786036. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Lutak Road. This project is funded by FEMA. |  | Between $2,500,000 and $5,000,000
Southcoast Region | (DELETED) |  |  | (5) [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.] | (13) [on 2022.03.15 project was added.]; [on 2022.04.15 the ANTADVDT changed to November 2022.]; [on 2022.05.16 PROJNAME changed.]; [on 2022.06.15 the ANTADVDT changed to January 2023.]; [on 2022.06.15 ENGEST changed.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to June 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.08.21 DESCRIPTION changed.] | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS STAGE III | Juneau | 2023-09-01 | SFHWY00058-3 | SFHWY00058-3 | 958032 | Phil D White | (907)465-4456 | Work required for this project includes reconstructing and resurfacing Douglas Highway from Egan Drive to about 700 feet south of Cordova Street. Other work includes ADA improvements, storm drain system repairs, and signing and striping improvements. A list of anticipated work items are: pavement removal and roadway excavation, pavement cold planning, removal and installation of concrete gutter and curb & gutters, removal and installation of asphalt and concrete sidewalks, reconstruction of existing accessible sidewalk ramps, replacement and lining of existing culverts and storm drains, construction of riprap aprons, installation of new curb inlets, removal and installation of storm drain manholes, replacement of existing signs, addition of new signs, new pavement markings, and replacement of existing guardrail and bridge transition rail. |  | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  | (7) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | (10) [on 2022.04.15 the ANTADVDT changed to December 2022.]; [on 2022.06.15 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | KTN TONGASS AVE IMPROVEMENTS | Ketchikan | 2023-09-01 | Z680910000 | Z680910000 | 902042 | Peter J Jackson | (907)465-4439 | Refurbish Tongass Avenue, from MP 0.2010 to 1.2565 including rehabilitation of asphalt and concert pavement surfaces, curb and gutter, sidewalk, correct ADA deficiencies, make improvements to the signalization, lane configurations, and to the pedestrian and bicycle facilities to improve safety and level of service. |  | Between $10,000,000 and $20,000,000
Southcoast Region | ADDED |  |  |  |  | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | Ketchikan | 2024-05-01 | SFHWY00536 | SFHWY00536 | 920031 | Brett M Wells | (907)465-1607 |  |  | Between $5,000,000 and $10,000,000
Southcoast Region | ADDLINFO | PFAS Investigation may cause delay depending on results and how to manage waste material. This project will be done in three phases; TA dates and estimate shown are for Phase 1 work (reconstruction of apron and Taxiway F). | This project will encompass the reconstruction of the Apron and Taxiway F. Taxiways C & D are anticipated to be advertised under separate solicitation(s) in 2025 and 2026 subject to funding availability. |  | (8) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2024-01-01 | SFAPT00227
Southcoast Region | ADDLINFO |  | Construct Section 2 of the Sitka Seawalk Phase II Project. Project would construct approximately 750 lineal feet of seawalk including: armored embankment along the existing Sitka Harbor Channel Bridge approach, concrete sidewalk, pedestrian lighting, landscaping and interpretive signage. |  | (2) [on 2023.05.15 project was added.]; [on 2023.07.14 DESCRIPTION changed.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2024-05-01 | SFHWY00312
Southcoast Region | ANTADVDT | 2024-04-01 | 2024-07-01 |  | (1) [on 2023.06.15 project was added.] | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2024-07-01 | SDRER00445
Southcoast Region | ANTADVDT | 2023-08-01 | 2023-10-01 | (3) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.] | (10) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.] | WRG ZIMOVIA HWY ROCK FALL MITIGATION HSIP | Wrangell | 2023-10-01 | SFHWY00308
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-03-01 | (1) [on 2023.06.15 the ANTADVDT changed to December 2023.] | (4) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 ENGEST changed.] | JNU WAYDELICH CREEK: LOWER WALL REPAIRS | Juneau | 2024-03-01 | SFHWY00485
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-03-01 | (1) [on 2023.06.15 the ANTADVDT changed to December 2023.] | (3) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.] | JNU WAYDELICH CREEK: UPPER WALL REPAIRS - DEC 20 SE PR | Juneau | 2024-03-01 | SFHWY00414
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-01-01 |  | (8) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2024-01-01 | SFAPT00227
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-03-01 | (2) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | (7) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-03-01 | SFHWY00070
Southcoast Region | ANTADVDT | 2024-02-01 | 2024-05-01 |  | (2) [on 2023.05.15 project was added.]; [on 2023.07.14 DESCRIPTION changed.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2024-05-01 | SFHWY00312
Southcoast Region | ANTADVDT | 2024-01-01 | 2024-03-01 | (1) [on 2023.06.15 the ANTADVDT changed to January 2024.] | (7) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-03-01 | Z686060000
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-08-01 |  | (1) [on 2023.07.14 project was added.] | SGY, HNH, PSG ROADWAY & CULVERTS - DEC 20 SE PR | Southcoast Region | 2024-08-01 | SFHWY00447
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (2) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-04-01 | SFHWY00481
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-07-01 | (2) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.] | (3) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2024-07-01 | SDRER00436
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-08-01 | (1) [on 2023.08.21 the ANTADVDT changed to May 2024.] | (2) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-08-01 | SFHWY00446
Southcoast Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (4) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to November 2023.] | (9) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to November 2023.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2024-01-01 | SFHWY00103
Southcoast Region | ANTADVDT | 2023-10-01 | 2024-02-01 | (5) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | (11) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-02-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2023-09-01 | 2023-11-01 | (9) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | (12) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2023-11-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2023-09-01 | 2023-11-01 | (3) [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.] | (8) [on 2022.11.17 project was added.]; [on 2022.12.17 ADDLINFO changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 DESCRIPTION changed.]; [on 2023.06.15 PROJNAME changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.] | POW NECK LAKE RD RECNTN STAGES 1 & 2 - WFLHD | Prince Of Wales Island | 2023-11-01 | SFHWY00375
Southcoast Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $10,000,000 and $20,000,000 |  | (8) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2024-01-01 | SFAPT00227
Southcoast Region | ENGEST | Between $500,000 and $1,000,000 | Between $1,000,000 and $2,500,000 | (1) [on 2023.08.21 the ANTADVDT changed to May 2024.] | (2) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-08-01 | SFHWY00446
Southcoast Region | FEDNUM | 3-02-0200-120-2018 | 3-02-0277-007-2023 | (9) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | (12) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2023-11-01 | SFAPT00212
Southcoast Region | PHONENUM | None | (907)465-4483 |  | (8) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2024-01-01 | SFAPT00227
Southcoast Region | PHONENUM | (907)465-4456 | (907)465-1215 | (11) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.08.21 the ANTADVDT changed to February 2024.] | (15) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to February 2024.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2024-02-01 | Z680850000
Southcoast Region | PROJMAN | David A Pyeatt | David B Epstein |  | (8) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.] | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | Kodiak | 2024-01-01 | SFAPT00227
Southcoast Region | PROJMAN | Phil D White | Kirk D Miller | (11) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.08.21 the ANTADVDT changed to February 2024.] | (15) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to February 2024.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2024-02-01 | Z680850000