## 2023.11.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (2) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.] | ANCHORAGE AREA PAVEMENT PRESERVATION GROUP A | Anchorage | 2024-05-01 | CFHWY00851 | CFHWY00851 | 1739 | Christina A Huber | (907)269-0572 | Pavement preservation on multiple routes. Work may include improvements to roadside hardware, drainage, intersections, automated traffic recorders, pedestrian facilities, bridge work, striping, and utilities.
Central Region | (DELETED) |  |  | (5) [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | (11) [on 2022.12.17 project was added.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to June 2023.]; [on 2023.03.15 PHONENUM changed.]; [on 2023.03.15 PROJMAN changed.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.10.25 FEDNUM changed.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2023-11-01 | CFAPT00993 | CFAPT00993 | AIP 3-02-0016-228-2024 | Kim D Satterfield | (907)269-0623 | Repair the water main pipes at the South Terminal, North Terminal and Old Field Maintenance. | <a class=linkcopy href=https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/9_00993%20ANC%20Terminal%20Water%20Main%20Improvements%20-%20TAL.pdf>Preliminary Plans (~21 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (1) [on 2023.10.25 the ANTADVDT changed to September 2024.] | (4) [on 2022.05.16 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to September 2024.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2024-09-01 | CFHWY00555 | CFHWY00555 | 1657 | Julia R Hanson | (907)269-0753 | This AMATS funded project will reconstructed the traffic signal and street lighting system on 4th Ave between A Street and Ingra Street. Work may included signing, Striping, ATRs, drainage, paving, pedestrian & ADA amenities, utility relocation, landscaping and roadside hardware.
Central Region | ADDED |  |  |  |  | TALKEETNA AIRPORT LIGHTING IMPROVEMENTS | Talkeetna | 2024-04-01 | CFAPT01020 | CFAPT01020 | N/A | Kim D Satterfield | (907)269-0623 | Reconstruct the runway (1-19) lighting and taxiway (A, B, C, D, E, F, and G) lighting at Talkeetna Airport. Improvements also include replacing the wind cones, rotating beacon, and threshold markers. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | ANC ATCT REPLACEMENT PARKING | Anchorage | 2024-08-01 | CRMBS00831 | CRMBS00831 | N/A | Philip W Cheasebro | (907)269-0606 | This project will construct additional aircraft parking at LHD Echo Parking to replace parking impacted by FAA's new ATCT. | PIH 75% Review Estimate | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  |  | SEWARD HWY MP 90-99 PAVEMENT PRESERVATION | Regionwide | 2024-08-01 | CFHWY00850 | CFHWY00850 | 0A31066 | Julia R Hanson | (907)269-0753 | Pavement preservation, which may include improvements to roadside hardware, drainage, intersections, automated traffic recorders, pedestrian facilities, bridge work, striping, and utilities. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | ANC Job Order Construction Contract (RFP 2024) | Anchorage | 2024-01-01 | CSAPT01156 | CSAPT01156 | N/A | Jesse Campbell | (907)266-2723 | Indefinite delivery / indefinite quantity contract to perform maintenance, repair, and construction work supporting the mission of the Ted Stevens Anchorage International Airport. Contractor shall be responsible for both design and construction work. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | CHENEGA BAY AIRPORT LIGHTING IMPROVEMENTS | Chenega Bay | 2024-07-01 | CFAPT01021 | CFAPT01021 | N/A | Kim D Satterfield | (907)269-0623 | Replace runway and taxiway lighting systems, the segmented circle and lighted primary wind cone, and the lighted supplemental wind cone. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | ANC FIRING RANGE MAINTENANCE | Anchorage | 2024-03-01 | CSAPT01152 | CSAPT01152 | N/A | Jennifer M Lombardo | (907)266-2731 | Perform deferred maintenance on the active firing/shooting range at ANC by removing lead bullets and bullet fragments. Amend remaining affected soil with a heavy metal fixation reagent to prevent leaching of lead. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  |  | ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTIO | Anchorage | 2024-03-01 | CFAPT00881 | CFAPT00881 | N/A | Aaron C Hughes | (907)269-0523 | This project will design and construct improvements for the North Terminal Northside Aprons and Taxilane.
Central Region | ADDED |  |  |  |  | AMATS: VFW ROAD - EAGLE RIVER LP TO EAGLE RIVER RD PP | Eagle River | 2024-09-01 | CFHWY00732 | CFHWY00732 | 1695 | Christina A Huber | (907)269-0572 | This pavement preservation project includes resurfacing, roadside hardware, drainage improvements, bridge improvements, ADA improvements, and utilities as necessary. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | Wasilla | 2024-09-01 | CFHWY00723 | CFHWY00723 | 1703 | Chris L Bentz | (907)269-0652 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities.
Central Region | ADDLINFO |  | <a class=linkcopy href="https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/00880_PSE_Review_Plans_TAL.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> |  | (4) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.]; [on 2023.10.25 FEDNUM changed.] | ANC TAXIWAY R NORTH IMPROVEMENTS | Anchorage | 2024-03-01 | CFAPT00880
Central Region | ANTADVDT | 2024-04-01 | 2024-02-01 | (3) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.09.15 the ANTADVDT changed to April 2024.] | (6) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to April 2024.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Central Region | 2024-02-01 | CFHWY00523
Central Region | ANTADVDT | 2024-02-01 | 2024-05-01 |  | (2) [on 2023.03.15 project was added.]; [on 2023.07.14 FEDNUM changed.] | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | Big Lake | 2024-05-01 | CFHWY00392
Central Region | ANTADVDT | 2024-01-01 | 2023-12-01 | (2) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (4) [on 2023.05.15 project was added.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 ENGEST changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | SEWARD HWY: MP 75-90 ROAD&BRIDGE REHAB PHASE III | Anchorage | 2023-12-01 | Z581050000
Central Region | ANTADVDT | 2024-03-01 | 2024-05-01 |  | (4) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-05-01 | CFHWY01084
Central Region | ANTADVDT | 2024-05-01 | 2024-10-01 | (2) [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to May 2024.] | (6) [on 2022.11.17 project was added.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.07.14 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to May 2024.] | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | Wasilla | 2024-10-01 | CFHWY00622
Central Region | ANTADVDT | 2023-10-01 | 2023-11-01 |  | (2) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.] | ANC VISUAL PAGING SYSTEM INSTALLATION | Anchorage | 2023-11-01 | CFAPT00930
Central Region | ANTADVDT | 2023-10-01 | 2023-12-01 | (1) [on 2023.09.15 the ANTADVDT changed to October 2023.] | (2) [on 2023.08.21 project was added.]; [on 2023.09.15 the ANTADVDT changed to October 2023.] | DOT&PF Annex Building Earthquake Repairs | Anchorage | 2023-12-01 | NPFAC00547
Central Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 | (5) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.] | (6) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.] | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | Anchorage | 2024-06-01 | CFAPT00992
Central Region | ENGEST | Between $10,000,000 and $20,000,000 | Between $20,000,000 and $30,000,000 |  | (4) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.]; [on 2023.10.25 FEDNUM changed.] | ANC TAXIWAY R NORTH IMPROVEMENTS | Anchorage | 2024-03-01 | CFAPT00880
Central Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 |  | (4) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-05-01 | CFHWY01084
Central Region | ENGEST |  | Between $10,000,000 and $20,000,000 |  | (3) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.06.15 project was added.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-05-01 | CFAPT00572
Central Region | FEDNUM | 3-02-0468-00X-202X | 3-02-0468-003-2024 | (1) [on 2022.11.17 the ANTADVDT changed to August 2023.] | (4) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.04.14 project was added.] | CHEVAK AIRPORT REHABILITATION | Chevak | 2024-03-01 | Z537250000
Marine Highways | (DELETED) |  |  |  | (2) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.] | AMHS JNU AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | Juneau | 2024-01-01 | SAMHS00419 | SAMHS00419 | 933048 | Misty L Butler | (907)465-4414 | Make improvements to the AMHS Auke Bay Terminal East Berth. Work would include: Replacement of mooring dolphins, refurbish/replace transfer bridge and support float, install mechanical and electrical upgrades. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  |  | Richardson Highway MP 111.5 Turn Lanes | Glennallen | 2024-03-01 | NRMBS00553 | NRMBS00553 | N/A | Russell M Johnson | (907)451-5059 | Construct turn lanes at the Copper River Native Association Clinic entrance/exit located at Richardson Highway milepost 111.5. |  | Between $500,000 and $1,000,000
Northern Region | ADDED |  |  |  |  | Yankovich-Miller Hill Road Reconstruction and Multi-Use Path | Fairbanks | 2024-10-01 | NFHWY00139 | NFHWY00139 | 2378 | Ivet Hall | (907)451-5386 | Reconstruct Miller Hill Road and Yankovich Road, and improve existing separated multi-use path as needed. Project work will include roadside hardware, drainage improvements, and utilities. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDLINFO |  | 2-year construction, 2024-2025 |  | (1) [on 2023.08.21 project was added.] | PEARL CREEK ELEMENTARY SCHOOL ACCESS IMP AND PLUG-INS (CMAQ) | Fairbanks | 2024-05-01 | NFHWY00712
Northern Region | ANTADVDT | 2023-12-01 | 2024-03-01 | (1) [on 2023.08.21 the ANTADVDT changed to December 2023.] | (2) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | COPPER CENTER VISITOR CENTER PAVEMENT PRESERVATION | Copper Center | 2024-03-01 | NFHWY00720
Northern Region | ANTADVDT | 2024-01-01 | 2024-05-01 |  | (1) [on 2023.08.21 project was added.] | PEARL CREEK ELEMENTARY SCHOOL ACCESS IMP AND PLUG-INS (CMAQ) | Fairbanks | 2024-05-01 | NFHWY00712
Northern Region | ANTADVDT | 2023-11-01 | 2024-03-01 |  | (1) [on 2023.10.25 project was added.] | Richardson Highway MP 106.5-115 Resurfacing | Tazlina | 2024-03-01 | NFHWY00834
Northern Region | ANTADVDT | 2023-10-01 | 2023-11-01 | (8) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.] | (12) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2023-11-01 | Z768840000
Northern Region | ANTADVDT | 2023-10-01 | 2023-11-01 | (1) [on 2023.10.25 the ANTADVDT changed to October 2023.] | (4) [on 2022.11.17 project was added.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.10.25 the ANTADVDT changed to October 2023.] | Richardson Highway MP 351 Interchange | North Pole | 2023-11-01 | NFHWY00097
Northern Region | FEDNUM | 8650106 | 650106 | (1) [on 2023.08.21 the ANTADVDT changed to December 2023.] | (2) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | COPPER CENTER VISITOR CENTER PAVEMENT PRESERVATION | Copper Center | 2024-03-01 | NFHWY00720
Northern Region | FEDNUM | N/A | Pending |  | (1) [on 2023.10.25 project was added.] | Richardson Highway MP 106.5-115 Resurfacing | Tazlina | 2024-03-01 | NFHWY00834
Northern Region | PROJNAME | RICHARDSON HWY MP 106.5-115 RESURFACING | Richardson Highway MP 106.5-115 Resurfacing |  | (1) [on 2023.10.25 project was added.] | Richardson Highway MP 106.5-115 Resurfacing | Tazlina | 2024-03-01 | NFHWY00834
Southcoast Region | (DELETED) |  |  |  | (1) [on 2023.08.21 project was added.] | Sheldon Jackson Museum Door Replacement | Southcoast Region | 2024-06-01 | 25RC053622 | 25RC053622 | N/A | David R Hepler | (907)269-0815 | Replacing main entry doors on the Sheldon Jackson Muesum. |  | Less than $200,000
Southcoast Region | ADDLINFO | This project will encompass the reconstruction of the Apron and Taxiway F. Taxiways C & D are anticipated to be advertised under separate solicitation(s) in 2025 and 2026 subject to funding availability. | Reconstruct taxiway F and Apron. Replace edge lights, conduit, and cable. Install apron flood lighting along northern end; upgrade light bases and cabling. Significant drainage rehabilitation. | (1) [on 2023.10.25 the ANTADVDT changed to January 2024.] | (13) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | Kodiak | 2024-02-01 | SFAPT00227
Southcoast Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (1) [on 2023.10.25 the ANTADVDT changed to January 2024.] | (13) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | Kodiak | 2024-02-01 | SFAPT00227
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 | (10) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.] | (11) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2024-05-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2023-10-01 | 2023-11-01 | (4) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.] | (11) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to October 2023.] | WRG ZIMOVIA HWY ROCK FALL MITIGATION HSIP | Wrangell | 2023-11-01 | SFHWY00308
Southcoast Region | DESCRIPTION | ADQ airport ARFF Access improvements and Rehabilitation of Taxiway C, D and F. Project includes the non-private portion of the Apron. | Reconstruct taxiway F and Apron. Replace edge lights, conduit, and cable. Install apron flood lighting along northern end; upgrade light bases and cabling. Significant drainage rehabilitation. | (1) [on 2023.10.25 the ANTADVDT changed to January 2024.] | (13) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | Kodiak | 2024-02-01 | SFAPT00227
Southcoast Region | ENGEST | Between $10,000,000 and $20,000,000 | Between $20,000,000 and $30,000,000 | (1) [on 2023.10.25 the ANTADVDT changed to January 2024.] | (13) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | Kodiak | 2024-02-01 | SFAPT00227
Southcoast Region | PROJNAME | KDK: ADQ AIRPORT APRON AND TWY C, D AND F REHAB | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | (1) [on 2023.10.25 the ANTADVDT changed to January 2024.] | (13) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | Kodiak | 2024-02-01 | SFAPT00227