## 2023.12.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (3) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.11.15 the ANTADVDT changed to December 2023.] | (5) [on 2023.05.15 project was added.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 ENGEST changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.11.15 the ANTADVDT changed to December 2023.] | SEWARD HWY: MP 75-90 ROAD&BRIDGE REHAB PHASE III | Anchorage | 2023-12-01 | Z581050000 | Z581050000 | 0A31035 | Christina A Huber | (907)269-0572 | This federally funded project comprises pathway and parking lot work that was deleted from Phase II and the Portage Creek Multimodal Connector project. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (10) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (18) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2024-01-01 | CFAPT00882 | CFAPT00882 | 3-02-0013-XXX-2023 | Jennifer M Lombardo | (907)266-2731 | Rehabilitate the pavement of Aircraft and Lakeshore Dr from Voight Cir to the Lake Hood East property boundary south of runway 14/32. Project includes roadway reconditioning, structural section repairs, drainage improvements, and striping. | Rehabilitate Aircraft and Lakeshore Drive pavement. Includes drainage improvements. | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  | (4) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 PROJNAME changed.]; [on 2023.09.15 the project was removed.] | AMATS: DOWNTOWN TRAIL CONNECTION | Anchorage | 2024-11-01 | CFHWY00586 | CFHWY00586 | 1662 | Kristina H Busch | (907)269-0567 | Project will construct a connection between the Tony Knowles Coastal Trail to the Ship Creek Trail in downtown Anchorage. Major Project Elements include Bridge Work (Pedestrian), Roadside Hardware, Drainage Improvements, Intersection Improvements and ADA Improvements. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | ANC TAXILANE E IMPROVEMENTS | Anchorage | 2024-11-01 | CFAPT01002 | CFAPT01002 | N/A | Kim D Satterfield | (907)269-0623 | Rehabilitate Taxiway Echo from Taxiway Victor to Taxiway Lima. Improvements include: provide adequate typical section; evaluate taxiway safety area; replace lighting, markings, and signs; remove, replace, or modify existing storm drainage as needed; and adjust utilities as needed. |  | Pending
Central Region | ADDLINFO | PIH 75% Review Estimate | Pre PS&E review documents are located at the link below: <a class=linkcopy href="https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/00831%20ANC%20ATCT%20Replacement%20Parking%20PSE%20Review%20Plans_TAL.pdf">Preliminary Plans (~14 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> |  | (1) [on 2023.11.15 project was added.] | ANC ATCT REPLACEMENT PARKING | Anchorage | 2024-08-01 | CRMBS00831
Central Region | ADDLINFO | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/23-04-24_2022_FINAL_Safety%20Corridors%20Audit_DOTPF_DPS.pdf">Safety Corridors Audit 2022 (~10 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/23-04-24_2022_FINAL_Safety%20Corridors%20Audit_DOTPF_DPS.pdf">Safety Corridors Audit 2022 (~10 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/CFHWY00130A_DRAFT_RFP.pdf">DRAFT RFP (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | (3) [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | (8) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2024-01-01 | CFHWY00130A
Central Region | ANTADVDT | 2023-12-01 | 2024-01-01 | (5) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.] | (11) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2024-01-01 | Z512210000
Central Region | ANTADVDT | 2024-01-01 | 2024-03-01 | (1) [on 2023.10.25 the ANTADVDT changed to January 2024.] | (2) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | ANC RON 2 Rehabilitation | Anchorage | 2024-03-01 | CFAPT01104
Central Region | ANTADVDT | 2024-01-01 | 2024-03-01 |  | (1) [on 2023.10.25 project was added.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-03-01 | CFAPT00983A
Central Region | ANTADVDT | 2024-01-01 | 2024-03-01 | (4) [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (9) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2024-03-01 | CFHWY00943
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (5) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.] | (7) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.] | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | Anchorage | 2024-07-01 | CFAPT00992
Central Region | ANTADVDT | 2023-11-01 | 2023-12-01 | (1) [on 2023.11.15 the ANTADVDT changed to November 2023.] | (3) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | ANC VISUAL PAGING SYSTEM INSTALLATION | Anchorage | 2023-12-01 | CFAPT00930
Central Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (3) [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | (8) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2024-01-01 | CFHWY00130A
Central Region | DESCRIPTION | Design and construct improvements to the Seward Highway and Sterling Highway intersection to improve traffic flow and safety. Anticipated work includes road reconstruction, lighting, drainage, utility relocation, and avalanche hazard mitigation. This project will use the Progressive Design-Build (PDB) delivery method. The selected PDB team will provide design and support services to design the intersection improvements. The PDB team and the Contracting Agency will negotiate a Target Maximum Price for construction based on the preliminary design and, if agreement is reach, a design-build contract to finish the design and construct the project may be awarded. | UDPATE: This project will be delivered using a Design-Bid-Build (DBB) process, with an option to use CMGC later. Project will construct improvements to the Seward Highway and Sterling Highway intersection to improve traffic flow and safety. Anticipated work includes intersection reconstruction, lighting, drainage, utility relocation, and avalanche hazard mitigation. This project will be delivered using a traditional DBB process, with an option to award a CMGC contract later in the process. Future updates on this design contract will be available on the Tentative RFP Advertising Schedule: https://dot.alaska.gov/procurement/docs/CR-tent-adv-list.pdf If the Department chooses to use CMGC delivery, updates will be posted on this Tentative Advertising Schedule. | (4) [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (9) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2024-03-01 | CFHWY00943
Central Region | ENGEST |  | Pending |  | (1) [on 2023.11.15 project was added.] | ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTIO | Anchorage | 2024-03-01 | CFAPT00881
Central Region | ENGEST | Between $70,000,000 and $80,000,000 | Between $90,000,000 and $100,000,000 | (3) [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | (8) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2024-01-01 | CFHWY00130A
Central Region | ENGEST |  | Pending |  | (1) [on 2023.11.15 project was added.] | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | Wasilla | 2024-09-01 | CFHWY00723
Central Region | FEDNUM | N/A | 697DCK-22-T-00001 |  | (1) [on 2023.11.15 project was added.] | ANC ATCT REPLACEMENT PARKING | Anchorage | 2024-08-01 | CRMBS00831
Northern Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (9) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | (13) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2024-01-01 | Z768840000
Northern Region | ANTADVDT | 2023-11-01 | 2024-01-01 | (2) [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | (5) [on 2022.11.17 project was added.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | Richardson Highway MP 351 Interchange | North Pole | 2024-01-01 | NFHWY00097
Northern Region | ENGEST | Between $40,000,000 and $50,000,000 | Between $50,000,000 and $60,000,000 | (9) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | (13) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2024-01-01 | Z768840000
Northern Region | PROJNAME | Kotzebue Airport Crosswind Runway Imporvements | Kotzebue Airport Crosswind Runway Improvements |  | (4) [on 2023.06.15 project was added.]; [on 2023.09.15 ENGEST changed.]; [on 2023.09.15 FEDNUM changed.]; [on 2023.10.25 PROJNAME changed.] | Kotzebue Airport Crosswind Runway Improvements | Kotzebue | 2024-05-01 | NFAPT00600
Southcoast Region | (DELETED) |  |  | (5) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | (12) [on 2022.02.22 the ANTADVDT changed to November 2022.]; [on 2022.02.22 DESCRIPTION changed.]; [on 2022.04.15 DESCRIPTION changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 ENGEST changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.] | WRG ZIMOVIA HWY ROCK FALL MITIGATION HSIP | Wrangell | 2023-11-01 | SFHWY00308 | SFHWY00308 | 3262 | Nathan A Purves | (907)465-4521 | Perform slope stabilization and mitigation work at two rock fall sites on Zimovia Highway in Wrangell, Alaska. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | Kalsin Bay Maintenance Station - Phase 2 | Southcoast Region | 2024-03-01 | CPFAC00080 | CPFAC00080 | N/A | Eric F Hershey | (907)269-5572 | The Kalsin Bay Maintenance Station was replaced in 2019. The reconstructed facility is a 4100 SQ. Ft. steel frame building with three maintenance bays and an adjoining office, break room, and bathroom. Phase 2 consists of miscellaneous remaining scope required for full functionality of the maintenance station, including but are not limited to, concrete apron replacement, building envelope upgrades, domestic water filtration, wastewater holding tank modifications, fuel tank relocation, provision of an emergency generator, and other mechanical and electrical upgrades. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  | (4) [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 the ANTADVDT changed to February 2024.] | (10) [on 2022.09.13 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the project was removed.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2024-11-01 | SFHWY00326 | SFHWY00326 | 3265 | Brett M Wells | (907)465-1607 | Replace two damaged culverts with new Aquatic Organism Passage structures across Trout Creek and Little Trout Creek in Cold Bay, AK. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  | (2) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.] | HNS LUTAK ROAD 437114 - DEC 20 SE PR | Haines | 2024-11-01 | SDRER00448 | SDRER00448 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Damage Inventory Numbers 461224, 461227, 461237 - 461239, 461243 - 461250, 784625 - 784632, and 786036. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Lutak Road. This project is funded by FEMA. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDLINFO | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise. New draft plans were posted on 11-22-2023 | (2) [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | (8) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-03-01 | Z686060000
Southcoast Region | ANTADVDT | 2024-01-01 | 2024-03-01 | (5) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (10) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2024-03-01 | SFHWY00103
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 | (2) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | (4) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | JNU WAYDELICH CREEK: UPPER WALL REPAIRS - DEC 20 SE PR | Juneau | 2024-05-01 | SFHWY00414
Southcoast Region | ANTADVDT | 2023-11-01 | 2023-12-01 | (10) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | (14) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.10.25 FEDNUM changed.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2023-12-01 | SFAPT00212
Southcoast Region | PHONENUM | (907)465-8189 | (907)465-2393 | (1) [on 2023.10.25 the ANTADVDT changed to May 2024.] | (4) [on 2023.05.15 project was added.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to May 2024.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2024-05-01 | SFHWY00312
Southcoast Region | PROJMAN | Loren K Gehring | Gregory K Lockwood | (1) [on 2023.10.25 the ANTADVDT changed to May 2024.] | (4) [on 2023.05.15 project was added.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to May 2024.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2024-05-01 | SFHWY00312