## 2024.01.16 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (1) [on 2023.11.15 project was added.] | TALKEETNA AIRPORT LIGHTING IMPROVEMENTS | Talkeetna | 2024-04-01 | CFAPT01020 | CFAPT01020 | N/A | Kim D Satterfield | (907)269-0623 | Reconstruct the runway (1-19) lighting and taxiway (A, B, C, D, E, F, and G) lighting at Talkeetna Airport. Improvements also include replacing the wind cones, rotating beacon, and threshold markers. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (5) [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | (11) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2023.12.15 DESCRIPTION changed.] | Seward Hwy Sterling Hwy Intersection Improvements Progressive Design Build | Cooper Landing | 2024-03-01 | CFHWY00943 | CFHWY00943 | 0A32025 | Julia R Hanson | (907)269-0753 | UDPATE: This project will be delivered using a Design-Bid-Build (DBB) process, with an option to use CMGC later. Project will construct improvements to the Seward Highway and Sterling Highway intersection to improve traffic flow and safety. Anticipated work includes intersection reconstruction, lighting, drainage, utility relocation, and avalanche hazard mitigation. This project will be delivered using a traditional DBB process, with an option to award a CMGC contract later in the process. Future updates on this design contract will be available on the Tentative RFP Advertising Schedule: https://dot.alaska.gov/procurement/docs/CR-tent-adv-list.pdf If the Department chooses to use CMGC delivery, updates will be posted on this Tentative Advertising Schedule. |  | Between $20,000,000 and $30,000,000
Central Region | ADDED |  |  |  |  | AKUTAN GENERATOR SYSTEM UPGRADE DESIGN-BUILD | Akutan | 2024-01-01 | SFAPT00539 | SFAPT00539 | AIP 3-02-0005-009-2024 | Levi D Overbeck | (907)269-0617 | This federally funded contract requires the Contractor to provide the necessary design and construction services, as required, to replace the failing generators at the Akutan Airport Snow Removal Equipment Building (SREB). |  | Between $500,000 and $1,000,000
Central Region | ADDLINFO | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/23-04-24_2022_FINAL_Safety%20Corridors%20Audit_DOTPF_DPS.pdf">Safety Corridors Audit 2022 (~10 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/CFHWY00130A_DRAFT_RFP.pdf">DRAFT RFP (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/23-04-24_2022_FINAL_Safety%20Corridors%20Audit_DOTPF_DPS.pdf">Safety Corridors Audit 2022 (~10 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/CFHWY00130A_DRAFT_RFP.pdf">DRAFT RFP (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Pre-RFP_Meeting_Invite.pdf">Pre RFP Meeting Invite </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling Safety PDB Pre-RFP Meeting.ics">Pre-RFP Meeting iCal Invite </a> | (4) [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | (11) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 ADDLINFO changed.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2023.12.15 ENGEST changed.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2024-01-01 | CFHWY00130A
Central Region | ANTADVDT | 2023-12-01 | 2024-03-01 | (1) [on 2022.11.17 the ANTADVDT changed to July 2023.] | (7) [on 2022.04.15 project was added.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.] | AMATS: EAGLE RIVER LOOP RD - EAGLE RIVER RD TO OLD GLENN HWY | Eagle River | 2024-03-01 | CFHWY00731
Central Region | ANTADVDT | 2023-12-01 | 2024-01-01 | (2) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.] | (4) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.] | ANC VISUAL PAGING SYSTEM INSTALLATION | Anchorage | 2024-01-01 | CFAPT00930
Central Region | ANTADVDT | 2023-12-01 | 2024-01-01 | (2) [on 2023.09.15 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to December 2023.] | (3) [on 2023.08.21 project was added.]; [on 2023.09.15 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to December 2023.] | DOT&PF Annex Building Earthquake Repairs | Anchorage | 2024-01-01 | NPFAC00547
Central Region | ANTADVDT | 2023-12-01 | 2024-01-01 | (5) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.] | (8) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2024-01-01 | 25RC053608
Central Region | ANTADVDT | 2023-12-01 | 2024-03-01 | (1) [on 2022.11.17 the ANTADVDT changed to July 2023.] | (5) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.] | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | Eagle River | 2024-03-01 | CFHWY00621
Central Region | ANTADVDT | 2024-02-01 | 2024-04-01 | (4) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.] | (7) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Central Region | 2024-04-01 | CFHWY00523
Central Region | ANTADVDT | 2024-01-01 | 2024-03-01 | (8) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.] | (13) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2024-03-01 | CSAPT00931
Central Region | ANTADVDT | 2024-01-01 | 2024-03-01 | (2) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (7) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-03-01 | CFHWY01083
Central Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (6) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | (12) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2024-02-01 | Z512210000
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (1) [on 2023.08.21 project was added.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-04-01 | CFAPT01136
Central Region | ANTADVDT | 2024-09-01 | 2024-08-01 |  | (2) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.] | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | Wasilla | 2024-08-01 | CFHWY00723
Central Region | DESCRIPTION | This project will use the Progressive Design-Build (PDB) delivery method. The selected PDB team will provide design and support services to design a four-lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed federally funded project will improve safety and reduce congestion. The PDB team and the Contracting Agency will negotiate a Target Maximum Price for construction based on the preliminary design and, if agreement is reached, a design-build contract to finish the design and construct the project may be awarded. | Update: The Contracting Agency will host a pre-RFP meeting on Dec. 22, 2023, at 9am via Microsoft Teams. Details are in the Pre-RFP Meeting Invite posted below. Contact the Design Manager (Julia Hanson) if you have trouble with that attachment or to request an iCal invite. This project will use the Progressive Design-Build (PDB) delivery method. The selected PDB team will provide design and support services to design a four-lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed federally funded project will improve safety and reduce congestion. The PDB team and the Contracting Agency will negotiate a Target Maximum Price for construction based on the preliminary design and, if agreement is reached, a design-build contract to finish the design and construct the project may be awarded. | (4) [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | (11) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 ADDLINFO changed.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2023.12.15 ENGEST changed.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2024-01-01 | CFHWY00130A
Central Region | DESCRIPTION | Reconstruct approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, new structural section, drainage improvements and pavement markings. | Rehabilitate approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, new structural section, drainage improvements and pavement markings. | (6) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | (8) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | ANC TAXIWAY KILO TUG ROAD REHABILITATION | Anchorage | 2024-07-01 | CFAPT00992
Central Region | ENGEST | Between $200,000 and $500,000 | Less than $200,000 | (5) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.] | (8) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2024-01-01 | 25RC053608
Central Region | ENGEST | Between $500,000 and $1,000,000 | Between $1,000,000 and $2,500,000 |  | (1) [on 2023.08.21 project was added.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-04-01 | CFAPT01136
Central Region | ENGEST | Pending | Between $20,000,000 and $30,000,000 |  | (1) [on 2023.12.15 project was added.] | ANC TAXILANE E IMPROVEMENTS | Anchorage | 2024-11-01 | CFAPT01002
Central Region | ENGEST | Pending | Between $10,000,000 and $20,000,000 |  | (2) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.] | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | Wasilla | 2024-08-01 | CFHWY00723
Central Region | FEDNUM | N/A | 3-02-0016-XXX-2024 | (6) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | (8) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | ANC TAXIWAY KILO TUG ROAD REHABILITATION | Anchorage | 2024-07-01 | CFAPT00992
Central Region | PROJNAME | ANC TAXIWAY KILO TUG ROAD RECONSTRUCTION | ANC TAXIWAY KILO TUG ROAD REHABILITATION | (6) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | (8) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | ANC TAXIWAY KILO TUG ROAD REHABILITATION | Anchorage | 2024-07-01 | CFAPT00992
Central Region | PROJNAME | HSIP: PALMER-FISHHOOK ROAD & TRUNK ROAD ROUNDABOUT | HSIP: PALMER-FISHHOOK RD & TRUNK RD ROUNDABOUT |  | (3) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2023.08.21 project was added.] | HSIP: PALMER-FISHHOOK RD & TRUNK RD ROUNDABOUT | Palmer | 2024-07-01 | CFHWY00829
Northern Region | ADDED |  |  |  |  | Cowles Street Reconstruction - Airport Way to East Cowles | Fairbanks | 2024-04-01 | NFHWY00883 | NFHWY00883 | N/A | Ivet Hall | (907)451-5386 | Reconstruct Cowles Street from Airport Way through East Cowles Street. Project work will include roadside hardware, drainage improvements, intersection improvements, ADA improvements and utilities. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  | (3) [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | (11) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.09.15 the project was removed.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2024-12-01 | Z631860000 | Z631860000 | 713010 | Russell M Johnson | (907)451-5059 | Reconstruct the Richardson Highway between MP 167 and 173. Project includes roadside hardware, drainage improvements and utility relocations. | Reconstruct the Richardson Highway between mileposts 167-173. | Between $30,000,000 and $40,000,000
Northern Region | ANTADVDT | 2023-12-01 | 2024-01-01 | (1) [on 2023.10.25 the ANTADVDT changed to December 2023.] | (6) [on 2023.08.21 project was added.]; [on 2023.09.15 FEDNUM changed.]; [on 2023.09.15 LOCATION changed.]; [on 2023.09.15 PROJNAME changed.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.10.25 PROJNAME changed.] | Chena Ridge Road Resurfacing - Kentshire Drive to Friar's Way | Fairbanks | 2024-01-01 | NFHWY00838
Northern Region | ANTADVDT | 2023-12-01 | 2024-04-01 |  | (2) [on 2023.02.24 project was added.]; [on 2023.06.15 PROJNAME changed.] | Seppala Drive Upgrade | Nome | 2024-04-01 | Z620030000
Northern Region | ANTADVDT | 2024-01-01 | 2024-04-01 |  | (2) [on 2023.08.21 project was added.]; [on 2023.10.25 DESCRIPTION changed.] | Alaska Highway MP 1235-1268 Rehabilitation (Const MP 1252-1268) | Northway | 2024-04-01 | Z607520000
Northern Region | ANTADVDT | 2024-01-01 | 2024-02-01 |  | (5) [on 2023.06.15 project was added.]; [on 2023.07.14 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.07.14 LOCATION changed.]; [on 2023.07.14 PROJNAME changed.] | Denali Highway Culvert Replacement | Cantwell | 2024-02-01 | NFHWY00701
Northern Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (1) [on 2023.03.15 the ANTADVDT changed to January 2024.] | (8) [on 2022.06.15 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.02.24 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.03.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.10.25 LOCATION changed.] | Elliott Highway MP 18 - 29 Resurfacing | Fox | 2024-02-01 | NFHWY00588
Northern Region | FEDNUM | 650106 | 8650106 | (2) [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.11.15 the ANTADVDT changed to March 2024.] | (4) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.11.15 the ANTADVDT changed to March 2024.]; [on 2023.11.15 FEDNUM changed.] | Copper Center Visitor Center Pavement Preservation | Copper Center | 2024-03-01 | NFHWY00720
Northern Region | LOCATION | Glennallen | Tazlina |  | (1) [on 2023.11.15 project was added.] | Richardson Highway MP 111.5 Turn Lanes | Tazlina | 2024-03-01 | NRMBS00553
Northern Region | PHONENUM | (907)451-5359 | (907)451-2281 |  | (2) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.] | HSIP: City of Fairbanks Systemic Signal Upgrades | Fairbanks | 2024-03-01 | NFHWY00592
Northern Region | PHONENUM | (907)451-5359 | (907)451-2281 |  | (2) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.] | HSIP: Northern Region Systemic Signal Upgrades | Fairbanks North Star Borough | 2024-03-01 | NFHWY00531
Northern Region | PROJMAN | Carl F Heim | Ethan E Graetz |  | (2) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.] | HSIP: City of Fairbanks Systemic Signal Upgrades | Fairbanks | 2024-03-01 | NFHWY00592
Northern Region | PROJMAN | Carl F Heim | Ethan E Graetz |  | (2) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.] | HSIP: Northern Region Systemic Signal Upgrades | Fairbanks North Star Borough | 2024-03-01 | NFHWY00531
Northern Region | PROJNAME | Alaska Hwy MP 1235-1268 Rehabilitation (Const MP 1252-1268) | Alaska Highway MP 1235-1268 Rehabilitation (Const MP 1252-1268) |  | (2) [on 2023.08.21 project was added.]; [on 2023.10.25 DESCRIPTION changed.] | Alaska Highway MP 1235-1268 Rehabilitation (Const MP 1252-1268) | Northway | 2024-04-01 | Z607520000
Northern Region | PROJNAME | COPPER CENTER VISITOR CENTER PAVEMENT PRESERVATION | Copper Center Visitor Center Pavement Preservation | (2) [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.11.15 the ANTADVDT changed to March 2024.] | (4) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.11.15 the ANTADVDT changed to March 2024.]; [on 2023.11.15 FEDNUM changed.] | Copper Center Visitor Center Pavement Preservation | Copper Center | 2024-03-01 | NFHWY00720
Southcoast Region | (DELETED) |  |  | (1) [on 2023.10.25 the ANTADVDT changed to August 2024.] | (2) [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to August 2024.] | SGY, HNH, PSG ROADWAY & CULVERTS - DEC 20 SE PR | Southcoast Region | 2024-08-01 | SFHWY00447 | SFHWY00447 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2020 01 HNH001, AK 2020 01 HNH002, AK 2021 01 PTG002, AK 2021 01 PTG003, and AK 2021 01 SGY001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites in Hoonah, Petersburg & Skagway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (8) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.06.15 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 the project was removed.] | CRAIG ADA IMPROVEMENTS | Craig | 2024-12-01 | SFHWY00377 | SFHWY00377 | 3274 | Bran P Pollard | (907)465-4526 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  |  |  | KOKHANOK AIRPORT RESURFACING AND FENCING | Kokhanok | 2024-12-01 | SFAPT00361 | SFAPT00361 | N/A | David B Epstein | (907)465-4483 | Resurfacing and grading the runway, regrading ditches and safety areas, replacement of inoperative culverts and drainage repairs. Installation of new AWOS. CC 24300447 LC 33008462 Phase: T02FA1 LC & CC Description: SFAPT00361-2P-Resurf. |  | Between $5,000,000 and $10,000,000
Southcoast Region | ADDED |  |  |  |  | FFY24 GUSTAVUS PAVEMENT MARKINGS/LOADER | Gustavus | 2024-03-01 | SFAPT00478 | SFAPT00478 | N/A | Spencer M Gates | (907)465-1014 | Apply new pavement markings, Replace snow removal equipment. |  | Pending
Southcoast Region | ADDED |  |  |  |  | FFY24 KTN PAVEMENT MARKINGS/CRACKSEAL | Ketchikan | 2024-03-01 | SFAPT00467 | SFAPT00467 | N/A | Spencer M Gates | (907)465-1014 | Pre Grant Apply new pavement marking and crackseal |  | Pending
Southcoast Region | ADDED |  |  |  |  | FFY24 PSG PAVEMENT MARKINGS/LOADER | Petersburg | 2024-03-01 | SFAPT00469 | SFAPT00469 | N/A | Spencer M Gates | (907)465-1014 | Apply new pavement markings, Replace snow removal Equipment CC 24300448 LC 33008472 Phase: T02FA1 CC&LC Description: SFAPT00469-2P-Pavement |  | Pending
Southcoast Region | ADDED |  |  |  |  | FFY24 Southeast District Highway Painting | Statewide | 2024-03-01 | SFHWY00556 | SFHWY00556 | N/A | David B Epstein | (907)465-4483 | Narrative/Scope(if not FHWA)/Explanation for other changes: (New Project - Pre Grant) This project consists of applying new paint and beads to all striping, symbols, crosswalks, and stop bars on state owned roads through out the Southeast District. Any necessary training for State personnel, sweeping, flushing, and any other required pavement preparation where new paint is to be applied. Locations include Juneau, Ketchikan, Klawock, Petersburg, Wrangell, Yakutat. 83% of work is Non-NHS. 17% of work is NHS. |  | Pending
Southcoast Region | ADDED |  |  |  |  | FFY24 WRG SURFACE PAVEMENT MARKINGS & SRE | Wrangell | 2024-03-01 | SFAPT00468 | SFAPT00468 | N/A | Spencer M Gates | (907)465-1014 | Pre Grant apply new pavement markings and crackseal. Replace snow removal equipment |  | Pending
Southcoast Region | ADDED |  |  |  |  | FFY24 YAK PAVEMENT MARKINGS | Yakutat | 2024-03-01 | SFAPT00474 | SFAPT00474 | N/A | Spencer M Gates | (907)465-1014 | Apply new pavement markings |  | Pending
Southcoast Region | ANTADVDT | 2024-04-01 | 2024-06-01 | (1) [on 2023.10.25 the ANTADVDT changed to April 2024.] | (3) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to April 2024.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-06-01 | SFHWY00481
Southcoast Region | ANTADVDT | 2024-04-01 | 2024-08-01 | (1) [on 2023.06.15 the ANTADVDT changed to April 2024.] | (4) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2024-08-01 | SFHWY00438
Southcoast Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (2) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.] | (4) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-09-01 | SFHWY00446
Southcoast Region | ANTADVDT | 2023-12-01 | 2024-01-01 | (11) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.] | (15) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.12.15 the ANTADVDT changed to December 2023.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2024-01-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2024-02-01 | 2024-06-01 | (1) [on 2023.07.14 the ANTADVDT changed to February 2024.] | (12) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-06-01 | SFAPT00178
Southcoast Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (3) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.] | (4) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2024-08-01 | SDRER00436
Southcoast Region | ANTADVDT | 2024-07-01 | 2024-12-01 | (1) [on 2023.10.25 the ANTADVDT changed to July 2024.] | (2) [on 2023.06.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to July 2024.] | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2024-12-01 | SDRER00445
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-09-01 |  | (2) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-09-01 | SFHWY00440
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (4) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.] | (11) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-04-01 | SFAPT00412
Southcoast Region | DESCRIPTION | This project will construct permanent repairs (PR) to the upper portion of the Waydelich Creek retaining wall damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK2021-1 JNS003. Repairs may include, but are not limited to, asphalt, embankment, geotextile, concrete, steel reinforcement, riprap, drainage, roadside hardware, and utilities. | This project will construct permanent repairs (PR) to the upper & lower portion of the Waydelich Creek retaining wall. The upper wall was damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK2021-1 JNS003. Repairs may include, but are not limited to, asphalt, embankment, geotextile, concrete, steel reinforcement, riprap, drainage, roadside hardware, and utilities. Phase code is T02015. The lower wall has years of deterioration & requires additional work to bring the full wall up to seismic code & extend the service life another 40 years. This portion of the project has PM-funding. Phase code is T02A15. | (3) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.] | JNU Waydelich Creek: Upper & Lower Wall Repairs | Juneau | 2024-05-01 | SFHWY00414
Southcoast Region | ENGEST | Between $200,000 and $500,000 | Between $1,000,000 and $2,500,000 | (3) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.] | JNU Waydelich Creek: Upper & Lower Wall Repairs | Juneau | 2024-05-01 | SFHWY00414
Southcoast Region | PHONENUM | (907)465-2393 | (907)465-4526 | (1) [on 2023.07.14 the ANTADVDT changed to February 2024.] | (12) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-06-01 | SFAPT00178
Southcoast Region | PROJMAN | Gregory K Lockwood | Bran P Pollard | (1) [on 2023.07.14 the ANTADVDT changed to February 2024.] | (12) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-06-01 | SFAPT00178
Southcoast Region | PROJNAME | JNU WAYDELICH CREEK: UPPER WALL REPAIRS - DEC 20 SE PR | JNU Waydelich Creek: Upper & Lower Wall Repairs | (3) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.] | JNU Waydelich Creek: Upper & Lower Wall Repairs | Juneau | 2024-05-01 | SFHWY00414