## 2024.02.14 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (3) [on 2023.09.15 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | (4) [on 2023.08.21 project was added.]; [on 2023.09.15 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | DOT&PF Annex Building Earthquake Repairs | Anchorage | 2024-01-01 | NPFAC00547 | NPFAC00547 | N/A | Vadim Belozertsev | (907)269-0879 | Project includes replacement of the West wing and repairs of other damage at the DOT&PF Annex Building, resulting from the November 30, 2018 earthquake. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (6) [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | (10) [on 2023.02.24 project was added.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to June 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.01.16 ENGEST changed.] | Mt. Edgecumbe H.S. Building 295 Heritage Hall Window Upgrades | City & Borough Of Sitka | 2024-01-01 | 25RC053608 | 25RC053608 | N/A | Lance Mearig | (907)419-4903 | This State funded project will replace the windows at Building 295 Heritage Hall at Mt. Edgeucmbe High School, Sitka, Alaska. |  | Less than $200,000
Central Region | (DELETED) |  |  | (4) [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | (13) [on 2023.06.15 project was added.]; [on 2023.07.14 ADDLINFO changed.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.08.21 ADDLINFO changed.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 ADDLINFO changed.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2023.12.15 ENGEST changed.]; [on 2024.01.16 ADDLINFO changed.]; [on 2024.01.16 DESCRIPTION changed.] | Sterling Safety Corridor Improvements MP 82.5 to 94 Progressive Design Build | Sterling | 2024-01-01 | CFHWY00130A | CFHWY00130A | 0A33026 | Julia R Hanson | (907)269-0753 | Update: The Contracting Agency will host a pre-RFP meeting on Dec. 22, 2023, at 9am via Microsoft Teams. Details are in the Pre-RFP Meeting Invite posted below. Contact the Design Manager (Julia Hanson) if you have trouble with that attachment or to request an iCal invite. This project will use the Progressive Design-Build (PDB) delivery method. The selected PDB team will provide design and support services to design a four-lane divided highway from approximately Sterling Highway MP 82.5 to 94. The proposed federally funded project will improve safety and reduce congestion. The PDB team and the Contracting Agency will negotiate a Target Maximum Price for construction based on the preliminary design and, if agreement is reached, a design-build contract to finish the design and construct the project may be awarded. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00130/Environmental_Assessment.pdf">Environmental Assessment (~30 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Final%20Environmental%20Assessment%20Appendices.pdf">Final Environmental Assessment Appendices (~270 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling_Hwy_CAD.zip">Preliminary Design CAD Files (.zip ~26 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Historical_Geotech_Reports.zip">Historical Geotech Reports (.zip ~77 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/00130_Geotech_Dec2022.pdf">Project Geotechnical Report, Dec. 2022 (~16 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/23-04-24_2022_FINAL_Safety%20Corridors%20Audit_DOTPF_DPS.pdf">Safety Corridors Audit 2022 (~10 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/CFHWY00130A_DRAFT_RFP.pdf">DRAFT RFP (~4 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Pre-RFP_Meeting_Invite.pdf">Pre RFP Meeting Invite </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00130/Sterling Safety PDB Pre-RFP Meeting.ics">Pre-RFP Meeting iCal Invite </a> | Between $90,000,000 and $100,000,000
Central Region | (DELETED) |  |  | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (3) [on 2023.03.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.] | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | Big Lake | 2024-05-01 | CFHWY00392 | CFHWY00392 | 1686 | Alex L Read | (907)269-0641 | Pavement preservation, roadside hardware, structural improvement in limited areas, minor drainage and/or safety improvements, utility adjustment/relocation, signing and striping. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  | (5) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the project was removed.] | ANC TAXILANE R SOUTH REHABILITATION | Anchorage | 2025-01-01 | CFAPT00758 | CFAPT00758 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate the structural taxilane pavement, remove and replace airfield lighting and restripe. | Rehabilitate asphalt. | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  | (4) [on 2022.05.16 project was added.]; [on 2022.07.12 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.10.25 the project was removed.] | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | Statewide | 2025-01-01 | CFHWY00394 | CFHWY00394 | 0A15039 | Kristina H Busch | (907)269-0567 | Resurface the Glenn Highway from Kings River bridge to Cascade. Additional improvements may include bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities as necessary. Project construction may be phased. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  | (10) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.] | (19) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.03.15 the ANTADVDT changed to October 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.03.15 PROJNAME changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the ANTADVDT changed to January 2023.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.11.17 DESCRIPTION changed.]; [on 2022.12.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.01.17 ENGEST changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 FEDNUM changed.]; [on 2023.05.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the project was removed.] | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | Anchorage | 2025-01-01 | CFAPT00882 | CFAPT00882 | 3-02-0013-XXX-2024 | Jennifer M Lombardo | (907)266-2731 | Rehabilitate the pavement of Aircraft and Lakeshore Dr from Voight Cir to the Lake Hood East property boundary south of runway 14/32. Project includes roadway reconditioning, structural section repairs, drainage improvements, and striping. | Rehabilitate Aircraft and Lakeshore Drive pavement. Includes drainage and safety improvements. | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | OLD GLENN HWY OUTER SPRINGER LP & INNER SPRINGER LP PAVEMENT | Palmer | 2025-01-01 | CFHWY00887 | CFHWY00887 | 1748 | Kristina H Busch | (907)269-0567 | This pavement preservation project will resurface Old Glenn Hwy, Outer Springer Loop and Inner Springer Loop. Additional improvements may also include: utility relocation, roadsidehardward, vegetation clearing, dig-outs, drainage, signs, striping, bridge repairs, ADA improvements, and safety improvements. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2024-03-01 | CFAPT00993A | CFAPT00993A | AIP 3-02-0016-228-2024 | Kim D Satterfield | (907)269-0623 | This federally funded project will rehabilitate approximately 6,000 feet of water pipe around the North Terminal, C Concourse, A Concourse, and Old Airfield Maintenance (OAM) building at the Ted Stevens Anchorage International Airport. Improvements will also include hydrant replacements, valve replacements, and grouting a decommissioned water pipe segment under the South Terminal. | <a class=linkcopy href=https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/9_00993%20ANC%20Terminal%20Water%20Main%20Improvements%20-%20TAL.pdf>Preliminary Plans (~21 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | CR24 Anchorage District NHS Preventative Maintenance CFHWY01137 / 0001786 | Anchorage | 2024-03-01 | 24-25-1-002 | 24-25-1-002 | N/A | Vernon S Vreeland | (907)269-0778 | This contract shall provide for all materials, equipment, supervision, labor, maintenance, fuel, mobilization, and demobilization necessary to clear brush on the State of Alaska Highway facilities within the Anchorage Maintenance District, on an as-needed basis as directed by the DOT&PF Representative. The State may opt to offer renewal of this contract for up to four (4) additional one (1) year period. |  | Between $200,000 and $500,000
Central Region | ADDED |  |  |  |  | CR24 PENINSULA DISTRICT NHS PREVENTATIVE MAINTENANCE CFHWY01139 / 0001787 CR24 PENINSULA DISTRICT NON-NHS PREVENTATIVE MAINTENANCE CFHWY01142 / 0001790 | Soldotna | 2024-03-01 | 24-25-1-001 | 24-25-1-001 | N/A | Joshua D Stuckey | (907)269-0751 | This federally funded contract is for stormwater infrastructure cleaning services. Work includes cleaning of curb inlets, catch basins, catch basin manholes, manholes, field inlets, lift stations, storm drain pipes and culvert pipes along State of Alaska roadways located in the Kenai Peninsula Maintenance District. |  | Between $500,000 and $1,000,000
Central Region | ANTADVDT | 2024-04-01 | 2024-06-01 |  | (1) [on 2023.08.21 project was added.] | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | Hope | 2024-06-01 | CFHWY00928
Central Region | ANTADVDT | 2024-02-01 | 2024-10-01 | (8) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (11) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2024-10-01 | CFHWY00260
Central Region | ANTADVDT | 2024-02-01 | 2024-03-01 | (9) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (12) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2024-03-01 | CFHWY00395
Central Region | ANTADVDT | 2024-02-01 | 2024-05-01 | (3) [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (10) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2024-05-01 | CFHWY00883
Central Region | ANTADVDT | 2024-01-01 | 2024-02-01 |  | (1) [on 2024.01.16 project was added.] | AKUTAN GENERATOR SYSTEM UPGRADE DESIGN-BUILD | Akutan | 2024-02-01 | SFAPT00539
Central Region | ANTADVDT | 2024-01-01 | 2024-02-01 |  | (1) [on 2023.11.15 project was added.] | ANC Job Order Construction Contract (RFP 2024) | Anchorage | 2024-02-01 | CSAPT01156
Central Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (3) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | (5) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | Anchorage | 2024-02-01 | CFAPT00930
Central Region | ANTADVDT | 2024-07-01 | 2025-01-01 | (6) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | (11) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 FEDNUM changed.]; [on 2024.01.16 PROJNAME changed.] | ANC TAXIWAY KILO TUG ROAD REHABILITATION | Anchorage | 2025-01-01 | CFAPT00992
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (9) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | (14) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2024-04-01 | CSAPT00931
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (1) [on 2023.11.15 project was added.] | ANC FIRING RANGE MAINTENANCE | Anchorage | 2024-04-01 | CSAPT01152
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (1) [on 2023.09.15 project was added.] | ANC OLD AFM GATE | Anchorage | 2024-04-01 | CSAPT01150
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (2) [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | (3) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | ANC RON 2 Rehabilitation | Anchorage | 2024-04-01 | CFAPT01104
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (3) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | (8) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-04-01 | CFHWY01083
Central Region | ANTADVDT | 2024-05-01 | 2024-06-01 |  | (4) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.11.15 ENGEST changed.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-06-01 | CFAPT00572
Central Region | DESCRIPTION | Rehabilitate 3,300 feet of Postmark Drive from Rockwell Avenue to Dehavilland Avenue. Project includes pavement planning, paving, and striping. | Rehabilitate Postmark Drive from Rockwell Avenue to Dehavilland Avenue. Project includes pavement planning, paving, and striping. | (1) [on 2023.10.25 the ANTADVDT changed to April 2024.] | (3) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2023.10.25 ENGEST changed.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-04-01 | CSAPT01146
Central Region | DESCRIPTION | Rehabilitate approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, new structural section, drainage improvements and pavement markings. | Rehabilitate approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, pavement rehabilitation, drainage improvements and pavement markings. | (6) [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.12.15 the ANTADVDT changed to July 2024.] | (11) [on 2022.08.14 project was added.]; [on 2022.09.13 the ANTADVDT changed to May 2023.]; [on 2022.11.17 the ANTADVDT changed to June 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to June 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2023.12.15 the ANTADVDT changed to July 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 FEDNUM changed.]; [on 2024.01.16 PROJNAME changed.] | ANC TAXIWAY KILO TUG ROAD REHABILITATION | Anchorage | 2025-01-01 | CFAPT00992
Central Region | DESCRIPTION | Project will include: 1) constructing a new vehicle access control gate at AFM West; 2) install head bolt outlets (HBO) at the TW A and DeHavilland Avenue snow disposal sites; and 3) re-grade the tug road ditch south of the Trans-northern lease lot. | Project will include constructing a new vehicle access control gate at AFM West and install head bolt outlets (HBO) at the TW A and DeHavilland Avenue snow disposal sites. | (9) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | (14) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | Anchorage | 2024-04-01 | CSAPT00931
Central Region | DESCRIPTION | Rehabilitate the runway, taxiway, safety areas, apron, and access road. Place and compact CASC, apply dust palliative, and replace the airport lighting system. | Rehabilitate the runway, taxiway, safety areas, apron, and access road. Widen and extend RSA to meet ADG II standards. Place and compact CASC, apply dust palliative. Reconstruct the airfield lighting system, primary wind cone, and supplemental wind cone. Replace rotating beacon on a tip-down pole. Relevel SREB. Construct barge landing. |  | (4) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.11.15 ENGEST changed.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-06-01 | CFAPT00572
Central Region | ENGEST | Pending | Between $10,000,000 and $20,000,000 |  | (2) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.] | ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTIO | Anchorage | 2024-03-01 | CFAPT00881
Central Region | PHONENUM | (907)269-0652 | (907)707-1912 | (1) [on 2024.01.16 the ANTADVDT changed to August 2024.] | (4) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.01.16 ENGEST changed.] | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | Wasilla | 2024-08-01 | CFHWY00723
Central Region | PHONENUM | (907)269-0693 | (907)269-0657 | (8) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (11) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2024-10-01 | CFHWY00260
Central Region | PHONENUM | (907)269-0693 | (907)269-0657 | (9) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (12) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2024-03-01 | CFHWY00395
Central Region | PHONENUM | (907)269-0652 | (907)707-1912 | (7) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to February 2024.] | (13) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to February 2024.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2024-02-01 | Z512210000
Central Region | PHONENUM | (907)269-0652 | (907)707-1912 | (3) [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2023.11.15 the ANTADVDT changed to October 2024.] | (7) [on 2022.11.17 project was added.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.07.14 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2023.11.15 the ANTADVDT changed to October 2024.] | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | Wasilla | 2024-10-01 | CFHWY00622
Central Region | PROJMAN | Galen K Jones | Travis W Holmes |  | (1) [on 2023.08.21 project was added.] | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | Hope | 2024-06-01 | CFHWY00928
Central Region | PROJMAN | Cynthia L Ferguson | Noah C King | (8) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (11) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2024-10-01 | CFHWY00260
Central Region | PROJMAN | Cynthia L Ferguson | Noah C King | (9) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (12) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2024-03-01 | CFHWY00395
Central Region | PROJNAME | ANC VISUAL PAGING SYSTEM INSTALLATION | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | (3) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | (5) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | Anchorage | 2024-02-01 | CFAPT00930
Northern Region | (DELETED) |  |  | (2) [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | (7) [on 2023.08.21 project was added.]; [on 2023.09.15 FEDNUM changed.]; [on 2023.09.15 LOCATION changed.]; [on 2023.09.15 PROJNAME changed.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.10.25 PROJNAME changed.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | Chena Ridge Road Resurfacing - Kentshire Drive to Friar's Way | Fairbanks | 2024-01-01 | NFHWY00838 | NFHWY00838 | Pending | John J Netardus | (907)451-5448 | Resurface Chena Ridge Road from Kentshire Drive to Friar's Way. Project includes drainage improvements and roadside hardware. |  | Between $2,500,000 and $5,000,000
Northern Region | (DELETED) |  |  |  | (5) [on 2023.06.15 project was added.]; [on 2023.09.15 ENGEST changed.]; [on 2023.09.15 FEDNUM changed.]; [on 2023.10.25 PROJNAME changed.]; [on 2023.12.15 PROJNAME changed.] | Kotzebue Airport Crosswind Runway Improvements | Kotzebue | 2024-05-01 | NFAPT00600 | NFAPT00600 | 3-02-0160-___-____ | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate and construct safety improvements to the Kotzebue Airport crosswind runway 18-36 and taxiway G, replace airfield lighting, apply dust palliative, and construct a new general aviation apron. |  | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  | (6) [on 2022.02.22 project was added.]; [on 2022.06.15 ADDLINFO changed.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 LOCATION changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.11.17 the project was removed.] | Chena Ridge Road and Chena Pump Road Resurfacing | Fairbanks | 2025-01-01 | NFHWY00570 | NFHWY00570 | 645015 | John J Netardus | (907)451-5448 | Resurface Chena Ridge Road and Chena Pump Road. Project will include bridge work, drainage improvements, embankment stabilization, and roadside hardware. | Single chip seal overlay proposed. | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  |  | (2) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.] | Deadhorse Airport Improvements | Deadhorse | 2024-05-01 | NFAPT00549 | NFAPT00549 | 3-02-0339-___-____ | Jonathan J Hutchinson | (907)451-5479 | Construct drainage improvements at the Deadhorse Airport and along Deadhorse Drive and fill in-fields adjacent to the runway and apron. Construct a wildlife perimeter fence with a service road around the airfield. |  | Between $30,000,000 and $40,000,000
Northern Region | ANTADVDT | 2024-01-01 | 2024-04-01 | (10) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | (15) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2023.12.15 ENGEST changed.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2024-04-01 | Z768840000
Northern Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (3) [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | (6) [on 2022.11.17 project was added.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.] | Richardson Highway MP 351 Interchange | North Pole | 2024-02-01 | NFHWY00097
Northern Region | ANTADVDT | 2024-03-01 | 2024-05-01 |  | (4) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.] | HSIP: City of Fairbanks Systemic Signal Upgrades | Fairbanks | 2024-05-01 | NFHWY00592
Northern Region | ANTADVDT | 2024-03-01 | 2024-05-01 |  | (4) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.] | HSIP: Northern Region Systemic Signal Upgrades | Fairbanks North Star Borough | 2024-05-01 | NFHWY00531
Northern Region | ANTADVDT | 2024-03-01 | 2024-10-01 |  | (2) [on 2023.07.14 project was added.]; [on 2023.09.15 PROJNAME changed.] | Ruby Slough Road Rehabilitation | Ruby | 2024-10-01 | NFHWY00630
Northern Region | FEDNUM | Pending | 772001 | (1) [on 2023.11.15 the ANTADVDT changed to March 2024.] | (4) [on 2023.10.25 project was added.]; [on 2023.11.15 the ANTADVDT changed to March 2024.]; [on 2023.11.15 FEDNUM changed.]; [on 2023.11.15 PROJNAME changed.] | Richardson Highway MP 106.5-115 Resurfacing | Tazlina | 2024-03-01 | NFHWY00834
Northern Region | PHONENUM | None | (907)451-5424 |  | (2) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez | 2024-04-01 | Z618600000
Northern Region | PROJMAN | Brian L Logan | Lauren A Staft |  | (2) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez | 2024-04-01 | Z618600000
Northern Region | PROJNAME | PEARL CREEK ELEMENTARY SCHOOL ACCESS IMP AND PLUG-INS (CMAQ) | Pearl Creek Elementary School Access Imp and Plug-ins (CMAQ) | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (3) [on 2023.08.21 project was added.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.] | Pearl Creek Elementary School Access Imp and Plug-ins (CMAQ) | Fairbanks | 2024-05-01 | NFHWY00712
Southcoast Region | (DELETED) |  |  | (1) [on 2022.07.12 the ANTADVDT changed to March 2023.] | (9) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.07.12 the ANTADVDT changed to March 2023.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.06.15 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.01.16 project was added.] | CRAIG ADA IMPROVEMENTS | Craig | 2024-12-01 | SFHWY00377 | SFHWY00377 | 3274 | Bran P Pollard | (907)465-4526 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (4) [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | (9) [on 2022.11.17 project was added.]; [on 2022.12.17 ADDLINFO changed.]; [on 2023.02.24 the ANTADVDT changed to April 2023.]; [on 2023.02.24 ENGEST changed.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 DESCRIPTION changed.]; [on 2023.06.15 PROJNAME changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.] | POW NECK LAKE RD RECNTN STAGES 1 & 2 - WFLHD | Prince Of Wales Island | 2023-11-01 | SFHWY00375 | SFHWY00375 | AK PFH 58(2) | Gregory K Lockwood | (907)465-2393 | This project is to provide funding for state support and review of Neck Lake Road Segment 2 design developed under FHWA, Western Federal Lands Highway Division. Neck Lake Rd Stage 1 Match Transfer funding is also processed thru this project. | Phase 1 of Neck Lake Road Reconstruction will consist of approximately 3.96 miles of road reconstruction on Neck Lake Road beginning at the intersection of NPOWI Highway. The project will be advertised by Western Federal Lands. For more info go to: https://highways.dot.gov/federal-lands/projects/ak/pfh-58-1 | Between $10,000,000 and $20,000,000
Southcoast Region | ADDED |  |  |  |  | KDK ADQ AIRPORT TAXIWAYS C AND D RECNSTN | Kodiak | 2024-12-01 | SFAPT00558 | SFAPT00558 | N/A | David B Epstein | (907)465-4483 | Reconstruct Taxiways C and D at Kodiak Airport, Kodiak, AK. This new project replaces stages 2 and 3 of Kodiak Airport apron and Taxiways C, D, and F reconstruction. |  | Between $20,000,000 and $30,000,000
Southcoast Region | ADDED |  |  | (1) [on 2023.10.25 the ANTADVDT changed to August 2024.] | (3) [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the project was removed.] | SGY, HNH, PSG ROADWAY & CULVERTS - DEC 20 SE PR | Southcoast Region | 2025-01-01 | SFHWY00447 | SFHWY00447 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2020 01 HNH001, AK 2020 01 HNH002, AK 2021 01 PTG002, AK 2021 01 PTG003, and AK 2021 01 SGY001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites in Hoonah, Petersburg & Skagway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ANTADVDT | 2024-04-01 | 2024-06-01 | (5) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | (12) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-06-01 | SFAPT00412
Southcoast Region | ANTADVDT | 2024-02-01 | 2024-03-01 | (6) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | (12) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-03-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2024-02-01 | 2024-04-01 | (2) [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.] | (18) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2023.11.15 DESCRIPTION changed.]; [on 2023.11.15 ENGEST changed.]; [on 2023.11.15 PROJNAME changed.] | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | Kodiak | 2024-04-01 | SFAPT00227
Southcoast Region | ANTADVDT | 2024-02-01 | 2024-03-01 | (11) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.08.21 the ANTADVDT changed to February 2024.] | (17) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to February 2024.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2024-03-01 | Z680850000
Southcoast Region | ANTADVDT | 2024-01-01 | 2024-02-01 | (12) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | (16) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2024-02-01 | SFAPT00212
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (2) [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.] | (15) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-07-01 | SFAPT00178
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (2) [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | (9) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 ADDLINFO changed.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-04-01 | Z686060000
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 | (3) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | (8) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-05-01 | SFHWY00070
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 | (6) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | (11) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2024-05-01 | SFHWY00103
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (3) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.] | (8) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 ENGEST changed.]; [on 2024.01.16 PROJNAME changed.] | JNU Waydelich Creek: Upper & Lower Wall Repairs | Juneau | 2024-06-01 | SFHWY00414
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (1) [on 2023.10.25 the ANTADVDT changed to May 2024.] | (6) [on 2023.05.15 project was added.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2023.12.15 PHONENUM changed.]; [on 2023.12.15 PROJMAN changed.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2024-06-01 | SFHWY00312
Southcoast Region | ANTADVDT | 2024-11-01 | 2024-12-01 |  | (3) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2023.12.15 project was added.] | HNS LUTAK ROAD 437114 - DEC 20 SE PR | Haines | 2024-12-01 | SDRER00448
Southcoast Region | ENGEST | Between $500,000 and $1,000,000 | Between $1,000,000 and $2,500,000 | (2) [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2024-08-01 | SFHWY00438
Southcoast Region | FEDNUM | N/A | 3-02-0111-010-2024 |  | (1) [on 2024.01.16 project was added.] | FFY24 GUSTAVUS PAVEMENT MARKINGS/LOADER | Gustavus | 2024-03-01 | SFAPT00478