## 2024.04.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (1) [on 2024.02.14 the ANTADVDT changed to February 2024.] | (2) [on 2024.01.16 project was added.]; [on 2024.02.14 the ANTADVDT changed to February 2024.] | AKUTAN GENERATOR SYSTEM UPGRADE DESIGN-BUILD | Akutan | 2024-02-01 | SFAPT00539 | SFAPT00539 | AIP 3-02-0005-009-2024 | Levi D Overbeck | (907)269-0617 | This federally funded contract requires the Contractor to provide the necessary design and construction services, as required, to replace the failing generators at the Akutan Airport Snow Removal Equipment Building (SREB). |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (1) [on 2024.02.14 the ANTADVDT changed to February 2024.] | (2) [on 2023.11.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to February 2024.] | ANC Job Order Construction Contract (RFP 2024) | Anchorage | 2024-02-01 | CSAPT01156 | CSAPT01156 | N/A | Jesse Campbell | (907)266-2723 | Indefinite delivery / indefinite quantity contract to perform maintenance, repair, and construction work supporting the mission of the Ted Stevens Anchorage International Airport. Contractor shall be responsible for both design and construction work. |  | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (7) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to February 2024.] | (14) [on 2022.03.15 the ANTADVDT changed to February 2023.]; [on 2022.03.15 ENGEST changed.]; [on 2022.03.15 PROJMAN changed.]; [on 2022.11.17 ADDLINFO changed.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to June 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to December 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to February 2024.]; [on 2024.02.14 PHONENUM changed.] | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Wasilla | 2024-02-01 | Z512210000 | Z512210000 | 1417 | Chris L Bentz | (907)707-1912 | Upgrade Seward Meridian to a four-lane roadway and a multi-use, separated pathway along the west side from the Palmer-Wasilla Highway to Bogard Road and extend SMP one mile from Bogard Road to Seldon Road. Intersection improvements include a signal at the Bogard Road intersection and at the Seldon Road intersection. A new bridge, Cottonwood Creek Bridge #1696, would replace the existing culvert at the Cottonwood Creek crossing. | <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/51221/51221_Plans.pdf">Preliminary Plans (~40 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> <br><a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/51221/51221_CrossSections.pdf">Preliminary Cross Sections (~5 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $50,000,000 and $60,000,000
Central Region | (DELETED) |  |  |  | (6) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.07.12 the project was removed.]; [on 2024.02.14 project was added.] | ANC TAXILANE R SOUTH REHABILITATION | Anchorage | 2025-01-01 | CFAPT00758 | CFAPT00758 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate the structural taxilane pavement, remove and replace airfield lighting and restripe. | Rehabilitate asphalt. | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.02.14 project was added.] | CR24 Anchorage District NHS Preventative Maintenance CFHWY01137 / 0001786 | Anchorage | 2024-03-01 | 24-25-1-002 | 24-25-1-002 | N/A | Vernon S Vreeland | (907)269-0778 | This contract shall provide for all materials, equipment, supervision, labor, maintenance, fuel, mobilization, and demobilization necessary to clear brush on the State of Alaska Highway facilities within the Anchorage Maintenance District, on an as-needed basis as directed by the DOT&PF Representative. The State may opt to offer renewal of this contract for up to four (4) additional one (1) year period. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (10) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.] | (15) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.07.14 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.] | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | Anchorage | 2024-03-01 | CFHWY00395 | CFHWY00395 | 1642 | Noah C King | (907)269-0657 | Pavement Preservation project for Elmore Road: Abbott Rd. to Providence Dr. This project includes resurfacing, roadside hardware, drainage improvements, intersection improvements, and ADA improvements as necessary. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | AVTEC Industrial Electronics Building Renovations | Seward | 2024-04-01 | 25C0741600 | 25C0741600 | N/A | David R Hepler | (907)269-0815 | This state funded project will replace a portion of roofing on the AVTEC Industrial Electronics Building in Seward, Alaska. This project includes four (4) additive alternates for additional roofing replacement; siding, window, and door replacement; boiler replacement; and construction of a new roof canopy. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | Peger Road Engineering & Contracts Building Roof Replacement | Fairbanks | 2024-04-01 | 2501000064 | 2501000064 | N/A | Lauren A Staft | (907)451-5424 | This state funded project includes all necessary construction services as required to replace the existing roof with a new EPDM roofing system at the Peger Road Engineering & Contracts Building at the Department of Transportation Complex at 2301 Peger Road in Fairbanks, Alaska. |  | Pending
Central Region | ADDED |  |  |  | (2) [on 2022.10.20 project was added.]; [on 2022.11.17 the project was removed.] | HSIP: BOGARD AT ENGSTROM RD/GREEN FOREST DR INTER IMP | Wasilla | 2025-02-01 | CFHWY00453 | CFHWY00453 | 1630 | Chris L Bentz | (907)707-1912 | Reconstruction, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. |  | Pending
Central Region | ADDED |  |  |  |  | ANC C Concourse Plaza Renovation Design | Anchorage | 2025-01-01 | CSAPT01196 | CSAPT01196 | N/A | Jennifer M Lombardo | (907)266-2731 | Provide a design to improve the function, utilization, and maintenance of the C Concourse Plaza area. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | ANC RON 12-14 Rehabilitation | Anchorage | 2025-01-01 | CFAPT01192 | CFAPT01192 | 3-02-0016-XXX-2025 | Jennifer M Lombardo | (907)266-2731 | Rehabilitate and extend the life of aprons RON 12, 13, and 14 to include joint seal replacement and concrete rehabilitation. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | ANC South Terminal Employee Entrance Improvements | Anchorage | 2025-01-01 | CSAPT01183 | CSAPT01183 | N/A | Jennifer M Lombardo | (907)266-2731 | Adjust drive lanes at the entrance to provide enough width for maintenance equipment to plow in the vicinity of the access points. Project could include pavement removal and replacement, curb removal and replacement, landscaping, and utility relocations. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  | (5) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.] | (10) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.]; [on 2023.07.14 the project was removed.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2024-07-01 | CFHWY00253 | CFHWY00253 | 221019 | Alex L Read | (907)269-0641 | This project will rehabilitate the Kenai Spur Highway between Soldotna and Kenai. A 5-lane highway will be constructed between the Sports Lake Road and Robin Drive intersections to increase capacity and improve safety. This is the second of two phases to construct the project. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00253/00253.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $40,000,000 and $50,000,000
Central Region | ADDED |  |  | (1) [on 2023.10.25 the ANTADVDT changed to September 2024.] | (5) [on 2022.05.16 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to September 2024.]; [on 2023.11.15 the project was removed.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2025-03-01 | CFHWY00555 | CFHWY00555 | 1657 | Julia R Hanson | (907)269-0753 | This AMATS funded project will reconstructed the traffic signal and street lighting system on 4th Ave between A Street and Ingra Street. Work may included signing, Striping, ATRs, drainage, paving, pedestrian & ADA amenities, utility relocation, landscaping and roadside hardware. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  |  | HSIP: ANCHORAGE FLASHING YLW ARROW & SIGNAL HEAD DISPLAY IMP | Anchorage | 2025-03-01 | CFHWY00944 | CFHWY00944 | 1750 | Galen K Jones | (907)269-0550 | This project will install FYA signal heads for existing protected-permissive and permissive left turning movements (opposing left turns will both be upgraded, where identified); install new signal poles, mast arms, and foundations as required to complete FYA upgrades; upgrade existing TS-1 traffic controller cabinets and electrical load centers to support FYA operation; relocate mast arm signage and reconstruct existing sidewalk, roadway, curb and gutter, and curb ramps as required to modify the required traffic signal to FYA operation. | Two PS&Es will be advertised on year apart with roughly equal amounts in 2025 and 2026. The amount shown is for the first contract. | Pending
Central Region | ADDED |  |  |  | (2) [on 2022.04.15 project was added.]; [on 2022.09.13 the project was removed.] | Knik Goose Bay Rd Reconstruct, Vine to Settlers Bay | Wasilla | 2025-03-01 | Z517170000 | Z517170000 | N/A | Tom J Schmid | None | Reconstruct Knik-Goose Bay Rd from its intersection with the Vine Road to its intersection with Settlers Bay Drive. Work may include widening the roadway to add additional thru traffic lanes, turning lanes, as well as new signals and associated drainage and safety improvements. | Project will be constructed in two phases. The first phase of construction (Fairview Loop Road to Centaur Ave., approx. 4mi) will be advertised under project CFHWY00599. This project will be part of the 2nd phase (Settlers Bay to Fairview Loop Road, approx. 4mi) will be constructed with project Z524640000. | Between $20,000,000 and $30,000,000
Central Region | ADDED |  |  |  | (2) [on 2022.04.15 project was added.]; [on 2022.09.13 the project was removed.] | KNIK-GOOSE BAY RD RECONSTRUCTION PHASE II - VINE ROAD TO FAIRVIEW LOOP | Wasilla | 2025-03-01 | Z524640000 | Z524640000 | 525016 | Tom J Schmid | None | Project will improve capacity of this segment of Knik-Goose Bay Road, likely requiring additional lanes. Includes constructing bike/pedestrian facilities and implementing appropriate safety engineering strategies and access management. | Project will be constructed in two phases. The first phase of construction (Fairview Loop Road to Centaur Ave., approx. 4mi) will be advertised under project CFHWY00599. The 2nd phase (Settlers Bay to Fairview Loop Road, approx. 4mi) will be constructed under project Z524640000 and project 51717. | Between $20,000,000 and $30,000,000
Central Region | ADDED |  |  |  |  | TAKOTNA AIRPORT REHABILITATION | Central | 2025-03-01 | CFAPT00805 | CFAPT00805 | N/A | Aaron C Hughes | (907)269-0523 | Resurface the runway, taxiway, apron, and access road to correct deep cracks, uneven surfaces, soft spots, and areas where subbase is exposed. Replace lighting, NAVAIDS, and improve drainage. |  | Pending
Central Region | ADDED |  |  |  |  | ANC Runway 7R Pavement Repairs | Anchorage | 2024-05-01 | CSAPT01187 | CSAPT01187 | N/A | Jennifer M Lombardo | (907)266-2731 | Repair pavement along a section of Runway 7R from the edge of concrete to Taxiway G. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | FALSE PASS SREB (DFS) | Central Region | 2024-05-01 | SFAPT00416 | SFAPT00416 | N/A | Matthew R Epp | (907)764-4881 | This project will remove and replace the existing single bay SREB at the same location. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | Replace Nenana Station Shop Roof | Nenana | 2024-05-01 | 2501000065A | 2501000065A | N/A | Lauren A Staft | (907)451-5424 | Replace Nenana DOT Maintenance Station shop roof. | This project will be advertising with Project No. 2501000063- Replace Healy Station Shop Roof. | Between $200,000 and $500,000
Central Region | ADDLINFO | Project will advertise with Taxiway R North and Taxilane U Rehabilitation. | Project will advertise with Taxiway R North Improvements | (1) [on 2023.12.15 the ANTADVDT changed to March 2024.] | (2) [on 2023.10.25 project was added.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-04-01 | CFAPT00983A
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (1) [on 2024.02.14 the ANTADVDT changed to April 2024.] | (2) [on 2023.11.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | ANC FIRING RANGE MAINTENANCE | Anchorage | 2024-05-01 | CSAPT01152
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (1) [on 2024.02.14 the ANTADVDT changed to April 2024.] | (2) [on 2023.09.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | ANC OLD AFM GATE | Anchorage | 2024-05-01 | CSAPT01150
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (1) [on 2023.10.25 the ANTADVDT changed to April 2024.] | (4) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.02.14 DESCRIPTION changed.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-05-01 | CSAPT01146
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (1) [on 2024.01.16 the ANTADVDT changed to April 2024.] | (3) [on 2023.08.21 project was added.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 ENGEST changed.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-05-01 | CFAPT01136
Central Region | ANTADVDT | 2024-04-01 | 2024-06-01 | (4) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | (9) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-06-01 | CFHWY01083
Central Region | ANTADVDT | 2024-02-01 | 2024-04-01 | (4) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.] | (7) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.02.14 PROJNAME changed.] | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | Anchorage | 2024-04-01 | CFAPT00930
Central Region | ANTADVDT | 2024-07-01 | 2024-11-01 |  | (4) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2023.08.21 project was added.]; [on 2024.01.16 PROJNAME changed.] | HSIP: PALMER-FISHHOOK RD & TRUNK RD ROUNDABOUT | Palmer | 2024-11-01 | CFHWY00829
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (2) [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | (8) [on 2022.04.15 project was added.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | AMATS: EAGLE RIVER LOOP RD - EAGLE RIVER RD TO OLD GLENN HWY | Eagle River | 2024-04-01 | CFHWY00731
Central Region | ANTADVDT | 2024-03-01 | 2024-05-01 |  | (3) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.]; [on 2024.02.14 ENGEST changed.] | ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTIO | Anchorage | 2024-05-01 | CFAPT00881
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (1) [on 2023.12.15 the ANTADVDT changed to March 2024.] | (2) [on 2023.10.25 project was added.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-04-01 | CFAPT00983A
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (6) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 ENGEST changed.] | ANC TAXIWAY R NORTH & Taxilane U IMPROVEMENTS | Anchorage | 2024-04-01 | CFAPT00880
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (1) [on 2023.10.25 the ANTADVDT changed to March 2024.] | (3) [on 2023.08.21 project was added.]; [on 2023.09.15 DESCRIPTION changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | ANC TAXIWAY R TUG ROAD IMPROVEMENTS | Anchorage | 2024-04-01 | CSAPT01127
Central Region | ANTADVDT | 2024-03-01 | 2024-05-01 |  | (1) [on 2024.02.14 project was added.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2024-05-01 | CFAPT00993A
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (1) [on 2022.11.17 the ANTADVDT changed to August 2023.] | (5) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.11.15 FEDNUM changed.] | CHEVAK AIRPORT REHABILITATION | Chevak | 2024-04-01 | Z537250000
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (1) [on 2024.02.14 project was added.] | CR24 Peninsula District NHS Preservation CFHWY01139 / 0001787 CR24 Peninsula District Non-NHS Preservation CFHWY01142 / 0001790 | Soldotna | 2024-04-01 | 24-25-1-001
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (1) [on 2023.12.15 project was added.] | Kalsin Bay Maintenance Station - Phase 2 | Kodiak Island Borough | 2024-04-01 | CPFAC00080
Central Region | ANTADVDT | 2024-03-01 | 2024-04-01 | (2) [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | (6) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to March 2024.] | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | Eagle River | 2024-04-01 | CFHWY00621
Central Region | ANTADVDT | 2024-05-01 | 2024-07-01 | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (6) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2023.11.15 ENGEST changed.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-07-01 | CFHWY01084
Central Region | DESCRIPTION | Install a vertical pivot gate to secure the M&O yard at the Old AFM complex. | Install a vertical pivot gate to secure the M&O yard at the Old AFM complex and card reader at North Terminal Employee exit. | (1) [on 2024.02.14 the ANTADVDT changed to April 2024.] | (2) [on 2023.09.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | ANC OLD AFM GATE | Anchorage | 2024-05-01 | CSAPT01150
Central Region | DESCRIPTION | Rehabilitate Postmark Drive from Rockwell Avenue to Dehavilland Avenue. Project includes pavement planning, paving, and striping. | Rehabilitate Postmark Drive from Rockwell Avenue to Dehavilland Avenue. Project includes pavement planning, paving, striping, and drainage. | (1) [on 2023.10.25 the ANTADVDT changed to April 2024.] | (4) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.02.14 DESCRIPTION changed.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-05-01 | CSAPT01146
Central Region | DESCRIPTION | Provide a drainage system for the lighting duct near the east end of Runway (RW) 7L25R. | Provide a drainage system for the lighting duct near the east end of Runway (RW) 7L/25R. |  | (1) [on 2023.09.15 project was added.] | ANC RUNWAY 7L/25R LIGHTING DUCT DRAINAGE IMPROVEMENTS | Anchorage | 2024-04-01 | CFAPT01149
Central Region | DESCRIPTION | Remove and replace approximately 1,000 feet of security fence along the northeast edge of the airfield. Project includes clearing, grubbing, embankment extension and replacing swing gates. | Remove and replace approximately 1,000 feet of security fence along the northeast edge of the airfield. Project includes clearing, grubbing, embankment extension and replacing swing gates. To be advertised with CFAPT00880 ANC Taxiway R North and Taxilane U Improvements project. | (1) [on 2023.12.15 the ANTADVDT changed to March 2024.] | (2) [on 2023.10.25 project was added.]; [on 2023.12.15 the ANTADVDT changed to March 2024.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-04-01 | CFAPT00983A
Central Region | DESCRIPTION | This federally funded project will rehabilitate approximately 6,000 feet of water pipe around the North Terminal, C Concourse, A Concourse, and Old Airfield Maintenance (OAM) building at the Ted Stevens Anchorage International Airport. Improvements will also include hydrant replacements, valve replacements, and grouting a decommissioned water pipe segment under the South Terminal. | This federally funded project will rehabilitate approximately 6,000 feet of water pipe around the North Terminal, C Concourse, A Concourse, and Old Airfield Maintenance (OAM) building at the Ted Stevens Anchorage International Airport. Improvements will also include hydrant replacements, valve replacements, and grouting a decommissioned water pipe segment under the South Terminal. To be advertised with CFAPT00881 ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTION. |  | (1) [on 2024.02.14 project was added.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2024-05-01 | CFAPT00993A
Central Region | ENGEST | Between $500,000 and $1,000,000 | Between $1,000,000 and $2,500,000 | (1) [on 2023.10.25 the ANTADVDT changed to March 2024.] | (3) [on 2023.08.21 project was added.]; [on 2023.09.15 DESCRIPTION changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | ANC TAXIWAY R TUG ROAD IMPROVEMENTS | Anchorage | 2024-04-01 | CSAPT01127
Central Region | FEDNUM | 3-02-0468-003-2024 | 3-02-0468-004-2024 | (1) [on 2022.11.17 the ANTADVDT changed to August 2023.] | (5) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.11.15 FEDNUM changed.] | CHEVAK AIRPORT REHABILITATION | Chevak | 2024-04-01 | Z537250000
Central Region | LOCATION | Southcoast Region | Kodiak Island Borough |  | (1) [on 2023.12.15 project was added.] | Kalsin Bay Maintenance Station - Phase 2 | Kodiak Island Borough | 2024-04-01 | CPFAC00080
Central Region | PHONENUM | (907)269-0550 | (907)269-0543 | (1) [on 2024.02.14 the ANTADVDT changed to June 2024.] | (3) [on 2023.08.21 project was added.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 PROJMAN changed.] | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | Hope | 2024-06-01 | CFHWY00928
Central Region | PHONENUM | (907)269-0751 | (907)269-0778 |  | (1) [on 2024.02.14 project was added.] | CR24 Peninsula District NHS Preservation CFHWY01139 / 0001787 CR24 Peninsula District Non-NHS Preservation CFHWY01142 / 0001790 | Soldotna | 2024-04-01 | 24-25-1-001
Central Region | PROJMAN | Joshua D Stuckey | Vernon S Vreeland |  | (1) [on 2024.02.14 project was added.] | CR24 Peninsula District NHS Preservation CFHWY01139 / 0001787 CR24 Peninsula District Non-NHS Preservation CFHWY01142 / 0001790 | Soldotna | 2024-04-01 | 24-25-1-001
Central Region | PROJNAME | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | (10) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | (16) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.02.14 DESCRIPTION changed.] | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | Anchorage | 2024-04-01 | CSAPT00931
Central Region | PROJNAME | ANC RUNWAY 7L25R LIGHTING DUCT DRAINAGE IMPROVEMENTS | ANC RUNWAY 7L/25R LIGHTING DUCT DRAINAGE IMPROVEMENTS |  | (1) [on 2023.09.15 project was added.] | ANC RUNWAY 7L/25R LIGHTING DUCT DRAINAGE IMPROVEMENTS | Anchorage | 2024-04-01 | CFAPT01149
Central Region | PROJNAME | ANC TAXIWAY R NORTH IMPROVEMENTS | ANC TAXIWAY R NORTH & Taxilane U IMPROVEMENTS |  | (6) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 ENGEST changed.] | ANC TAXIWAY R NORTH & Taxilane U IMPROVEMENTS | Anchorage | 2024-04-01 | CFAPT00880
Central Region | PROJNAME | CR24 PENINSULA DISTRICT NHS PREVENTATIVE MAINTENANCE CFHWY01139 / 0001787 CR24 PENINSULA DISTRICT NON-NHS PREVENTATIVE MAINTENANCE CFHWY01142 / 0001790 | CR24 Peninsula District NHS Preservation CFHWY01139 / 0001787 CR24 Peninsula District Non-NHS Preservation CFHWY01142 / 0001790 |  | (1) [on 2024.02.14 project was added.] | CR24 Peninsula District NHS Preservation CFHWY01139 / 0001787 CR24 Peninsula District Non-NHS Preservation CFHWY01142 / 0001790 | Soldotna | 2024-04-01 | 24-25-1-001
Central Region | REGION | Southcoast Region | Central Region |  | (1) [on 2023.12.15 project was added.] | Kalsin Bay Maintenance Station - Phase 2 | Kodiak Island Borough | 2024-04-01 | CPFAC00080
Marine Highways | ADDED |  |  |  | (3) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the project was removed.] | AMHS AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | Juneau | 2025-02-01 | SAMHS00419 | SAMHS00419 | 933048 | Misty L Butler | (907)465-4546 | Make improvements to the AMHS Auke Bay Terminal East Berth. Work would include: Replacement of mooring dolphins, refurbish/replace transfer bridge and support float, install mechanical and electrical upgrades. |  | Between $5,000,000 and $10,000,000
Marine Highways | ADDED |  |  |  |  | M/V Columbia CPP System Replacement | Statewide | 2024-03-01 | SAMHS00147_C | SAMHS00147_C | 9500143 | Troy J Sherrill | (907)228-6829 | The scope of work for this federally funded contract includes the installation of a new Owner-Furnished Controlled Pitch Propeller (CPP) System on the M/V Columbia, including Alarm and Monitoring systems installation, Fire Detection system, testing, and demonstration of acceptable operation to regulatory agencies and the owner. Work includes necessary remediation of contaminated materials, limited engineering, documentation, and State funded annual overhaul work as outlined in the plans and specifications. |  | Pending
Northern Region | (DELETED) |  |  | (11) [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | (16) [on 2022.11.17 project was added.]; [on 2022.12.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.02.24 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to April 2023.]; [on 2023.05.15 the ANTADVDT changed to May 2023.]; [on 2023.06.15 ADDLINFO changed.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2023.12.15 ENGEST changed.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | Kotzebue to Cape Blossom Road - Stage II | Kotzebue | 2024-04-01 | Z768840000 | Z768840000 | 2204 | Jonathan J Hutchinson | (907)451-5479 | Construct a road from Kotzebue to Cape Blossom. Project work will include a new bridge over Sadie Creek (#1596), roadside hardware, drainage improvements, and utilities | Project will be advertised as a CMGC RFP. | Between $50,000,000 and $60,000,000
Northern Region | (DELETED) |  |  | (1) [on 2024.01.16 the ANTADVDT changed to February 2024.] | (6) [on 2023.06.15 project was added.]; [on 2023.07.14 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.07.14 LOCATION changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2024.01.16 the ANTADVDT changed to February 2024.] | Denali Highway Culvert Replacement | Cantwell | 2024-02-01 | NFHWY00701 | NFHWY00701 | Pending | David K Fischer | (907)451-5357 | Replace culverts on the Denali Highway at MP 93.2, MP 107 and MP 124.5. Project includes roadside hardware. |  | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  | (2) [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to February 2024.] | (9) [on 2022.06.15 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.02.24 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.03.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.07.14 PROJNAME changed.]; [on 2023.10.25 LOCATION changed.]; [on 2024.01.16 the ANTADVDT changed to February 2024.] | Elliott Highway MP 18 - 29 Resurfacing | Fox | 2024-02-01 | NFHWY00588 | NFHWY00588 | 650035 | John J Netardus | (907)451-5448 | Resurface the Elliott Highway from MP 18 - 29. Project will include selected areas of roadway rehabilitation, bridge work, drainage improvements, roadside hardware, and utilities. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  | (4) [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.] | (7) [on 2022.11.17 project was added.]; [on 2023.05.15 DESCRIPTION changed.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.10.25 the ANTADVDT changed to October 2023.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.] | Richardson Highway MP 351 Interchange | North Pole | 2024-02-01 | NFHWY00097 | NFHWY00097 | 0A24034 | David K Fischer | (907)451-5357 | Reconstruct the Old Richardson Highway and Richardson Highway intersection at MP 351 of the Richardson Highway. Work will include intersection improvements, bridge work, roadside hardware, drainage improvements, and utilities. Additional work includes construction of a connection between Keeney and the extension of the Old Richardson highway and relocation of the North Pole city water line. | Construct an overpass at the Old Richardson Hwy (12 Mile) and relocate the intersection of Old Rich and Richardson Hwy, including realigning access of Keeney Road. | Between $20,000,000 and $30,000,000
Northern Region | (DELETED) |  |  | (2) [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.11.15 the ANTADVDT changed to March 2024.] | (6) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.11.15 the ANTADVDT changed to March 2024.]; [on 2023.11.15 FEDNUM changed.]; [on 2024.01.16 FEDNUM changed.]; [on 2024.01.16 PROJNAME changed.] | Copper Center Visitor Center Pavement Preservation | Copper Center | 2024-03-01 | NFHWY00720 | NFHWY00720 | 8650106 | Russell M Johnson | (907)451-5059 | Resurface pavement at the Copper Center Visitor Center complex. |  | Between $200,000 and $500,000
Northern Region | (DELETED) |  |  | (1) [on 2023.11.15 the ANTADVDT changed to March 2024.] | (5) [on 2023.10.25 project was added.]; [on 2023.11.15 the ANTADVDT changed to March 2024.]; [on 2023.11.15 FEDNUM changed.]; [on 2023.11.15 PROJNAME changed.]; [on 2024.02.14 FEDNUM changed.] | Richardson Highway MP 106.5-115 Resurfacing | Tazlina | 2024-03-01 | NFHWY00834 | NFHWY00834 | 772001 | Russell M Johnson | (907)451-5059 | Resurface the Richardson Highway from MP 106.5 - 115. Improvements include drainage improvements and roadside hardware. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  |  | (2) [on 2023.11.15 project was added.]; [on 2024.01.16 LOCATION changed.] | Richardson Highway MP 111.5 Turn Lanes | Tazlina | 2024-03-01 | NRMBS00553 | NRMBS00553 | N/A | Russell M Johnson | (907)451-5059 | Construct turn lanes at the Copper River Native Association Clinic entrance/exit located at Richardson Highway milepost 111.5. |  | Between $500,000 and $1,000,000
Northern Region | (DELETED) |  |  | (1) [on 2024.02.14 the ANTADVDT changed to May 2024.] | (5) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | HSIP: City of Fairbanks Systemic Signal Upgrades | Fairbanks | 2024-05-01 | NFHWY00592 | NFHWY00592 | 2495 | Ethan E Graetz | (907)451-2281 | Reconstruct 22 signalized intersections at multiple locations in the City of Fairbanks. Work includes roadside hardware and intersection improvements. | This project will be advertised with HSIP: Northern Region Systemic Signal Upgrades (NFHWY00531) | Between $5,000,000 and $10,000,000
Northern Region | (DELETED) |  |  | (1) [on 2024.02.14 the ANTADVDT changed to May 2024.] | (5) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | HSIP: Northern Region Systemic Signal Upgrades | Fairbanks North Star Borough | 2024-05-01 | NFHWY00531 | NFHWY00531 | 2474 | Ethan E Graetz | (907)451-2281 | Reconstruct eight signalized intersections at multiple locations in the Fairbanks and Parks Highway Nenana Canyon area. Work includes roadside hardware and intersection improvements. | This project will be constructed with HSIP: City of Fairbanks Systemic Signal Upgrades (NFHWY00592) | Between $2,500,000 and $5,000,000
Northern Region | ADDED |  |  |  |  | Nome Kougarok Road MP 61.5, MP 66.5, and MP 79.5 Perm Repair | Nome | 2024-04-01 | NDRER00895 | NDRER00895 | 733519 | Christopher E Johnson | None | Construct permanent repairs to the Kougarok Road at MP 61.5, MP 66.5, and MP 79.5. Project includes roadway reconstruction and drainage improvements. |  | Between $1,000,000 and $2,500,000
Northern Region | ADDED |  |  |  |  | Kotzebue to Cape Blossom Road - Stage II: CMGC | Kotzebue | 2024-07-01 | Z768840000_CMGC | Z768840000_CMGC | 2204 | Jonathan J Hutchinson | (907)451-5479 | The Northern Region State of Alaska Department of Transportation and Public Facilities (Department) invites proposals from general construction contractors to serve as "Construction Manager/General Contractor (CMGC)" for Kotzebue to Cape Blossom Road - Stage II. The CMGC procurement is intended to encompass all materials, labor, supplies, equipment and supervision necessary for the complete construction of the project, including any preconstruction related services during the development process. | Project will be advertised as a CMGC RFP. | Between $50,000,000 and $60,000,000
Northern Region | ADDED |  |  | (1) [on 2022.02.22 the ANTADVDT changed to July 2022.] | (6) [on 2022.02.22 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2023.03.15 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.10.25 the project was removed.] | Deering Airport Improvements | Deering | 2025-03-01 | NFAPT00249 | NFAPT00249 | 3-02-0400-XX-202X | Jonathan J Hutchinson | (907)451-5479 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $20,000,000 and $30,000,000
Northern Region | ADDED |  |  |  |  | HSIP: CHENA SMALL TRACTS ROUNDABOUT | Fairbanks North Star Borough | 2025-03-01 | NFHWY00699 | NFHWY00699 | 645016 | Ethan E Graetz | (907)451-2281 | Construct a roundabout at the intersection of Chena Pump Road, Old Chena Ridge Road, and Chena Small Tracts Road. Project will include intersection improvements, roadside hardware, and utilities. |  | Pending
Northern Region | ADDED |  |  |  |  | City of Fairbanks Systemic Signal Upgrades - Stage 1 (HSIP) | Fairbanks | 2024-05-01 | NFHWY00905 | NFHWY00905 | N/A | Ethan E Graetz | (907)451-2281 | Reconstruct eleven signalized intersections at multiple locations in the City of Fairbanks. Work includes intersection improvements and roadside hardware. | This project will advertise with NFHWY00904. | Less than $200,000
Northern Region | ADDED |  |  |  |  | Glenn/Richardson Highway Right of Way Reconciliation | Glennallen | 2024-05-01 | HSHWY00018 | HSHWY00018 | N/A | Carl F Heim | (907)451-5359 | Reconcile right of way and encroachment conflicts along the Glenn and Richardson Highways near Glennallen Alaska, to allow for completion of future federal projects. This work may include right of way research, appraisals, purchases and other activities necessary to eliminate conflicts. Completion of a highway wayside as part of the conflict elimination will also be included as part of this effort. |  | Between $500,000 and $1,000,000
Northern Region | ADDED |  |  |  |  | Northern Region Systemic Signal Upgrades - Stage 1 (HSIP) | Regionwide | 2024-05-01 | NFHWY00904 | NFHWY00904 | N/A | Ethan E Graetz | (907)451-2281 | Reconstruct seven signalized intersections at multiple locations in the Fairbanks and Parks Highway Nenana Canyon area. Work includes intersection improvements and roadside hardware. | This project will advertise with NFHWY00905. | Between $5,000,000 and $10,000,000
Northern Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (1) [on 2024.01.16 the ANTADVDT changed to April 2024.] | (4) [on 2023.08.21 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 PROJNAME changed.] | Alaska Highway MP 1235-1268 Rehabilitation (Const MP 1252-1268) | Northway | 2024-05-01 | Z607520000
Northern Region | ANTADVDT | 2024-04-01 | 2024-11-01 |  | (1) [on 2024.01.16 project was added.] | Cowles Street Reconstruction - Airport Way to East Cowles | Fairbanks | 2024-11-01 | NFHWY00883
Northern Region | ANTADVDT | 2024-04-01 | 2025-01-01 |  | (1) [on 2023.08.21 project was added.] | Fairbanks Bike Lane Striping and Signing (TAP) | Fairbanks | 2025-01-01 | NFHWY00835
Northern Region | ANTADVDT | 2024-04-01 | 2024-07-01 | (1) [on 2024.01.16 the ANTADVDT changed to April 2024.] | (3) [on 2023.02.24 project was added.]; [on 2023.06.15 PROJNAME changed.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | Seppala Drive Upgrade | Nome | 2024-07-01 | Z620030000
Northern Region | ANTADVDT | 2024-04-01 | 2024-05-01 |  | (4) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez | 2024-05-01 | Z618600000
Northern Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (2) [on 2023.08.21 project was added.]; [on 2023.10.25 PROJNAME changed.] | Woll Road Resurfacing and Widening | North Pole | 2024-04-01 | NFHWY00448
Northern Region | ANTADVDT | 2024-10-01 | 2025-02-01 |  | (1) [on 2023.11.15 project was added.] | Yankovich-Miller Hill Road Reconstruction and Multi-Use Path | Fairbanks | 2025-02-01 | NFHWY00139
Northern Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 |  | (4) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez | 2024-05-01 | Z618600000
Southcoast Region | (DELETED) |  |  | (3) [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | (19) [on 2022.01.18 project was added.]; [on 2022.02.22 ADDLINFO changed.]; [on 2022.03.15 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.07.12 the project was removed.]; [on 2022.11.17 project was added.]; [on 2023.01.17 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2023.11.15 DESCRIPTION changed.]; [on 2023.11.15 ENGEST changed.]; [on 2023.11.15 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | KDK: ADQ AIRPORT APRON AND TWY F RECNSTN | Kodiak | 2024-04-01 | SFAPT00227 | SFAPT00227 | N/A | David B Epstein | (907)465-4483 | Reconstruct taxiway F and Apron. Replace edge lights, conduit, and cable. Install apron flood lighting along northern end; upgrade light bases and cabling. Significant drainage rehabilitation. | Reconstruct taxiway F and Apron. Replace edge lights, conduit, and cable. Install apron flood lighting along northern end; upgrade light bases and cabling. Significant drainage rehabilitation. | Between $20,000,000 and $30,000,000
Southcoast Region | (DELETED) |  |  | (13) [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.] | (17) [on 2022.01.18 DESCRIPTION changed.]; [on 2022.02.22 the ANTADVDT changed to March 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.06.15 the ANTADVDT changed to July 2022.]; [on 2022.07.12 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to September 2022.]; [on 2022.09.13 the ANTADVDT changed to October 2022.]; [on 2022.10.20 the project was removed.]; [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to August 2023.]; [on 2023.09.15 the ANTADVDT changed to September 2023.]; [on 2023.10.25 the ANTADVDT changed to November 2023.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.] | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | Regionwide | 2024-02-01 | SFAPT00212 | SFAPT00212 | 3-02-0277-007-2023 | Peter J Jackson | (907)465-4439 | Remove and replace secondary wind cone and install new conduit and wire. Remove and replace primary wind cone and install new conduit and wire. Remove and replace rotating Airport Beacon. Phase 4 - CC 24300206 LC 33004012 |  | Between $200,000 and $500,000
Southcoast Region | (DELETED) |  |  | (1) [on 2023.10.25 the ANTADVDT changed to August 2024.] | (4) [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the project was removed.]; [on 2024.02.14 project was added.] | SGY, HNH, PSG ROADWAY & CULVERTS - DEC 20 SE PR | Southcoast Region | 2025-01-01 | SFHWY00447 | SFHWY00447 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2020 01 HNH001, AK 2020 01 HNH002, AK 2021 01 PTG002, AK 2021 01 PTG003, and AK 2021 01 SGY001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites in Hoonah, Petersburg & Skagway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (2) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 ENGEST changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.] | JNU WAYDELICH CREEK: LOWER WALL REPAIRS | Juneau | 2024-03-01 | SFHWY00485 | SFHWY00485 | 933050 | Joel D Osburn | (907)465-4409 | This project will repair the damage & deterioration to the lower part of the retaining wall at Waydelich Creek. Repairs may include, but are not limited to embankment, geotextile, concrete, steel reinforcement, riprap, drainage, roadside hardware, and utilities. |  | Between $500,000 and $1,000,000
Southcoast Region | (DELETED) |  |  | (12) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.08.21 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.] | (18) [on 2022.02.22 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.04.15 ENGEST changed.]; [on 2022.06.15 the ANTADVDT changed to August 2022.]; [on 2022.08.14 the ANTADVDT changed to October 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2023.02.24 the ANTADVDT changed to July 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.05.15 the ANTADVDT changed to January 2024.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.05.15 PROJMAN changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to February 2024.]; [on 2023.10.25 PHONENUM changed.]; [on 2023.10.25 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to March 2024.] | SGY STATE STREET PAVEMENT REHABILITATION | Skagway | 2024-03-01 | Z680850000 | Z680850000 | 972018 | Kirk D Miller | (907)465-1215 | Rehabilitate the pavement, replace curb and gutter in select areas, upgrade curb ramps and vehicular curb cuts to meet ADA standards, repair and/or replace drainage facilities as needed, and replace all signs within the project limits. | Rehabilitate the pavement from 1st Avenue to the Skagway River Bridge. Repair and/or replace existing drainage infrastructure. Replace existing sidewalk, curb ramps, and driveways to meet current ADA requirements. | Between $20,000,000 and $30,000,000
Southcoast Region | ADDED |  |  |  |  | KTN WATER STREET BRIDGE NBI#797 STRENGTHENING | Ketchikan | 2024-04-01 | SSHWY00496 | SSHWY00496 | N/A | James L Brown | (907)465-1796 | Bridge strengthening to NBI#797 at the intersection of Bauer Way and Water Street. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  | (2) [on 2022.08.14 project was added.]; [on 2022.11.17 the project was removed.] | KTN WOLFE POINT SLOPE STABILITY IMPROVEMENTS | Ketchikan | 2024-04-01 | SFHWY00432 | SFHWY00432 | 920032 | James L Brown | (907)465-1796 | The project will repair unstable slopes from MP 3.0 to MP 3.9 on Tongass Highway. | Work will need to be shifted into the Summer to allow for blasting at maximum availability of daylight hours. | Between $5,000,000 and $10,000,000
Southcoast Region | ADDED |  |  |  | (5) [on 2023.03.15 project was added.]; [on 2023.05.15 ENGEST changed.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the project was removed.] | JNU L00P RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | Juneau | 2025-03-01 | SFHWY00403 | SFHWY00403 | 966030 | Nathan A Purves | (907)465-4521 | Construct a single-lane roundabout at the Loop Road - Mendenhall Boulevard - Valley Boulevard intersection. |  | Between $5,000,000 and $10,000,000
Southcoast Region | ANTADVDT | 2024-04-01 | 2024-06-01 | (3) [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | (10) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 ADDLINFO changed.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-06-01 | Z686060000
Southcoast Region | ANTADVDT | 2024-08-01 | 2024-10-01 | (4) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2024-10-01 | SDRER00436
Southcoast Region | ANTADVDT | 2024-08-01 | 2024-10-01 | (2) [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.] | (6) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.02.14 ENGEST changed.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2024-10-01 | SFHWY00438
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-03-01 | (1) [on 2024.02.14 the ANTADVDT changed to December 2024.] | (4) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2023.12.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to December 2024.] | HNS LUTAK ROAD 437114 - DEC 20 SE PR | Haines | 2025-03-01 | SDRER00448
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-01-01 | (2) [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.] | (3) [on 2023.06.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.] | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2025-01-01 | SDRER00445
Southcoast Region | ANTADVDT | 2024-07-01 | 2024-09-01 | (3) [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.02.14 the ANTADVDT changed to July 2024.] | (16) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to July 2024.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-09-01 | SFAPT00178
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-10-01 | (2) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.] | (4) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-10-01 | SFHWY00481
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 |  | (2) [on 2024.01.16 project was added.]; [on 2024.02.14 FEDNUM changed.] | FFY24 GUSTAVUS PAVEMENT MARKINGS/LOADER | Gustavus | 2024-05-01 | SFAPT00478
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-06-01 |  | (1) [on 2024.01.16 project was added.] | FFY24 KTN PAVEMENT MARKINGS/CRACKSEAL | Ketchikan | 2024-06-01 | SFAPT00467
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-06-01 |  | (1) [on 2024.01.16 project was added.] | FFY24 PSG PAVEMENT MARKINGS/LOADER | Petersburg | 2024-06-01 | SFAPT00469
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-04-01 |  | (1) [on 2024.01.16 project was added.] | FFY24 Southeast District Highway Painting | Statewide | 2024-04-01 | SFHWY00556
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-06-01 |  | (1) [on 2024.01.16 project was added.] | FFY24 WRG SURFACE PAVEMENT MARKINGS & SRE | Wrangell | 2024-06-01 | SFAPT00468
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-06-01 |  | (1) [on 2024.01.16 project was added.] | FFY24 YAK PAVEMENT MARKINGS | Yakutat | 2024-06-01 | SFAPT00474
Southcoast Region | ANTADVDT | 2024-03-01 | 2024-05-01 | (7) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.] | (13) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-05-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (6) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.] | (17) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-06-01 | SFHWY00359
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-07-01 | (11) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.]; [on 2023.11.15 the ANTADVDT changed to May 2024.] | (12) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.]; [on 2023.11.15 the ANTADVDT changed to May 2024.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2024-07-01 | SFAPT00144
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-06-01 |  | (1) [on 2023.10.25 project was added.] | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | Ketchikan | 2024-06-01 | SFHWY00536
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (7) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | (12) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2024-06-01 | SFHWY00103
Southcoast Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (1) [on 2024.01.16 the ANTADVDT changed to September 2024.] | (3) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-10-01 | SFHWY00440
Southcoast Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (3) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the ANTADVDT changed to September 2024.] | (5) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-10-01 | SFHWY00446
Southcoast Region | DESCRIPTION | Replace the twin culverts at Bridget Cove Creek. | The work includes excavation, grading, culvert replacement, seeding, rock armoring, and stream channel restoration. | (6) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.] | (17) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-06-01 | SFHWY00359
Southcoast Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $2,500,000 and $5,000,000 | (4) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.] | (5) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2024-10-01 | SDRER00436
Southcoast Region | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 |  | (1) [on 2024.01.16 project was added.] | KOKHANOK AIRPORT RESURFACING AND FENCING | Kokhanok | 2024-12-01 | SFAPT00361
Southcoast Region | ENGEST | Between $1,000,000 and $2,500,000 | Between $2,500,000 and $5,000,000 | (6) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | (13) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-06-01 | SFAPT00412
Southcoast Region | FEDNUM | N/A | 93007 | (3) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the ANTADVDT changed to September 2024.] | (5) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-10-01 | SFHWY00446