## 2024.05.16 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (3) [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | (9) [on 2022.04.15 project was added.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | AMATS: EAGLE RIVER LOOP RD - EAGLE RIVER RD TO OLD GLENN HWY | Eagle River | 2024-04-01 | CFHWY00731 | CFHWY00731 | 1694 | Julia R Hanson | (907)269-0753 | Pavement preservation, which may include improvements to roadside hardware, drainage, intersections, automated traffic recorders, pedestrian facilities, striping, signs, and utilities. | Project will be combined with CFHWY00621 North Eagle River Access Road Pavement Preservation | Between $2,500,000 and $5,000,000
Central Region | (DELETED) |  |  | (3) [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | (4) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | ANC RON 2 Rehabilitation | Anchorage | 2024-04-01 | CFAPT01104 | CFAPT01104 | 3-02-0016-XXX-2024 | Jennifer M Lombardo | (907)266-2731 | Remove and replace liquid joint sealant and perform cementitious and elastomeric concrete repairs on hardstand RON 2. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.04.15 project was added.] | AVTEC Industrial Electronics Building Renovations | Seward | 2024-04-01 | 25C0741600 | 25C0741600 | N/A | David R Hepler | (907)269-0815 | This state funded project will replace a portion of roofing on the AVTEC Industrial Electronics Building in Seward, Alaska. This project includes four (4) additive alternates for additional roofing replacement; siding, window, and door replacement; boiler replacement; and construction of a new roof canopy. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to April 2024.] | (5) [on 2024.02.14 project was added.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 PHONENUM changed.]; [on 2024.04.15 PROJMAN changed.]; [on 2024.04.15 PROJNAME changed.] | CR24 Peninsula District NHS Preservation CFHWY01139 / 0001787 CR24 Peninsula District Non-NHS Preservation CFHWY01142 / 0001790 | Soldotna | 2024-04-01 | 24-25-1-001 | 24-25-1-001 | N/A | Vernon S Vreeland | (907)269-0778 | This federally funded contract is for stormwater infrastructure cleaning services. Work includes cleaning of curb inlets, catch basins, catch basin manholes, manholes, field inlets, lift stations, storm drain pipes and culvert pipes along State of Alaska roadways located in the Kenai Peninsula Maintenance District. |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (3) [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | (7) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to July 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | N EAGLE RIVER ACCESS RD - POWDER RIDGE DR TO OLD GLENN HWY | Eagle River | 2024-04-01 | CFHWY00621 | CFHWY00621 | 1692 | Julia R Hanson | (907)269-0753 | This preventative maintenance project will resurface North Eagle River Access Road and may include as necessary; signing and striping, guardrail and other roadside hardware, signalization, lighting, drainage work, dig-outs, bridge repair, curb ramps, automated traffic recorders, and utility relocation. | Project will be combined with CFHWY00731 AMATS: Eagle River Loop Road Pavement Preservation. | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.04.15 project was added.] | Peger Road Engineering & Contracts Building Roof Replacement | Fairbanks | 2024-04-01 | 2501000064 | 2501000064 | N/A | Lauren A Staft | (907)451-5424 | This state funded project includes all necessary construction services as required to replace the existing roof with a new EPDM roofing system at the Peger Road Engineering & Contracts Building at the Department of Transportation Complex at 2301 Peger Road in Fairbanks, Alaska. |  | Pending
Central Region | (DELETED) |  |  | (1) [on 2023.10.25 the ANTADVDT changed to September 2024.] | (6) [on 2022.05.16 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to September 2024.]; [on 2023.11.15 the project was removed.]; [on 2024.04.15 project was added.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2025-03-01 | CFHWY00555 | CFHWY00555 | 1657 | Julia R Hanson | (907)269-0753 | This AMATS funded project will reconstructed the traffic signal and street lighting system on 4th Ave between A Street and Ingra Street. Work may included signing, Striping, ATRs, drainage, paving, pedestrian & ADA amenities, utility relocation, landscaping and roadside hardware. |  | Between $5,000,000 and $10,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2022.04.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2024.04.15 project was added.] | Knik Goose Bay Rd Reconstruct, Vine to Settlers Bay | Wasilla | 2025-03-01 | Z517170000 | Z517170000 | N/A | Tom J Schmid | None | Reconstruct Knik-Goose Bay Rd from its intersection with the Vine Road to its intersection with Settlers Bay Drive. Work may include widening the roadway to add additional thru traffic lanes, turning lanes, as well as new signals and associated drainage and safety improvements. | Project will be constructed in two phases. The first phase of construction (Fairview Loop Road to Centaur Ave., approx. 4mi) will be advertised under project CFHWY00599. This project will be part of the 2nd phase (Settlers Bay to Fairview Loop Road, approx. 4mi) will be constructed with project Z524640000. | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2022.04.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2024.04.15 project was added.] | KNIK-GOOSE BAY RD RECONSTRUCTION PHASE II - VINE ROAD TO FAIRVIEW LOOP | Wasilla | 2025-03-01 | Z524640000 | Z524640000 | 525016 | Tom J Schmid | None | Project will improve capacity of this segment of Knik-Goose Bay Road, likely requiring additional lanes. Includes constructing bike/pedestrian facilities and implementing appropriate safety engineering strategies and access management. | Project will be constructed in two phases. The first phase of construction (Fairview Loop Road to Centaur Ave., approx. 4mi) will be advertised under project CFHWY00599. The 2nd phase (Settlers Bay to Fairview Loop Road, approx. 4mi) will be constructed under project Z524640000 and project 51717. | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.04.15 project was added.] | ANC Runway 7R Pavement Repairs | Anchorage | 2024-05-01 | CSAPT01187 | CSAPT01187 | N/A | Jennifer M Lombardo | (907)266-2731 | Repair pavement along a section of Runway 7R from the edge of concrete to Taxiway G. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | ANCHOR POINT ROAD MP 0-1.3 PAVEMENT PRESERVATION | Anchor Point | 2025-04-01 | CFHWY00601 | CFHWY00601 | 1699 | Steven J Rzepka | (907)269-0592 | Resurface Anchor Point Road from Old Sterling Highway to end of road at beach parking lot. This project will include: Pavement Preservation, Roadside Hardware, Drainage improvements, and Utilities. |  | Pending
Central Region | ADDED |  |  | (4) [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.]; [on 2023.03.15 the ANTADVDT changed to September 2023.] | (7) [on 2022.03.15 PROJMAN changed.]; [on 2022.08.14 the ANTADVDT changed to January 2023.]; [on 2022.09.13 the ANTADVDT changed to February 2023.]; [on 2022.12.17 the ANTADVDT changed to June 2023.]; [on 2023.03.15 the ANTADVDT changed to September 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the project was removed.] | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | Anchorage | 2025-04-01 | CFHWY00286 | CFHWY00286 | 510007 | Jon W Knowles | (907)269-0643 | Pavement Preservation of DeArmoun Rd. from East 140th Avenue to Hillside Drive including improvements to drainage, intersections, ADA, roadside hardware, and utilities. High Friction Surface Treatment may be reapplied. |  | Between $2,500,000 and $5,000,000
Central Region | ADDED |  |  |  |  | TUNUNAK AIRPORT REHABILITATION | Tununak | 2025-04-01 | CFAPT00854 | CFAPT00854 | 3-02-0486-003-2024 | Kim D Satterfield | (907)269-0623 | This project proposes to rehabilitate and resurface the operational surfaces at the Tununak Airport to correct cracks, ruts, uneven surfaces, dips (over 6"), soft spots, and ponding. Dust palliative will be applied for fines preservation to bind aggregate and prevent loss of fines. Drainage improvements may include special ditching and culvert realignment where needed. Lighting and visual aids will be repaired or replaced where they have been damaged or displaced by subsidence. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | PETERS CREEK BRIDGE (1367) EMERGENCY REPAIRS | Peters Creek | 2024-08-01 | CDRER01160 | CDRER01160 | N/A | Steven J Rzepka | (907)269-0592 | This state funded emergency project will remove and replace the damaged girder on the Peters Creek Undercrossing (NBI 1367) on the Glenn Highway. Work also includes cast in place concrete, bridge rail, pavement striping, and traffic control. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | 7 Mile Asbestos Mitigation and HVAC Upgrades | Juneau | 2024-12-01 | 25RC013613 | 25RC013613 | N/A | None | None | Project to address remaining Asbestos ad HVac Issues within the Dot 7mi complex's main building within Juneau Alaska |  | Pending
Central Region | ADDED |  |  |  |  | ANC GATES N2 &N4 REHABILITATION | Anchorage | 2025-01-01 | CFAPT01205 | CFAPT01205 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate and extend the life of the aprons at Gates N2 and N4 to include joint seal replacement and concrete rehabilitation |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | PALMER-FISHHOOK ROAD MILEPOSTS 7-17 | Matanuska-Susitna Borough | 2025-01-01 | CFHWY00405 | CFHWY00405 | 580020 | Aaron L Hunting | (907)269-0546 | Pavement Preservation of Palmer-Fishhook Road Mileposts 7-17 and may include, as necessary: Bridge Work, Roadside Hardware, Drainage Improvements, and Utilities. |  | Pending
Central Region | ADDED |  |  |  |  | FAI Gate 3 Passenger Boarding Bridge Replacement Design-Build | Fairbanks North Star Borough | 2024-05-01 | NFAPT00888 | NFAPT00888 | AIP 3-02-0096-XXX-2024 | Jesse Campbell | (907)266-2723 | This federally funded Design-Build project will design and install a new apron drive PBB at Gate 3 of the Fairbanks International Airport (FAI). The new PBB is to replace the existing PBB at the same location and is to be fully integrated into the terminal building. |  | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  |  |  | Plant Materials Center Storage Building Design-Build | Palmer | 2024-05-01 | 25C1041605 | 25C1041605 | N/A | David R Hepler | (907)269-0815 | This state funded project is to construct a storage building for the Plant Materials Center. |  | Pending
Central Region | ADDLINFO | This project will be advertising with Project No. 2501000063- Replace Healy Station Shop Roof. |  |  | (1) [on 2024.04.15 project was added.] | Nenana Station Shop Roof Improvements | Nenana | 2024-05-01 | 2501000065A
Central Region | ANTADVDT | 2024-04-01 | 2024-06-01 | (10) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.] | (17) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.] | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | Anchorage | 2024-06-01 | CSAPT00931
Central Region | ANTADVDT | 2024-04-01 | 2024-06-01 |  | (3) [on 2023.09.15 project was added.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.] | ANC RUNWAY 7L/25R LIGHTING DUCT DRAINAGE IMPROVEMENTS | Anchorage | 2024-06-01 | CFAPT01149
Central Region | ANTADVDT | 2024-04-01 | 2024-06-01 | (2) [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | (5) [on 2023.10.25 project was added.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.04.15 ADDLINFO changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 DESCRIPTION changed.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-06-01 | CFAPT00983A
Central Region | ANTADVDT | 2024-04-01 | 2024-06-01 | (1) [on 2024.04.15 the ANTADVDT changed to April 2024.] | (8) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 PROJNAME changed.] | ANC TAXIWAY R NORTH & Taxilane U IMPROVEMENTS | Anchorage | 2024-06-01 | CFAPT00880
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (2) [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | (5) [on 2023.08.21 project was added.]; [on 2023.09.15 DESCRIPTION changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 ENGEST changed.] | ANC TAXIWAY R TUG ROAD IMPROVEMENTS | Anchorage | 2024-05-01 | CSAPT01127
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (5) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | (8) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.02.14 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | Anchorage | 2024-05-01 | CFAPT00930
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (2) [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | (7) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.11.15 FEDNUM changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 FEDNUM changed.] | CHEVAK AIRPORT REHABILITATION | Chevak | 2024-05-01 | Z537250000
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (5) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | (8) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Anchorage | 2024-05-01 | CFHWY00523
Central Region | ANTADVDT | 2024-04-01 | 2024-05-01 | (1) [on 2024.04.15 the ANTADVDT changed to April 2024.] | (4) [on 2023.12.15 project was added.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 LOCATION changed.]; [on 2024.04.15 REGION changed.] | Kalsin Bay Maintenance Station - Phase 2 | Kodiak Island Borough | 2024-05-01 | CPFAC00080
Central Region | ANTADVDT | 2024-08-01 | 2025-03-01 |  | (3) [on 2023.11.15 project was added.]; [on 2023.12.15 ADDLINFO changed.]; [on 2023.12.15 FEDNUM changed.] | ANC ATCT REPLACEMENT PARKING | Anchorage | 2025-03-01 | CRMBS00831
Central Region | ANTADVDT | 2024-06-01 | 2024-08-01 | (1) [on 2024.02.14 the ANTADVDT changed to June 2024.] | (6) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.11.15 ENGEST changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 DESCRIPTION changed.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-08-01 | CFAPT00572
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (5) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | (10) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-07-01 | CFHWY01083
Central Region | ANTADVDT | 2024-05-01 | 2024-07-01 | (2) [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | (3) [on 2023.11.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | ANC FIRING RANGE MAINTENANCE | Anchorage | 2024-07-01 | CSAPT01152
Central Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (1) [on 2024.04.15 the ANTADVDT changed to May 2024.] | (4) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTIO | Anchorage | 2024-06-01 | CFAPT00881
Central Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (2) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | (6) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 DESCRIPTION changed.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-06-01 | CSAPT01146
Central Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (1) [on 2024.04.15 the ANTADVDT changed to May 2024.] | (3) [on 2024.02.14 project was added.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 DESCRIPTION changed.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2024-06-01 | CFAPT00993A
Central Region | ANTADVDT | 2024-05-01 | 2024-07-01 | (2) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | (4) [on 2023.08.21 project was added.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-07-01 | CFAPT01136
Central Region | ANTADVDT | 2024-11-01 | 2025-01-01 |  | (2) [on 2023.12.15 project was added.]; [on 2024.01.16 ENGEST changed.] | ANC TAXILANE E IMPROVEMENTS | Anchorage | 2025-01-01 | CFAPT01002
Central Region | DESCRIPTION | Pavement preservation, bridge work, roadside hardware, drainage improvements, and utilities. | This federally funded contract will perform work at the Glenn Highway Kinik River bridges and Peters Creek bridge. Work includes bridge deck and expansion joint repair work, guardrail, and paving. Limited duration bridge closures to perform the work will require installation of temporary detours as well as use of a movable concrete barrier system for changing the number travel lanes available for peak daily traffic flow direction during closures. | (5) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | (8) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Anchorage | 2024-05-01 | CFHWY00523
Central Region | DESCRIPTION | Replace Nenana DOT Maintenance Station shop roof. | Perform structural upgrades and replace Nenana DOT Maintenance Station shop roof. |  | (1) [on 2024.04.15 project was added.] | Nenana Station Shop Roof Improvements | Nenana | 2024-05-01 | 2501000065A
Central Region | ENGEST | Between $10,000,000 and $20,000,000 | Between $20,000,000 and $30,000,000 | (5) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | (8) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Anchorage | 2024-05-01 | CFHWY00523
Central Region | ENGEST | Between $200,000 and $500,000 | Between $500,000 and $1,000,000 |  | (1) [on 2024.04.15 project was added.] | Nenana Station Shop Roof Improvements | Nenana | 2024-05-01 | 2501000065A
Central Region | LOCATION | Central Region | Anchorage | (5) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | (8) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Anchorage | 2024-05-01 | CFHWY00523
Central Region | PROJNAME | Replace Nenana Station Shop Roof | Nenana Station Shop Roof Improvements |  | (1) [on 2024.04.15 project was added.] | Nenana Station Shop Roof Improvements | Nenana | 2024-05-01 | 2501000065A
Central Region | REGION | Northern Region | Central Region | (1) [on 2024.04.15 the ANTADVDT changed to May 2024.] | (6) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 ENGEST changed.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez | 2024-05-01 | Z618600000
Northern Region | (DELETED) |  |  |  | (2) [on 2023.08.21 project was added.]; [on 2023.09.15 PROJNAME changed.] | Northern Region ADA Improvements - Fairbanks: 4th and 11th Avenues | Fairbanks | 2024-04-01 | NFHWY00840 | NFHWY00840 | N/A | Ivet Hall | (907)451-5386 | Reconstruct pedestrian facilities and adjacent areas on 4th Avenue and 11 Avenue in Fairbanks. Project includes drainage improvements, roadside hardware, and utilities. |  | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to April 2024.] | (3) [on 2023.08.21 project was added.]; [on 2023.10.25 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | Woll Road Resurfacing and Widening | North Pole | 2024-04-01 | NFHWY00448 | NFHWY00448 | 2451 | Ivet Hall | (907)451-5386 | Resurface and widen the state-maintained portion of Woll Road in North Pole. Work also includes drainage improvements, roadside hardware, and utilities. |  | Between $2,500,000 and $5,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2024.04.15 project was added.] | Kotzebue to Cape Blossom Road - Stage II: CMGC | Kotzebue | 2024-07-01 | Z768840000_CMGC | Z768840000_CMGC | 2204 | Jonathan J Hutchinson | (907)451-5479 | The Northern Region State of Alaska Department of Transportation and Public Facilities (Department) invites proposals from general construction contractors to serve as "Construction Manager/General Contractor (CMGC)" for Kotzebue to Cape Blossom Road - Stage II. The CMGC procurement is intended to encompass all materials, labor, supplies, equipment and supervision necessary for the complete construction of the project, including any preconstruction related services during the development process. | Project will be advertised as a CMGC RFP. | Between $50,000,000 and $60,000,000
Northern Region | ADDED |  |  |  | (6) [on 2023.06.15 project was added.]; [on 2023.09.15 ENGEST changed.]; [on 2023.09.15 FEDNUM changed.]; [on 2023.10.25 PROJNAME changed.]; [on 2023.12.15 PROJNAME changed.]; [on 2024.02.14 the project was removed.] | Kotzebue Airport Crosswind Runway Improvements | Kotzebue | 2025-04-01 | NFAPT00600 | NFAPT00600 | 3-02-0160-___-____ | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate and construct safety improvements to the Kotzebue Airport crosswind runway 18-36 and taxiway G, replace airfield lighting, apply dust palliative, and construct a new general aviation apron. |  | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  |  | GLENN HIGHWAY MP 143-154 RESURFACING | Northern Region | 2024-11-01 | NFHWY00719 | NFHWY00719 | 0A14008 | Ivet Hall | (907)451-5386 | Resurface the Glenn Highway between MP 143-154. Project includes bridge work, drainage improvements, pavement preservation, roadside hardware, and utilities. |  | Pending
Northern Region | ANTADVDT | 2024-05-01 | 2024-06-01 |  | (1) [on 2024.04.15 project was added.] | City of Fairbanks Systemic Signal Upgrades - Stage 1 (HSIP) | Fairbanks | 2024-06-01 | NFHWY00905
Northern Region | ANTADVDT | 2024-05-01 | 2024-06-01 |  | (1) [on 2024.04.15 project was added.] | Northern Region Systemic Signal Upgrades - Stage 1 (HSIP) | Regionwide | 2024-06-01 | NFHWY00904
Southcoast Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to April 2024.] | (2) [on 2024.01.16 project was added.]; [on 2024.04.15 the ANTADVDT changed to April 2024.] | FFY24 Southeast District Highway Painting | Statewide | 2024-04-01 | SFHWY00556 | SFHWY00556 | N/A | David B Epstein | (907)465-4483 | Narrative/Scope(if not FHWA)/Explanation for other changes: (New Project - Pre Grant) This project consists of applying new paint and beads to all striping, symbols, crosswalks, and stop bars on state owned roads through out the Southeast District. Any necessary training for State personnel, sweeping, flushing, and any other required pavement preparation where new paint is to be applied. Locations include Juneau, Ketchikan, Klawock, Petersburg, Wrangell, Yakutat. 83% of work is Non-NHS. 17% of work is NHS. |  | Pending
Southcoast Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to June 2024.] | (2) [on 2024.01.16 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | FFY24 KTN PAVEMENT MARKINGS/CRACKSEAL | Ketchikan | 2024-06-01 | SFAPT00467 | SFAPT00467 | N/A | Spencer M Gates | (907)465-1014 | Pre Grant Apply new pavement marking and crackseal |  | Pending
Southcoast Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to June 2024.] | (2) [on 2024.01.16 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | FFY24 PSG PAVEMENT MARKINGS/LOADER | Petersburg | 2024-06-01 | SFAPT00469 | SFAPT00469 | N/A | Spencer M Gates | (907)465-1014 | Apply new pavement markings, Replace snow removal Equipment CC 24300448 LC 33008472 Phase: T02FA1 CC&LC Description: SFAPT00469-2P-Pavement |  | Pending
Southcoast Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to June 2024.] | (2) [on 2024.01.16 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | FFY24 WRG SURFACE PAVEMENT MARKINGS & SRE | Wrangell | 2024-06-01 | SFAPT00468 | SFAPT00468 | N/A | Spencer M Gates | (907)465-1014 | Pre Grant apply new pavement markings and crackseal. Replace snow removal equipment |  | Pending
Southcoast Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to June 2024.] | (2) [on 2024.01.16 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | FFY24 YAK PAVEMENT MARKINGS | Yakutat | 2024-06-01 | SFAPT00474 | SFAPT00474 | N/A | Spencer M Gates | (907)465-1014 | Apply new pavement markings |  | Pending
Southcoast Region | (DELETED) |  |  | (1) [on 2024.04.15 the ANTADVDT changed to May 2024.] | (3) [on 2024.01.16 project was added.]; [on 2024.02.14 FEDNUM changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | FFY24 GUSTAVUS PAVEMENT MARKINGS/LOADER | Gustavus | 2024-05-01 | SFAPT00478 | SFAPT00478 | 3-02-0111-010-2024 | Spencer M Gates | (907)465-1014 | Apply new pavement markings, Replace snow removal equipment. |  | Pending
Southcoast Region | ADDED |  |  | (1) [on 2023.10.25 the ANTADVDT changed to August 2024.] | (5) [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the project was removed.]; [on 2024.02.14 project was added.]; [on 2024.04.15 the project was removed.] | SGY, HNH, PSG ROADWAY & CULVERTS - DEC 20 SE PR | Southcoast Region | 2025-04-01 | SFHWY00447 | SFHWY00447 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2020 01 HNH001, AK 2020 01 HNH002, AK 2021 01 PTG002, AK 2021 01 PTG003, and AK 2021 01 SGY001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites in Hoonah, Petersburg & Skagway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ANTADVDT | 2024-04-01 | 2024-05-01 |  | (1) [on 2024.04.15 project was added.] | KTN WATER STREET BRIDGE NBI#797 STRENGTHENING | Ketchikan | 2024-05-01 | SSHWY00496
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (4) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | (9) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 ENGEST changed.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | JNU Waydelich Creek: Upper & Lower Wall Repairs | Juneau | 2024-07-01 | SFHWY00414
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (8) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | (14) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-06-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2024-05-01 | 2024-08-01 | (4) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | (9) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-08-01 | SFHWY00070
Southcoast Region | DESCRIPTION | The work includes excavation, grading, culvert replacement, seeding, rock armoring, and stream channel restoration. | The work includes excavation, grading, chip seal, culvert replacement, seeding, rock armoring, and stream channel restoration. | (7) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | (19) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.04.15 DESCRIPTION changed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-06-01 | SFHWY00359
Southcoast Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 | (4) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | (9) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-08-01 | SFHWY00070