## 2024.06.19 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (1) [on 2024.05.16 the ANTADVDT changed to June 2024.] | (4) [on 2023.09.15 project was added.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | ANC RUNWAY 7L/25R LIGHTING DUCT DRAINAGE IMPROVEMENTS | Anchorage | 2024-06-01 | CFAPT01149 | CFAPT01149 | 3-02-0016-XXX-2024 | Jennifer M Lombardo | (907)266-2731 | Provide a drainage system for the lighting duct near the east end of Runway (RW) 7L/25R. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (2) [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | (4) [on 2023.09.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 DESCRIPTION changed.] | ANC OLD AFM GATE | Anchorage | 2024-05-01 | CSAPT01150 | CSAPT01150 | N/A | Jennifer M Lombardo | (907)266-2731 | Install a vertical pivot gate to secure the M&O yard at the Old AFM complex and card reader at North Terminal Employee exit. |  | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (3) [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | (6) [on 2023.08.21 project was added.]; [on 2023.09.15 DESCRIPTION changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | ANC TAXIWAY R TUG ROAD IMPROVEMENTS | Anchorage | 2024-05-01 | CSAPT01127 | CSAPT01127 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate approximately 7,000 feet of the tug road from Taxiway Victor to Alaska Cargo Port. Project includes pavement planning, paving, and striping. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (3) [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | (8) [on 2022.09.13 project was added.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.11.15 FEDNUM changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 FEDNUM changed.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | CHEVAK AIRPORT REHABILITATION | Chevak | 2024-05-01 | Z537250000 | Z537250000 | 3-02-0468-004-2024 | Aaron C Hughes | (907)269-0523 | This project will rehabilitate the runway, taxiway, apron, and airport access road. The runway safety area will be expanded, and runway grades will be corrected to meet line-of-sight requirements. Additional improvements include replacement of airfield lighting, FAA navaids, wind cones, segmented circle, build a supplemental wind cone access, and apply dust palliative. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.05.16 project was added.] | FAI Gate 3 Passenger Boarding Bridge Replacement Design-Build | Fairbanks North Star Borough | 2024-05-01 | NFAPT00888 | NFAPT00888 | AIP 3-02-0096-XXX-2024 | Jesse Campbell | (907)266-2723 | This federally funded Design-Build project will design and install a new apron drive PBB at Gate 3 of the Fairbanks International Airport (FAI). The new PBB is to replace the existing PBB at the same location and is to be fully integrated into the terminal building. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (6) [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | (12) [on 2022.10.20 project was added.]; [on 2023.05.15 the ANTADVDT changed to November 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.08.21 ENGEST changed.]; [on 2023.09.15 the ANTADVDT changed to April 2024.]; [on 2023.11.15 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.]; [on 2024.05.16 DESCRIPTION changed.]; [on 2024.05.16 ENGEST changed.]; [on 2024.05.16 LOCATION changed.] | GLENN HIGHWAY BRIDGE DECK PRESERVATION | Anchorage | 2024-05-01 | CFHWY00523 | CFHWY00523 | 1685 | Christina A Huber | (907)269-0572 | This federally funded contract will perform work at the Glenn Highway Kinik River bridges and Peters Creek bridge. Work includes bridge deck and expansion joint repair work, guardrail, and paving. Limited duration bridge closures to perform the work will require installation of temporary detours as well as use of a movable concrete barrier system for changing the number travel lanes available for peak daily traffic flow direction during closures. |  | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.05.16 project was added.] | Plant Materials Center Storage Building Design-Build | Palmer | 2024-05-01 | 25C1041605 | 25C1041605 | N/A | David R Hepler | (907)269-0815 | This state funded project is to construct a storage building for the Plant Materials Center. |  | Pending
Central Region | ADDED |  |  |  |  | ANC Gate B4 Passenger Boarding Bridge Replacement Design-Build | Anchorage | 2024-06-01 | CFAPT01201 | CFAPT01201 | AIP 3-02-0016-XXX-2024 | Ashley B Devore | (907)269-6200 | This project will replace the existing Passenger Boarding Bridge (PBB) at Gate B4 with a new PBB through a Design-Build project. | Remove and replace existing Gate B4 PBB with new updated PBB. This will be a Design-Build project. | Between $1,000,000 and $2,500,000
Central Region | ADDED |  |  | (1) [on 2023.10.25 the ANTADVDT changed to September 2024.] | (7) [on 2022.05.16 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to September 2024.]; [on 2023.11.15 the project was removed.]; [on 2024.04.15 project was added.]; [on 2024.05.16 the project was removed.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2025-05-01 | CFHWY00555 | CFHWY00555 | 1657 | Julia R Hanson | (907)269-0753 | This AMATS funded project will reconstructed the traffic signal and street lighting system on 4th Ave between A Street and Ingra Street. Work may included signing, Striping, ATRs, drainage, paving, pedestrian & ADA amenities, utility relocation, landscaping and roadside hardware. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  |  | AMATS: FISH CREEK TRAIL CONNECTION | Anchorage | 2025-05-01 | CFHWY00587 | CFHWY00587 | 1696 | Noah C King | (907)269-0657 | This project will construct a multi-use path between Northern Lights Boulevard and the Tony Knowles Coastal Trail in the vicinity of Fish Creek. Work may include roadside hardware, ADA improvements, utilities, lighting, bridge work, and drainage improvements. |  | Pending
Central Region | ADDED |  |  | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (4) [on 2023.03.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 the project was removed.] | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | Big Lake | 2025-05-01 | CFHWY00392 | CFHWY00392 | 1686 | Alex L Read | (907)269-0641 | Pavement preservation, roadside hardware, structural improvement in limited areas, minor drainage and/or safety improvements, utility adjustment/relocation, signing and striping. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  |  | HSIP: VINE RD AT HOLLYWOOD INTERSECTION IMPROVEMENTS | Wasilla | 2025-05-01 | CFHWY00463 | CFHWY00463 | 1627 | Alex L Read | (907)269-0641 | Project will construct either a single lane roundabout or a traffic signal to mitigate crashes at the intersection of Vine and Hollywood. Project is included in the HSIP program. |  | Pending
Central Region | ADDED |  |  |  | (4) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2023.06.15 the project was removed.] | SEWARD AIRPORT IMPROVEMENTS | Seward | 2025-05-01 | Z548570000 | Z548570000 | N/A | Joy A Vaughn | None | Shift, raise and reconstruct R/W 16/34. Construct Armor protection. Rehabilitate aprons, replace airport lighting, and construct pads for NAVAIDS. Close R/W 13/31, Taxiways A, D, and E. Miscellaneous fencing, signing, etc... |  | Between $20,000,000 and $30,000,000
Central Region | ADDED |  |  |  |  | STERLING HWY: MP 157-169 RECON - PHASE I | Kenai Peninsula | 2024-11-01 | CFHWY01210 | CFHWY01210 | N/A | Aaron L Hunting | (907)269-0546 | This project reconstructs and upgrades a 12-mile segment of the Sterling Highway. It includes widening the highway, creating passing lanes, resurfacing, improving drainage, minor realignments, upgrading to current geometric standards, and replacing the North Fork Anchor River and Anchor River Bridges. This first phase will construct from MP 157 through 161 and include both bridges. |  | Between $60,000,000 and $70,000,000
Central Region | ADDLINFO | MP 12.9 only. MP 7.9 will be advertised under a separate contract in April 2025 |  | (1) [on 2024.02.14 the ANTADVDT changed to June 2024.] | (4) [on 2023.08.21 project was added.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 PHONENUM changed.] | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | Hope | 2025-03-01 | CFHWY00928
Central Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (3) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | (5) [on 2023.08.21 project was added.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-08-01 | CFAPT01136
Central Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (6) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | (11) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-08-01 | CFHWY01083
Central Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (2) [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.] | (7) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to July 2024.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-08-01 | CFHWY01084
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (11) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | (18) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | Anchorage | 2024-07-01 | CSAPT00931
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (2) [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | (5) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTIO | Anchorage | 2024-07-01 | CFAPT00881
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (3) [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | (6) [on 2023.10.25 project was added.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.04.15 ADDLINFO changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-07-01 | CFAPT00983A
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (2) [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | (9) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | ANC TAXIWAY R NORTH & Taxilane U IMPROVEMENTS | Anchorage | 2024-07-01 | CFAPT00880
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (2) [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | (4) [on 2024.02.14 project was added.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2024-07-01 | CFAPT00993A
Central Region | ANTADVDT | 2024-06-01 | 2025-03-01 | (1) [on 2024.02.14 the ANTADVDT changed to June 2024.] | (4) [on 2023.08.21 project was added.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 PHONENUM changed.] | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | Hope | 2025-03-01 | CFHWY00928
Central Region | ANTADVDT | 2025-03-01 | 2025-05-01 | (1) [on 2024.05.16 the ANTADVDT changed to March 2025.] | (4) [on 2023.11.15 project was added.]; [on 2023.12.15 ADDLINFO changed.]; [on 2023.12.15 FEDNUM changed.]; [on 2024.05.16 the ANTADVDT changed to March 2025.] | ANC ATCT REPLACEMENT PARKING | Anchorage | 2025-05-01 | CRMBS00831
Central Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (6) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | (9) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.02.14 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | Anchorage | 2024-06-01 | CFAPT00930
Central Region | ANTADVDT | 2024-05-01 | 2024-07-01 |  | (1) [on 2024.04.15 project was added.] | FALSE PASS SREB (DFS) | Central Region | 2024-07-01 | SFAPT00416
Central Region | ANTADVDT | 2024-05-01 | 2024-08-01 | (4) [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | (11) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2024-08-01 | CFHWY00883
Central Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (2) [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | (5) [on 2023.12.15 project was added.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 LOCATION changed.]; [on 2024.04.15 REGION changed.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | Kalsin Bay Maintenance Station - Phase 2 | Kodiak Island Borough | 2024-06-01 | CPFAC00080
Central Region | ANTADVDT | 2024-05-01 | 2024-07-01 |  | (5) [on 2024.04.15 project was added.]; [on 2024.05.16 ADDLINFO changed.]; [on 2024.05.16 DESCRIPTION changed.]; [on 2024.05.16 ENGEST changed.]; [on 2024.05.16 PROJNAME changed.] | Nenana Station Shop Roof Improvements | Nenana | 2024-07-01 | 2501000065A
Central Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (1) [on 2024.04.15 the ANTADVDT changed to May 2024.] | (7) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.05.16 REGION changed.] | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez | 2024-06-01 | Z618600000
Central Region | DESCRIPTION | Replace runway and taxiway lighting systems, the segmented circle and lighted primary wind cone, and the lighted supplemental wind cone. | Replace runway and taxiway lighting systems, the segmented circle and lighted primary wind cone, the rotating beacon, and the lighted supplemental wind cone. |  | (1) [on 2023.11.15 project was added.] | CHENEGA BAY AIRPORT LIGHTING IMPROVEMENTS | Chenega Bay | 2024-07-01 | CFAPT01021
Central Region | DESCRIPTION | The Kalsin Bay Maintenance Station was replaced in 2019. The reconstructed facility is a 4100 SQ. Ft. steel frame building with three maintenance bays and an adjoining office, break room, and bathroom. Phase 2 consists of miscellaneous remaining scope required for full functionality of the maintenance station, including but are not limited to, concrete apron replacement, building envelope upgrades, domestic water filtration, wastewater holding tank modifications, fuel tank relocation, provision of an emergency generator, and other mechanical and electrical upgrades. | This state funded contract includes miscellaneous upgrades required for full functionality of the Kalsin Bay Maintenance Station in Kodiak, Alaska. Work includes concrete apron replacement, building envelope upgrades, domestic water filtration, wastewater holding tank modifications, fuel tank relocation, and other mechanical and electrical upgrades. This contract includes one (1) additive alternate for installation of a new emergency generator system. | (2) [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | (5) [on 2023.12.15 project was added.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 LOCATION changed.]; [on 2024.04.15 REGION changed.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | Kalsin Bay Maintenance Station - Phase 2 | Kodiak Island Borough | 2024-06-01 | CPFAC00080
Central Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 | (1) [on 2024.02.14 the ANTADVDT changed to June 2024.] | (4) [on 2023.08.21 project was added.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 PHONENUM changed.] | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | Hope | 2025-03-01 | CFHWY00928
Central Region | FEDNUM | N/A | 3-02-0419-006-2024 |  | (1) [on 2023.11.15 project was added.] | CHENEGA BAY AIRPORT LIGHTING IMPROVEMENTS | Chenega Bay | 2024-07-01 | CFAPT01021
Marine Highways | DESCRIPTION | Make improvements to the AMHS Auke Bay Terminal East Berth. Work would include: Replacement of mooring dolphins, refurbish/replace transfer bridge and support float, install mechanical and electrical upgrades. | Work includes: Removal of 5 mooring/berthing dolphins and replacing with 6 new mooring/berthing dolphins, removal and replacement of 5 catwalks, removal and replacement of 2 gangways, and electrical upgrades to dolphin and walkway lighting systems. |  | (4) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the project was removed.]; [on 2024.04.15 project was added.] | AMHS AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | Juneau | 2025-02-01 | SAMHS00419
Marine Highways | ENGEST | Between $5,000,000 and $10,000,000 | Between $10,000,000 and $20,000,000 |  | (4) [on 2023.04.14 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.11.15 the project was removed.]; [on 2024.04.15 project was added.] | AMHS AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | Juneau | 2025-02-01 | SAMHS00419
Northern Region | (DELETED) |  |  |  | (1) [on 2024.04.15 project was added.] | Nome Kougarok Road MP 61.5, MP 66.5, and MP 79.5 Perm Repair | Nome | 2024-04-01 | NDRER00895 | NDRER00895 | 733519 | Christopher E Johnson | None | Construct permanent repairs to the Kougarok Road at MP 61.5, MP 66.5, and MP 79.5. Project includes roadway reconstruction and drainage improvements. |  | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  |  | (1) [on 2023.10.25 project was added.] | Shishmaref Sanitation Road Erosion Control | Shishmaref | 2024-06-01 | NFHWY00687 | NFHWY00687 | 2514 | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate sections of the Shishmaref Sanitation Road and construct erosion control features. Project will include drainage improvements and roadside hardware. |  | Between $10,000,000 and $20,000,000
Northern Region | (DELETED) |  |  | (2) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | (5) [on 2023.08.21 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.] | Alaska Highway MP 1235-1268 Rehabilitation (Const MP 1252-1268) | Northway | 2024-05-01 | Z607520000 | Z607520000 | 0A11014 | David K Fischer | (907)451-5357 | Rehabilitate the Alaska Highway and construct new passing lanes. Project work will include bridge work, roadside hardware, drainage, intersection improvements and utilities. |  | Between $30,000,000 and $40,000,000
Northern Region | ADDED |  |  |  |  | FIA RUNWAY 2L/20R LIGHTING REHABILITATION | Fairbanks North Star Borough | 2024-07-01 | NFAPT00889 | NFAPT00889 | N/A | RJ Stumpf | (907)474-2587 | Replace the 2L/20R runway lighting at the Fairbanks International Airport. |  | Between $1,000,000 and $2,500,000
Northern Region | ADDED |  |  | (1) [on 2024.02.14 the ANTADVDT changed to May 2024.] | (6) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the project was removed.] | HSIP: City of Fairbanks Systemic Signal Upgrades | Fairbanks | 2025-05-01 | NFHWY00592 | NFHWY00592 | 2495 | Ethan E Graetz | (907)451-2281 | Reconstruct 22 signalized intersections at multiple locations in the City of Fairbanks. Work includes roadside hardware and intersection improvements. | This project will be advertised with HSIP: Northern Region Systemic Signal Upgrades (NFHWY00531) | Between $5,000,000 and $10,000,000
Northern Region | ADDED |  |  | (1) [on 2024.02.14 the ANTADVDT changed to May 2024.] | (6) [on 2023.07.14 project was added.]; [on 2023.08.21 PROJNAME changed.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the project was removed.] | HSIP: Northern Region Systemic Signal Upgrades | Fairbanks North Star Borough | 2025-05-01 | NFHWY00531 | NFHWY00531 | 2474 | Ethan E Graetz | (907)451-2281 | Reconstruct eight signalized intersections at multiple locations in the Fairbanks and Parks Highway Nenana Canyon area. Work includes roadside hardware and intersection improvements. | This project will be constructed with HSIP: City of Fairbanks Systemic Signal Upgrades (NFHWY00592) | Between $2,500,000 and $5,000,000
Northern Region | ADDLINFO | 2-year construction, 2024-2025 | 2-year construction, 2025-2026 | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (4) [on 2023.08.21 project was added.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 PROJNAME changed.] | Pearl Creek Elementary School Access Imp and Plug-ins (CMAQ) | Fairbanks | 2024-10-01 | NFHWY00712
Northern Region | ANTADVDT | 2024-05-01 | 2024-07-01 |  | (3) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.02.14 project was added.] | Deadhorse Airport Improvements | Deadhorse | 2024-07-01 | NFAPT00549
Northern Region | ANTADVDT | 2024-05-01 | 2024-06-01 |  | (1) [on 2024.04.15 project was added.] | Glenn/Richardson Highway Right of Way Reconciliation | Glennallen | 2024-06-01 | HSHWY00018
Northern Region | ANTADVDT | 2024-05-01 | 2024-06-01 | (1) [on 2023.10.25 the ANTADVDT changed to May 2024.] | (2) [on 2023.09.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to May 2024.] | Gulkana River Boat Launch Fencing | Gulkana | 2024-06-01 | NSHWY00497a
Northern Region | ANTADVDT | 2024-05-01 | 2024-10-01 | (1) [on 2023.11.15 the ANTADVDT changed to May 2024.] | (4) [on 2023.08.21 project was added.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 PROJNAME changed.] | Pearl Creek Elementary School Access Imp and Plug-ins (CMAQ) | Fairbanks | 2024-10-01 | NFHWY00712
Northern Region | DESCRIPTION | Construct fencing along the boat launch on the Gulkana River. | Construct fencing along the woods next to the Gulkana River Bridge, near Mile 126.5 of the Richardson Highway, | (1) [on 2023.10.25 the ANTADVDT changed to May 2024.] | (2) [on 2023.09.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to May 2024.] | Gulkana River Boat Launch Fencing | Gulkana | 2024-06-01 | NSHWY00497a
Northern Region | ENGEST | Less than $200,000 | Between $200,000 and $500,000 | (1) [on 2023.10.25 the ANTADVDT changed to May 2024.] | (2) [on 2023.09.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to May 2024.] | Gulkana River Boat Launch Fencing | Gulkana | 2024-06-01 | NSHWY00497a
Southcoast Region | (DELETED) |  |  | (1) [on 2024.05.16 the ANTADVDT changed to May 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.05.16 the ANTADVDT changed to May 2024.] | KTN WATER STREET BRIDGE NBI#797 STRENGTHENING | Ketchikan | 2024-05-01 | SSHWY00496 | SSHWY00496 | N/A | James L Brown | (907)465-1796 | Bridge strengthening to NBI#797 at the intersection of Bauer Way and Water Street. |  | Between $500,000 and $1,000,000
Southcoast Region | ADDED |  |  |  |  | HSIP: JNU VANDERBILT CONTINUOUS GREEN T | Juneau | 2025-05-01 | SFHWY00524 | SFHWY00524 | 932054 | Joel D Osburn | (907)465-4409 | This project will convert the southbound Egan lanes to continuous green movements at the Vanderbilt intersection by adding a left turn acceleration lane for vehicles turning south from Vanderbilt onto Egan. |  | Between $1,000,000 and $2,500,000
Southcoast Region | ADDED |  |  |  |  | KTN N.Tongass HWY Resurface: A/P F.T. To Ward Creek Bridge Stage 2 | Ketchikan | 2025-05-01 | SFHWY00591 | SFHWY00591 | 920031 | Brett M Wells | (907)465-1607 | Resurface North Tongass from the Airport Ferry Terminal (milepoint 0.717) to (and including) the Ward Cove (milepoint 4.485). Replace culverts and guardrail at the end of useful life. Correct erosion and clear brush at Cannery Creek Bridge No. 746. |  | Between $10,000,000 and $20,000,000
Southcoast Region | ANTADVDT | 2025-01-01 | 2024-12-01 | (3) [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.] | (4) [on 2023.06.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.] | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2024-12-01 | SDRER00445
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (4) [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | (11) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 ADDLINFO changed.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-07-01 | Z686060000
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (7) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | (20) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 DESCRIPTION changed.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-07-01 | SFHWY00359
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (1) [on 2024.04.15 the ANTADVDT changed to June 2024.] | (2) [on 2023.10.25 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | Ketchikan | 2024-07-01 | SFHWY00536
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-10-01 | (8) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | (13) [on 2022.02.22 the ANTADVDT changed to June 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.12.17 the ANTADVDT changed to April 2023.]; [on 2023.03.15 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | Sitka | 2024-10-01 | SFHWY00103
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-11-01 | (2) [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | (7) [on 2023.05.15 project was added.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.10.25 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2023.12.15 PHONENUM changed.]; [on 2023.12.15 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | SIT SEAWALK PHASE II WFLHD RASPS | Sitka | 2024-11-01 | SFHWY00312
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (6) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | (14) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.04.15 ENGEST changed.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-07-01 | SFAPT00412
Southcoast Region | ANTADVDT | 2024-11-01 | 2025-01-01 | (4) [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 the ANTADVDT changed to February 2024.] | (11) [on 2022.09.13 project was added.]; [on 2022.10.20 ENGEST changed.]; [on 2022.11.17 the ANTADVDT changed to May 2023.]; [on 2022.12.17 the ANTADVDT changed to November 2023.]; [on 2022.12.17 DESCRIPTION changed.]; [on 2022.12.17 ENGEST changed.]; [on 2023.03.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the project was removed.]; [on 2023.12.15 project was added.] | COLD BAY TROUT CREEK CULVERTS WFL | Cold Bay | 2025-01-01 | SFHWY00326
Southcoast Region | ANTADVDT | 2024-10-01 | 2024-12-01 | (5) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | (7) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 ENGEST changed.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2024-12-01 | SDRER00436
Southcoast Region | ANTADVDT | 2024-10-01 | 2024-11-01 | (2) [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | (4) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-11-01 | SFHWY00440
Southcoast Region | ANTADVDT | 2024-10-01 | 2024-11-01 | (4) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | (7) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 FEDNUM changed.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2024-11-01 | SFHWY00446
Southcoast Region | ANTADVDT | 2024-10-01 | 2024-11-01 | (3) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | (5) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-11-01 | SFHWY00481
Southcoast Region | ANTADVDT | 2024-10-01 | 2024-12-01 | (3) [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | (7) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to October 2024.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2024-12-01 | SFHWY00438
Southcoast Region | DESCRIPTION |  | The project includes highway milling and paving, guardrail replacement, culvert replacement and lining, grading, and striping. | (1) [on 2024.04.15 the ANTADVDT changed to June 2024.] | (2) [on 2023.10.25 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.] | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | Ketchikan | 2024-07-01 | SFHWY00536
Southcoast Region | DESCRIPTION | Replace automated vehicle gate 3; Replace and widen vehicle gate 9 from 20' to 24'; Replace non-automated vehicle gate 10; Replace locking systems for vehicle gates 3 and 9; Replace locking systems for fence pedestrian gates 4 and 11; Remove vehicle gates 5 and 6 and replace with fence; Replace and relocate pedestrian gate 11; Repair approximately 1200-1500 feet of fence line. | Replace the electric vehicle gates, Gate #3 and Gate #9 and install up-to-date security systems; Increase width of Gate #9 entrance from 20’ to 24’; Replace pedestrian Gate 4; Replace non-automated vehicle gate #10 with a new non-automated swing gate; Remove vehicle gates 5, 6, and pedestrian gate 8 by fencing them over; Install compatible/compliant security entry systems on pedestrian gates, Gates #4 and #11; Replace approximately 600 feet of fence. | (6) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | (14) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.04.15 ENGEST changed.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-07-01 | SFAPT00412
Southcoast Region | FEDNUM | 3-02-0158-0XX-202X | 3-02-0158-022-2021 | (12) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.] | (13) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2024-07-01 | SFAPT00144
Southcoast Region | FEDNUM | N/A | 3-02-0323-018-2024 | (6) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.] | (14) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.04.15 ENGEST changed.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-07-01 | SFAPT00412
Southcoast Region | PROJNAME | JNU L00P RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | JNU LOOP RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP |  | (6) [on 2023.03.15 project was added.]; [on 2023.05.15 ENGEST changed.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the project was removed.]; [on 2024.04.15 project was added.] | JNU LOOP RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | Juneau | 2025-03-01 | SFHWY00403