## 2024.07.24 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  | (4) [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (7) [on 2023.10.25 project was added.]; [on 2023.12.15 the ANTADVDT changed to March 2024.]; [on 2024.04.15 ADDLINFO changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | ANC SECURITY FENCING IMPROVEMENTS 2023 | Anchorage | 2024-07-01 | CFAPT00983A | CFAPT00983A | 3-02-0016-XXX-2023 | Jennifer M Lombardo | (907)266-2731 | Remove and replace approximately 1,000 feet of security fence along the northeast edge of the airfield. Project includes clearing, grubbing, embankment extension and replacing swing gates. To be advertised with CFAPT00880 ANC Taxiway R North and Taxilane U Improvements project. | Project will advertise with Taxiway R North Improvements | Between $200,000 and $500,000
Central Region | (DELETED) |  |  | (3) [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (10) [on 2023.04.14 project was added.]; [on 2023.07.14 PHONENUM changed.]; [on 2023.07.14 PROJMAN changed.]; [on 2023.10.25 FEDNUM changed.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | ANC TAXIWAY R NORTH & Taxilane U IMPROVEMENTS | Anchorage | 2024-07-01 | CFAPT00880 | CFAPT00880 | AIP 3-02-0016-XXX-2024 | Kim D Satterfield | (907)269-0623 | This project will design and construct improvements for TW R from approximately TL P to TW Q for Airplane Design Group 6. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/00880_PSE_Review_Plans_TAL.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.06.19 project was added.] | ANC Gate B4 Passenger Boarding Bridge Replacement Design-Build | Anchorage | 2024-06-01 | CFAPT01201 | CFAPT01201 | AIP 3-02-0016-XXX-2024 | Ashley B Devore | (907)269-6200 | This project will replace the existing Passenger Boarding Bridge (PBB) at Gate B4 with a new PBB through a Design-Build project. | Remove and replace existing Gate B4 PBB with new updated PBB. This will be a Design-Build project. | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (3) [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | (7) [on 2023.12.15 project was added.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.04.15 LOCATION changed.]; [on 2024.04.15 REGION changed.]; [on 2024.05.16 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.06.19 DESCRIPTION changed.] | Kalsin Bay Maintenance Station - Phase 2 | Kodiak Island Borough | 2024-06-01 | CPFAC00080 | CPFAC00080 | N/A | Eric F Hershey | (907)269-5572 | This state funded contract includes miscellaneous upgrades required for full functionality of the Kalsin Bay Maintenance Station in Kodiak, Alaska. Work includes concrete apron replacement, building envelope upgrades, domestic water filtration, wastewater holding tank modifications, fuel tank relocation, and other mechanical and electrical upgrades. This contract includes one (1) additive alternate for installation of a new emergency generator system. |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  |  | GLENN HIGHWAY MILEPOST 86 ROCKFALL MITIGATION | Matanuska Valley | 2024-07-01 | CDRER01227 | CDRER01227 | N/A | Jacob A Dilley | (907)707-1922 | Project will complete slope scaling and rockfall mitigation to reduce rockfall occurrences on the Glenn Highway near milepost 86 |  | Between $500,000 and $1,000,000
Central Region | ADDED |  |  |  | (2) [on 2023.07.14 project was added.]; [on 2023.08.21 the project was removed.] | GLENN HIGHWAY: AIRPORT HEIGHTS TO PARK HIGHWAY REHAB | Anchorage | 2025-06-01 | CFHWY00545 | CFHWY00545 | 1656 | Chris L Bentz | (907)707-1912 | This project will rehabilitate the Glenn Highway from the intersection with Airport Heights ( MP 0.0) to the Parks Highway Interchange ( MP 33.0). The project may include Bridge work, roadside hardware, drainage Improvements, interchange improvements, ADA improvements, utilities and safety improvements. | Project likely to be phased for construction. | Greater than $100,000,000
Central Region | ADDED |  |  |  | (6) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.09.15 project was added.]; [on 2023.10.25 the project was removed.] | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | Anchorage | 2025-06-01 | CFHWY00502 | CFHWY00502 | 0A31063 | Noah C King | (907)269-0657 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards. |  | Pending
Central Region | ADDED |  |  |  | (9) [on 2022.07.12 project was added.]; [on 2022.08.14 the project was removed.]; [on 2023.04.14 project was added.]; [on 2023.07.14 the project was removed.]; [on 2023.08.21 project was added.]; [on 2023.09.15 ENGEST changed.]; [on 2023.09.15 PHONENUM changed.]; [on 2023.09.15 PROJMAN changed.]; [on 2023.10.25 the project was removed.] | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | Anchorage | 2025-06-01 | CFHWY00503 | CFHWY00503 | 1644 | Noah C King | (907)269-0657 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements. |  | Between $10,000,000 and $20,000,000
Central Region | ADDED |  |  |  |  | ANC PFAS Remediation | Anchorage | 2025-03-01 | CSAPT01228 | CSAPT01228 | N/A | Jennifer M Lombardo | (907)266-2731 | Perform PFAS Remediation measures at ANC. Remediation includes installing permeable reactive barriers using an activated carbon mixture within the Postmark Bog and ARFF building. Project also includes replacement of two manholes within the Postmark Bog. |  | Between $500,000 and $1,000,000
Central Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (4) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | (6) [on 2023.08.21 project was added.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-09-01 | CFAPT01136
Central Region | ANTADVDT | 2024-08-01 | 2024-10-01 | (5) [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | (12) [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.03.15 ENGEST changed.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | Wasilla | 2024-10-01 | CFHWY00883
Central Region | ANTADVDT | 2024-08-01 | 2024-10-01 | (2) [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.] | (7) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.11.15 ENGEST changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to August 2024.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-10-01 | CFAPT00572
Central Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (12) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (19) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | Anchorage | 2024-08-01 | CSAPT00931
Central Region | ANTADVDT | 2024-07-01 | 2024-10-01 | (5) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.] | (11) [on 2022.05.16 the ANTADVDT changed to February 2023.]; [on 2022.05.16 PHONENUM changed.]; [on 2022.05.16 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to March 2023.]; [on 2022.09.13 ENGEST changed.]; [on 2022.10.20 ADDLINFO changed.]; [on 2023.01.17 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to July 2023.]; [on 2023.06.15 the ANTADVDT changed to September 2023.]; [on 2023.07.14 the project was removed.]; [on 2024.04.15 project was added.] | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | Kenai | 2024-10-01 | CFHWY00253
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (3) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | (7) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-07-01 | CSAPT01146
Central Region | ANTADVDT | 2024-06-01 | 2024-08-01 | (7) [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | (10) [on 2023.09.15 project was added.]; [on 2023.10.25 ENGEST changed.]; [on 2023.11.15 the ANTADVDT changed to November 2023.]; [on 2023.12.15 the ANTADVDT changed to December 2023.]; [on 2024.01.16 the ANTADVDT changed to January 2024.]; [on 2024.02.14 the ANTADVDT changed to February 2024.]; [on 2024.02.14 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | Anchorage | 2024-08-01 | CFAPT00930
Central Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (2) [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | (8) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.05.16 REGION changed.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | Valdez Airport Snow Removal Equipment and Deicing Material Storage Building | Valdez | 2024-07-01 | Z618600000
Central Region | ANTADVDT | 2024-10-01 | 2025-03-01 | (9) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to October 2024.] | (14) [on 2022.01.18 the ANTADVDT changed to May 2022.]; [on 2022.04.15 the ANTADVDT changed to July 2022.]; [on 2022.05.16 the ANTADVDT changed to October 2022.]; [on 2022.08.14 the ANTADVDT changed to February 2023.]; [on 2022.08.14 ENGEST changed.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2023.01.17 the ANTADVDT changed to August 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.09.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to October 2024.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.] | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | Anchorage | 2025-03-01 | CFHWY00260
Central Region | DESCRIPTION | This project will remove and replace the existing single bay SREB at the same location. | This project will remove the existing single bay Snow Removal Equipment Building (SREB) at False Pass Airport and construct a new SREB at the same location. | (1) [on 2024.06.19 the ANTADVDT changed to July 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | False Pass Airport Snow Removal Equipment Building | False Pass | 2024-07-01 | SFAPT00416
Central Region | FEDNUM | N/A | 3-02-0195-002-2024 | (2) [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.] | (7) [on 2022.12.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.11.15 ENGEST changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to August 2024.] | NIGHTMUTE AIRPORT IMPROVEMENTS | Nightmute | 2024-10-01 | CFAPT00572
Central Region | FEDNUM | N/A | AIP 3-02-0097-005-2024 | (1) [on 2024.06.19 the ANTADVDT changed to July 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | False Pass Airport Snow Removal Equipment Building | False Pass | 2024-07-01 | SFAPT00416
Central Region | LOCATION | Central Region | False Pass | (1) [on 2024.06.19 the ANTADVDT changed to July 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | False Pass Airport Snow Removal Equipment Building | False Pass | 2024-07-01 | SFAPT00416
Central Region | PROJNAME | FALSE PASS SREB (DFS) | False Pass Airport Snow Removal Equipment Building | (1) [on 2024.06.19 the ANTADVDT changed to July 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | False Pass Airport Snow Removal Equipment Building | False Pass | 2024-07-01 | SFAPT00416
Central Region | PROJNAME | VALDEZ AIRPORT SNOW REMOVAL EQUIPMENT & DEICING BLDGS REPLM | Valdez Airport Snow Removal Equipment and Deicing Material Storage Building | (2) [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | (8) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.05.16 REGION changed.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | Valdez Airport Snow Removal Equipment and Deicing Material Storage Building | Valdez | 2024-07-01 | Z618600000
Northern Region | (DELETED) |  |  |  | (1) [on 2024.06.19 project was added.] | FIA RUNWAY 2L/20R LIGHTING REHABILITATION | Fairbanks North Star Borough | 2024-07-01 | NFAPT00889 | NFAPT00889 | N/A | RJ Stumpf | (907)474-2587 | Replace the 2L/20R runway lighting at the Fairbanks International Airport. |  | Between $1,000,000 and $2,500,000
Northern Region | (DELETED) |  |  | (2) [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | (5) [on 2023.09.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.06.19 DESCRIPTION changed.]; [on 2024.06.19 ENGEST changed.] | Gulkana River Boat Launch Fencing | Gulkana | 2024-06-01 | NSHWY00497a | NSHWY00497a | N/A | Scott L Maybrier | (907)451-5380 | Construct fencing along the woods next to the Gulkana River Bridge, near Mile 126.5 of the Richardson Highway, |  | Between $200,000 and $500,000
Northern Region | ADDED |  |  |  |  | DALTON HIGHWAY MP 245-274 RESURFACING | Coldfoot | 2025-02-01 | NFHWY00764 | NFHWY00764 | 655016 | David K Fischer | (907)451-5357 | Resurface the Dalton Highway between MP 245-274. Project includes bridge work (#1333, #1439, #1519, #1520, #4042, #4043, #4050, #7098, and #7099), drainage improvements, roadside hardware, spot repairs, and utilities. |  | Pending
Northern Region | ADDED |  |  |  |  | Gulkana River Boat Launch Fencing | Gulkana | 2024-07-01 | NSHWY0497A | NSHWY0497A | N/A | Scott L Maybrier | (907)451-5380 | Install 3,333' feet of 6' high chain link fencing, including vehicle gates and no parking signs, around the woods next to the Gulkana River boat launch at MP 126.5 of the Richardson Highway. |  | Between $200,000 and $500,000
Northern Region | ADDED |  |  |  | (8) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 FEDNUM changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2023.03.15 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.10.25 the project was removed.] | Buckland Airport Improvements | Buckland | 2025-06-01 | NFAPT00604 | NFAPT00604 | 3-02-0399-___-____ | Jonathan J Hutchinson | (907)451-5479 | Rehabilitate the runway and taxiway, stabilize the embankments, resurface the airport access road, apply dust palliative, and replace the airport lighting system. | Pushed due to funding availability | Between $10,000,000 and $20,000,000
Northern Region | ADDED |  |  |  |  | DALTON HWY MP 247-289 AND MP 305-362 DELINEATOR RPLMT (HSIP) | Northern Region | 2025-06-01 | NFHWY00947 | NFHWY00947 | 656007 | Ethan E Graetz | (907)451-2281 | Install and replace roadside delineators along the Dalton Highway from MP 247 - 289 and MP 305 - 362. |  | Pending
Northern Region | ANTADVDT | 2024-12-01 | 2025-01-01 | (3) [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.] | (12) [on 2022.01.18 project was added.]; [on 2022.04.15 LOCATION changed.]; [on 2022.04.15 PROJNAME changed.]; [on 2022.08.14 PROJNAME changed.]; [on 2022.10.20 PROJNAME changed.]; [on 2022.12.17 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.09.15 the project was removed.]; [on 2024.01.16 project was added.] | Richardson Highway MP 148-173 (CONST MP 167-173) | Paxson | 2025-01-01 | Z631860000
Northern Region | ANTADVDT | 2024-07-01 | 2024-11-01 | (2) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.] | (4) [on 2023.02.24 project was added.]; [on 2023.06.15 PROJNAME changed.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.] | Seppala Drive Upgrade | Nome | 2024-11-01 | Z620030000
Northern Region | ANTADVDT | 2024-06-01 | 2024-09-01 | (1) [on 2024.05.16 the ANTADVDT changed to June 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | City of Fairbanks Systemic Signal Upgrades - Stage 1 (HSIP) | Fairbanks | 2024-09-01 | NFHWY00905
Northern Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (1) [on 2024.06.19 the ANTADVDT changed to June 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to June 2024.] | Glenn/Richardson Highway Right of Way Reconciliation | Glennallen | 2024-07-01 | HSHWY00018
Northern Region | ANTADVDT | 2024-06-01 | 2024-09-01 | (1) [on 2024.05.16 the ANTADVDT changed to June 2024.] | (2) [on 2024.04.15 project was added.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | Northern Region Systemic Signal Upgrades - Stage 1 (HSIP) | Regionwide | 2024-09-01 | NFHWY00904
Southcoast Region | (DELETED) |  |  |  | (3) [on 2022.08.14 project was added.]; [on 2022.11.17 the project was removed.]; [on 2024.04.15 project was added.] | KTN WOLFE POINT SLOPE STABILITY IMPROVEMENTS | Ketchikan | 2024-04-01 | SFHWY00432 | SFHWY00432 | 920032 | James L Brown | (907)465-1796 | The project will repair unstable slopes from MP 3.0 to MP 3.9 on Tongass Highway. | Work will need to be shifted into the Summer to allow for blasting at maximum availability of daylight hours. | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  | (1) [on 2023.10.25 the ANTADVDT changed to August 2024.] | (6) [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the project was removed.]; [on 2024.02.14 project was added.]; [on 2024.04.15 the project was removed.]; [on 2024.05.16 project was added.] | SGY, HNH, PSG ROADWAY & CULVERTS - DEC 20 SE PR | Southcoast Region | 2025-04-01 | SFHWY00447 | SFHWY00447 | N/A | Joel D Osburn | (907)465-4409 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2020 01 HNH001, AK 2020 01 HNH002, AK 2021 01 PTG002, AK 2021 01 PTG003, and AK 2021 01 SGY001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites in Hoonah, Petersburg & Skagway. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (5) [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | (10) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to December 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 the ANTADVDT changed to May 2024.]; [on 2024.01.16 DESCRIPTION changed.]; [on 2024.01.16 ENGEST changed.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | JNU Waydelich Creek: Upper & Lower Wall Repairs | Juneau | 2024-07-01 | SFHWY00414 | SFHWY00414 | 93003 | Joel D Osburn | (907)465-4409 | This project will construct permanent repairs (PR) to the upper & lower portion of the Waydelich Creek retaining wall. The upper wall was damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK2021-1 JNS003. Repairs may include, but are not limited to, asphalt, embankment, geotextile, concrete, steel reinforcement, riprap, drainage, roadside hardware, and utilities. Phase code is T02015. The lower wall has years of deterioration & requires additional work to bring the full wall up to seismic code & extend the service life another 40 years. This portion of the project has PM-funding. Phase code is T02A15. |  | Between $1,000,000 and $2,500,000
Southcoast Region | (DELETED) |  |  | (12) [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.] | (14) [on 2022.09.13 project was added.]; [on 2022.10.20 the ANTADVDT changed to October 2022.]; [on 2022.11.17 the ANTADVDT changed to November 2022.]; [on 2022.12.17 the ANTADVDT changed to December 2022.]; [on 2023.01.17 the ANTADVDT changed to January 2023.]; [on 2023.02.24 the ANTADVDT changed to March 2023.]; [on 2023.03.15 the ANTADVDT changed to April 2023.]; [on 2023.04.14 the ANTADVDT changed to May 2023.]; [on 2023.06.15 the ANTADVDT changed to August 2023.]; [on 2023.07.14 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to March 2024.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.06.19 FEDNUM changed.] | KDK AIRPORT PERIMETER FENCING UPGRADES | Kodiak | 2024-07-01 | SFAPT00144 | SFAPT00144 | 3-02-0158-022-2021 | James L Brown | (907)465-1796 | Project will replace/upgrade access controls and gates to meet 49 CFR 1542 requirements. Replace existing fencing when needed. |  | Between $5,000,000 and $10,000,000
Southcoast Region | (DELETED) |  |  | (7) [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (17) [on 2022.02.22 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 the project was removed.]; [on 2022.05.16 project was added.]; [on 2022.10.20 the ANTADVDT changed to April 2023.]; [on 2022.10.20 DESCRIPTION changed.]; [on 2023.02.24 the ANTADVDT changed to September 2023.]; [on 2023.03.15 DESCRIPTION changed.]; [on 2023.04.14 the ANTADVDT changed to December 2023.]; [on 2023.07.14 the ANTADVDT changed to March 2024.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.02.14 the ANTADVDT changed to June 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.06.19 DESCRIPTION changed.]; [on 2024.06.19 FEDNUM changed.] | WRG GATES AND SECURITY UPGRADES | Wrangell | 2024-07-01 | SFAPT00412 | SFAPT00412 | 3-02-0323-018-2024 | David B Epstein | (907)465-4483 | Replace the electric vehicle gates, Gate #3 and Gate #9 and install up-to-date security systems; Increase width of Gate #9 entrance from 20’ to 24’; Replace pedestrian Gate 4; Replace non-automated vehicle gate #10 with a new non-automated swing gate; Remove vehicle gates 5, 6, and pedestrian gate 8 by fencing them over; Install compatible/compliant security entry systems on pedestrian gates, Gates #4 and #11; Replace approximately 600 feet of fence. |  | Between $2,500,000 and $5,000,000
Southcoast Region | ADDED |  |  |  |  | KDK AREAWIDE ROCKFALL TREATMENT PRESERVATION | Kodiak | 2025-05-01 | SFHWY00514 | SFHWY00514 | 11051 | Travis W Eckhoff | (907)465-1171 | This project is to remove rockfall debris from existing rockfall catchment ditches to restore functionality. |  | Between $500,000 and $1,000,000
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-01-01 | (6) [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.] | (8) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to March 2024.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.06.19 the ANTADVDT changed to December 2024.] | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | Haines | 2025-01-01 | SDRER00436
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-01-01 | (4) [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.] | (8) [on 2023.02.24 project was added.]; [on 2023.06.15 the ANTADVDT changed to April 2024.]; [on 2023.06.15 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to December 2024.] | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | Juneau | 2025-01-01 | SFHWY00438
Southcoast Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (8) [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (21) [on 2022.02.22 the project was removed.]; [on 2022.04.15 project was added.]; [on 2022.05.16 the ANTADVDT changed to April 2023.]; [on 2022.06.15 the project was removed.]; [on 2022.07.12 project was added.]; [on 2022.08.14 PHONENUM changed.]; [on 2022.08.14 PROJMAN changed.]; [on 2022.09.13 PHONENUM changed.]; [on 2022.09.13 PROJMAN changed.]; [on 2022.10.20 the ANTADVDT changed to July 2023.]; [on 2022.11.17 the ANTADVDT changed to August 2023.]; [on 2022.12.17 the ANTADVDT changed to September 2023.]; [on 2023.01.17 the ANTADVDT changed to November 2023.]; [on 2023.03.15 the ANTADVDT changed to December 2023.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 DESCRIPTION changed.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | Juneau | 2024-08-01 | SFHWY00359
Southcoast Region | ANTADVDT | 2024-07-01 | 2024-09-01 | (2) [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (4) [on 2023.10.25 project was added.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.06.19 DESCRIPTION changed.] | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | Ketchikan | 2024-09-01 | SFHWY00536
Southcoast Region | ANTADVDT | 2024-06-01 | 2024-07-01 | (9) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | (15) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-07-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2025-03-01 | 2025-06-01 | (2) [on 2024.02.14 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to March 2025.] | (5) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2023.12.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to March 2025.] | HNS LUTAK ROAD 437114 - DEC 20 SE PR | Haines | 2025-06-01 | SDRER00448
Southcoast Region | ANTADVDT | 2024-11-01 | 2024-12-01 | (3) [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | (5) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | HNS HIGHWAY MPT1-9- DEC 20 SE PR | Haines | 2024-12-01 | SFHWY00440
Southcoast Region | ANTADVDT | 2024-11-01 | 2025-01-01 | (5) [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | (8) [on 2023.06.15 project was added.]; [on 2023.08.21 the ANTADVDT changed to May 2024.]; [on 2023.10.25 the ANTADVDT changed to August 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to September 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.04.15 FEDNUM changed.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | HNS HWY / LUTAK ROAD - DEC 20 SE PR | Haines | 2025-01-01 | SFHWY00446
Southcoast Region | ANTADVDT | 2024-11-01 | 2024-12-01 | (4) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | (6) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-12-01 | SFHWY00481
Southcoast Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (4) [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.02.14 the ANTADVDT changed to July 2024.]; [on 2024.04.15 the ANTADVDT changed to September 2024.] | (17) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to July 2024.]; [on 2024.04.15 the ANTADVDT changed to September 2024.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2024-10-01 | SFAPT00178
Southcoast Region | DESCRIPTION | This project will design and construct a chip seal overlay on Glacier Highway, between Brotherhood Bridge and the Auke Bay Roundabout. | This project will design and construct a chip seal overlay on Glacier Highway, between Brotherhood Bridge & the AMHS Ferry Terminal in Auke Bay. | (4) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | (6) [on 2023.06.15 project was added.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.04.15 the ANTADVDT changed to October 2024.]; [on 2024.06.19 the ANTADVDT changed to November 2024.] | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | Juneau | 2024-12-01 | SFHWY00481