## 2024.08.15 tas-diff-add-del
REGION | CHANGE FIELD | ORIGINAL VALUE | UPDATED VALUE | DATE HISTORY | ALL HISTORY | PROJNAME | LOCATION | ANTADVDT | PROJID | STATENUM | FEDNUM | PROJMAN | PHONENUM | DESCRIPTION | ADDLINFO | ENGEST
Central Region | (DELETED) |  |  |  | (3) [on 2022.10.20 project was added.]; [on 2022.11.17 the project was removed.]; [on 2024.04.15 project was added.] | HSIP: BOGARD AT ENGSTROM RD/GREEN FOREST DR INTER IMP | Wasilla | 2025-02-01 | CFHWY00453 | CFHWY00453 | 1630 | Chris L Bentz | (907)707-1912 | Reconstruction, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. |  | Pending
Central Region | (DELETED) |  |  | (3) [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (6) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.]; [on 2024.02.14 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTIO | Anchorage | 2024-07-01 | CFAPT00881 | CFAPT00881 | N/A | Aaron C Hughes | (907)269-0523 | This project will design and construct improvements for the North Terminal Northside Aprons and Taxilane. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (4) [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.] | (8) [on 2023.08.21 project was added.]; [on 2023.10.25 the ANTADVDT changed to April 2024.]; [on 2023.10.25 ENGEST changed.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.] | ANC POSTMARK DRIVE REPAIRS 2024 | Anchorage | 2024-07-01 | CSAPT01146 | CSAPT01146 | N/A | Jennifer M Lombardo | (907)266-2731 | Rehabilitate Postmark Drive from Rockwell Avenue to Dehavilland Avenue. Project includes pavement planning, paving, striping, and drainage. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  | (3) [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (5) [on 2024.02.14 project was added.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 DESCRIPTION changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | ANC TERMINAL WATER MAIN IMPROVEMENTS | Anchorage | 2024-07-01 | CFAPT00993A | CFAPT00993A | AIP 3-02-0016-228-2024 | Kim D Satterfield | (907)269-0623 | This federally funded project will rehabilitate approximately 6,000 feet of water pipe around the North Terminal, C Concourse, A Concourse, and Old Airfield Maintenance (OAM) building at the Ted Stevens Anchorage International Airport. Improvements will also include hydrant replacements, valve replacements, and grouting a decommissioned water pipe segment under the South Terminal. To be advertised with CFAPT00881 ANC NORTH TERMINAL NORTHSIDE APRONS & TAXILANE RECONSTRUCTION. | <a class=linkcopy href=https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/9_00993%20ANC%20Terminal%20Water%20Main%20Improvements%20-%20TAL.pdf>Preliminary Plans (~21 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  | (1) [on 2024.06.19 the ANTADVDT changed to July 2024.] | (6) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 DESCRIPTION changed.]; [on 2024.07.24 FEDNUM changed.]; [on 2024.07.24 LOCATION changed.]; [on 2024.07.24 PROJNAME changed.] | False Pass Airport Snow Removal Equipment Building | False Pass | 2024-07-01 | SFAPT00416 | SFAPT00416 | AIP 3-02-0097-005-2024 | Matthew R Epp | (907)764-4881 | This project will remove the existing single bay Snow Removal Equipment Building (SREB) at False Pass Airport and construct a new SREB at the same location. |  | Between $1,000,000 and $2,500,000
Central Region | (DELETED) |  |  |  | (1) [on 2024.07.24 project was added.] | GLENN HIGHWAY MILEPOST 86 ROCKFALL MITIGATION | Matanuska Valley | 2024-07-01 | CDRER01227 | CDRER01227 | N/A | Jacob A Dilley | (907)707-1922 | Project will complete slope scaling and rockfall mitigation to reduce rockfall occurrences on the Glenn Highway near milepost 86 |  | Between $500,000 and $1,000,000
Central Region | (DELETED) |  |  | (3) [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.] | (10) [on 2023.05.15 project was added.]; [on 2023.10.25 DESCRIPTION changed.]; [on 2024.02.14 PHONENUM changed.]; [on 2024.02.14 PROJMAN changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 ENGEST changed.]; [on 2024.05.16 REGION changed.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.]; [on 2024.07.24 PROJNAME changed.] | Valdez Airport Snow Removal Equipment and Deicing Material Storage Building | Valdez | 2024-07-01 | Z618600000 | Z618600000 | N/A | Lauren A Staft | (907)451-5424 | Construct a new three bay snow removal equipment building including space for lighting controls and backup generators and a new deicing material storage building. |  | Between $10,000,000 and $20,000,000
Central Region | (DELETED) |  |  |  | (3) [on 2023.07.14 project was added.]; [on 2023.08.21 the project was removed.]; [on 2024.07.24 project was added.] | GLENN HIGHWAY: AIRPORT HEIGHTS TO PARK HIGHWAY REHAB | Anchorage | 2025-06-01 | CFHWY00545 | CFHWY00545 | 1656 | Chris L Bentz | (907)707-1912 | This project will rehabilitate the Glenn Highway from the intersection with Airport Heights ( MP 0.0) to the Parks Highway Interchange ( MP 33.0). The project may include Bridge work, roadside hardware, drainage Improvements, interchange improvements, ADA improvements, utilities and safety improvements. | Project likely to be phased for construction. | Greater than $100,000,000
Central Region | (DELETED) |  |  | (1) [on 2023.10.25 the ANTADVDT changed to September 2024.] | (8) [on 2022.05.16 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.07.14 project was added.]; [on 2023.10.25 the ANTADVDT changed to September 2024.]; [on 2023.11.15 the project was removed.]; [on 2024.04.15 project was added.]; [on 2024.05.16 the project was removed.]; [on 2024.06.19 project was added.] | AMATS: 4TH AVE SIGNAL & LIGHTING UPGRADE | Anchorage | 2025-05-01 | CFHWY00555 | CFHWY00555 | 1657 | Julia R Hanson | (907)269-0753 | This AMATS funded project will reconstructed the traffic signal and street lighting system on 4th Ave between A Street and Ingra Street. Work may included signing, Striping, ATRs, drainage, paving, pedestrian & ADA amenities, utility relocation, landscaping and roadside hardware. |  | Between $5,000,000 and $10,000,000
Central Region | ADDED |  |  |  |  | Seward Highway MP 98.5 – 118 Signage Project | Anchorage | 2024-08-01 | CSHWY01203 | CSHWY01203 | N/A | Sean M Baski | (907)269-0566 | This project will replace existing signs that do not meet ATM standards, install signs in advance of pullouts and recreation sites, and install additional mile points to help with wayfinding and reduce crashes. |  | Pending
Central Region | ADDED |  |  |  |  | WASILLA-FISHHOOK - MAIN STREET REHABILITATION | Wasilla | 2025-02-01 | Z600770000 | Z600770000 | 1408 | Clint J Adler | (907)707-1911 | Construct a one-way couplet in downtown Wasilla bounded by Bogard Road, KGB/Main Street, Yenlo/Talkeetna Street and the Palmer Wasilla Highway. The exact location of the couplet will be determined during the environmental and preliminary design phase. Improvements to Bogard Road will be necessary to make the couplet functional. Work will consist of new road construction, lane reconfigurations, signals, new pavement, signing and striping, and sidewalks. |  | Between $40,000,000 and $50,000,000
Central Region | ADDED |  |  |  | (4) [on 2022.03.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2022.08.14 project was added.]; [on 2023.06.15 the project was removed.] | ANC TAXIWAY Z IMPROVEMENTS EAST | Anchorage | 2025-07-01 | CFAPT00835 | CFAPT00835 | N/A | Philip W Cheasebro | (907)269-0606 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron. |  | Pending
Central Region | ADDED |  |  |  |  | KENAI SPUR HIGHWAY MP 29-38 PAVEMENT PRESERVATION | Kenai | 2025-07-01 | CFHWY00852 | CFHWY00852 | 490017 | Aaron L Hunting | (907)269-0546 | This project will resurface the Kenai Spur Highway between mileposts 29 and 38. Improvements to roadside hardware, safety, drainage, signs, and minor structural section improvements may also be included. |  | Between $5,000,000 and $10,000,000
Central Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (13) [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.] | (20) [on 2022.02.22 project was added.]; [on 2022.03.15 the ANTADVDT changed to September 2022.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.03.15 PHONENUM changed.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to November 2022.]; [on 2022.07.12 PROJMAN changed.]; [on 2022.09.13 the ANTADVDT changed to January 2023.]; [on 2022.11.17 the ANTADVDT changed to February 2023.]; [on 2023.01.17 the ANTADVDT changed to March 2023.]; [on 2023.02.24 the ANTADVDT changed to May 2023.]; [on 2023.05.15 the ANTADVDT changed to October 2023.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.02.14 DESCRIPTION changed.]; [on 2024.04.15 PROJNAME changed.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.]; [on 2024.07.24 the ANTADVDT changed to August 2024.] | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | Anchorage | 2024-09-01 | CSAPT00931
Central Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (1) [on 2024.01.16 the ANTADVDT changed to August 2024.] | (5) [on 2023.11.15 project was added.]; [on 2023.12.15 ENGEST changed.]; [on 2024.01.16 the ANTADVDT changed to August 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.02.14 PHONENUM changed.] | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | Wasilla | 2024-09-01 | CFHWY00723
Central Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (7) [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | (12) [on 2023.03.15 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 the ANTADVDT changed to November 2023.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.09.15 ADDLINFO changed.]; [on 2023.10.25 the ANTADVDT changed to January 2024.]; [on 2024.01.16 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | Wasilla | 2024-09-01 | CFHWY01083
Central Region | ANTADVDT | 2024-08-01 | 2024-09-01 | (3) [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | (8) [on 2023.04.14 project was added.]; [on 2023.05.15 PHONENUM changed.]; [on 2023.06.15 PHONENUM changed.]; [on 2023.06.15 PROJMAN changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2023.11.15 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.] | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | Wasilla | 2024-09-01 | CFHWY01084
Central Region | ANTADVDT | 2024-08-01 | 2025-02-01 |  | (1) [on 2024.05.16 project was added.] | PETERS CREEK BRIDGE (1367) EMERGENCY REPAIRS | Peters Creek | 2025-02-01 | CDRER01160
Central Region | ANTADVDT | 2024-08-01 | 2025-03-01 |  | (1) [on 2023.11.15 project was added.] | SEWARD HWY MP 90-99 PAVEMENT PRESERVATION | Regionwide | 2025-03-01 | CFHWY00850
Central Region | ANTADVDT | 2025-01-01 | 2025-02-01 | (1) [on 2024.05.16 the ANTADVDT changed to January 2025.] | (3) [on 2023.12.15 project was added.]; [on 2024.01.16 ENGEST changed.]; [on 2024.05.16 the ANTADVDT changed to January 2025.] | ANC TAXILANE E IMPROVEMENTS | Anchorage | 2025-02-01 | CFAPT01002
Central Region | ANTADVDT | 2024-07-01 | 2024-09-01 | (3) [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | (4) [on 2023.11.15 project was added.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.] | ANC FIRING RANGE MAINTENANCE | Anchorage | 2024-09-01 | CSAPT01152
Central Region | ANTADVDT | 2024-07-01 | 2024-08-01 |  | (3) [on 2023.11.15 project was added.]; [on 2024.06.19 DESCRIPTION changed.]; [on 2024.06.19 FEDNUM changed.] | CHENEGA BAY AIRPORT LIGHTING IMPROVEMENTS | Chenega Bay | 2024-08-01 | CFAPT01021
Central Region | ANTADVDT | 2024-07-01 | 2024-11-01 | (1) [on 2024.06.19 the ANTADVDT changed to July 2024.] | (6) [on 2024.04.15 project was added.]; [on 2024.05.16 ADDLINFO changed.]; [on 2024.05.16 DESCRIPTION changed.]; [on 2024.05.16 ENGEST changed.]; [on 2024.05.16 PROJNAME changed.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | Nenana Station Shop Roof Improvements | Nenana | 2024-11-01 | 2501000065A
Central Region | ANTADVDT | 2024-11-01 | 2025-01-01 | (1) [on 2024.04.15 the ANTADVDT changed to November 2024.] | (5) [on 2022.04.15 project was added.]; [on 2022.06.15 the project was removed.]; [on 2023.08.21 project was added.]; [on 2024.01.16 PROJNAME changed.]; [on 2024.04.15 the ANTADVDT changed to November 2024.] | HSIP: PALMER-FISHHOOK RD & TRUNK RD ROUNDABOUT | Palmer | 2025-01-01 | CFHWY00829
Central Region | ANTADVDT | 2024-10-01 | 2024-12-01 | (3) [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2023.11.15 the ANTADVDT changed to October 2024.] | (8) [on 2022.11.17 project was added.]; [on 2023.05.15 PROJNAME changed.]; [on 2023.07.14 ENGEST changed.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to May 2024.]; [on 2023.11.15 the ANTADVDT changed to October 2024.]; [on 2024.02.14 PHONENUM changed.] | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | Wasilla | 2024-12-01 | CFHWY00622
Central Region | ANTADVDT | 2024-09-01 | 2025-04-01 |  | (1) [on 2023.11.15 project was added.] | AMATS: VFW ROAD - EAGLE RIVER LP TO EAGLE RIVER RD PP | Eagle River | 2025-04-01 | CFHWY00732
Central Region | ANTADVDT | 2024-09-01 | 2024-10-01 | (5) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | (7) [on 2023.08.21 project was added.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-10-01 | CFAPT01136
Central Region | ENGEST | Between $20,000,000 and $30,000,000 | Between $40,000,000 and $50,000,000 | (1) [on 2024.05.16 the ANTADVDT changed to January 2025.] | (3) [on 2023.12.15 project was added.]; [on 2024.01.16 ENGEST changed.]; [on 2024.05.16 the ANTADVDT changed to January 2025.] | ANC TAXILANE E IMPROVEMENTS | Anchorage | 2025-02-01 | CFAPT01002
Central Region | ENGEST | Between $2,500,000 and $5,000,000 | Between $5,000,000 and $10,000,000 |  | (1) [on 2023.11.15 project was added.] | AMATS: VFW ROAD - EAGLE RIVER LP TO EAGLE RIVER RD PP | Eagle River | 2025-04-01 | CFHWY00732
Central Region | FEDNUM | 3-02-0016-XXX-2024 | 3-02-0016-XXX-2025 | (5) [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | (7) [on 2023.08.21 project was added.]; [on 2024.01.16 the ANTADVDT changed to April 2024.]; [on 2024.01.16 ENGEST changed.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to July 2024.]; [on 2024.06.19 the ANTADVDT changed to August 2024.]; [on 2024.07.24 the ANTADVDT changed to September 2024.] | ANC WEST PERIMETER ROAD | Anchorage | 2024-10-01 | CFAPT01136
Marine Highways | PHONENUM | (907)228-6829 | None |  | (1) [on 2024.04.15 project was added.] | M/V Columbia CPP System Replacement | Statewide | 2024-03-01 | SAMHS00147_C
Northern Region | (DELETED) |  |  | (1) [on 2024.06.19 the ANTADVDT changed to July 2024.] | (4) [on 2023.06.15 project was added.]; [on 2023.10.25 the project was removed.]; [on 2024.02.14 project was added.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | Deadhorse Airport Improvements | Deadhorse | 2024-07-01 | NFAPT00549 | NFAPT00549 | 3-02-0339-___-____ | Jonathan J Hutchinson | (907)451-5479 | Construct drainage improvements at the Deadhorse Airport and along Deadhorse Drive and fill in-fields adjacent to the runway and apron. Construct a wildlife perimeter fence with a service road around the airfield. |  | Between $30,000,000 and $40,000,000
Northern Region | (DELETED) |  |  |  | (1) [on 2024.07.24 project was added.] | Gulkana River Boat Launch Fencing | Gulkana | 2024-07-01 | NSHWY0497A | NSHWY0497A | N/A | Scott L Maybrier | (907)451-5380 | Install 3,333' feet of 6' high chain link fencing, including vehicle gates and no parking signs, around the woods next to the Gulkana River boat launch at MP 126.5 of the Richardson Highway. |  | Between $200,000 and $500,000
Northern Region | ADDED |  |  |  |  | Northern Region Preservation Maintenance FFY2024 | Yukon River | 2024-08-01 | NFAPT0094A | NFAPT0094A | N/A | Daniel A Phillips | (907)451-2926 | Complete surface preservation maintenance work at the following airports: Allakaket, Fort Yukon, Huslia, Nulato, and Tanana |  | Pending
Northern Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (2) [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.] | (3) [on 2024.04.15 project was added.]; [on 2024.06.19 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.] | Glenn/Richardson Highway Right of Way Reconciliation | Glennallen | 2024-08-01 | HSHWY00018
Northern Region | FEDNUM | N/A | Pending | (1) [on 2024.04.15 the ANTADVDT changed to November 2024.] | (2) [on 2024.01.16 project was added.]; [on 2024.04.15 the ANTADVDT changed to November 2024.] | Cowles Street Reconstruction - Airport Way to East Cowles | Fairbanks | 2024-11-01 | NFHWY00883
Northern Region | PROJNAME | Pearl Creek Elementary School Access Imp and Plug-ins (CMAQ) | Pearl Creek Elementary School Access Improvements and Plug-ins (CMAQ) | (2) [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.06.19 the ANTADVDT changed to October 2024.] | (6) [on 2023.08.21 project was added.]; [on 2023.11.15 ADDLINFO changed.]; [on 2023.11.15 the ANTADVDT changed to May 2024.]; [on 2024.02.14 PROJNAME changed.]; [on 2024.06.19 ADDLINFO changed.]; [on 2024.06.19 the ANTADVDT changed to October 2024.] | Pearl Creek Elementary School Access Improvements and Plug-ins (CMAQ) | Fairbanks | 2024-10-01 | NFHWY00712
Southcoast Region | ADDED |  |  |  | (2) [on 2022.08.14 project was added.]; [on 2023.03.15 the project was removed.] | KING SALMON AIRPORT RWY 18-36 AND GA APRON PVMNT REHAB PROJ | King Salmon | 2025-07-01 | SFAPT00362 | SFAPT00362 | N/A | Peter J Jackson | (907)465-4439 | Repave Runway 18-36 and Taxiways C,D,M, Terminal and GA Apron. Remove aligned taxiway on runway 36 |  | Between $5,000,000 and $10,000,000
Southcoast Region | ANTADVDT | 2024-12-01 | 2025-01-01 | (4) [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.]; [on 2024.06.19 the ANTADVDT changed to December 2024.] | (5) [on 2023.06.15 project was added.]; [on 2023.10.25 the ANTADVDT changed to July 2024.]; [on 2024.01.16 the ANTADVDT changed to December 2024.]; [on 2024.04.15 the ANTADVDT changed to January 2025.]; [on 2024.06.19 the ANTADVDT changed to December 2024.] | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | Haines | 2025-01-01 | SDRER00445
Southcoast Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (5) [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | (12) [on 2022.01.18 project was added.]; [on 2022.04.15 the project was removed.]; [on 2022.09.13 project was added.]; [on 2022.11.17 the project was removed.]; [on 2022.12.17 project was added.]; [on 2023.06.15 the ANTADVDT changed to January 2024.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2023.12.15 ADDLINFO changed.]; [on 2024.02.14 the ANTADVDT changed to April 2024.]; [on 2024.04.15 the ANTADVDT changed to June 2024.]; [on 2024.06.19 the ANTADVDT changed to July 2024.] | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Haines | 2024-08-01 | Z686060000
Southcoast Region | ANTADVDT | 2024-07-01 | 2024-08-01 | (10) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.] | (16) [on 2022.02.22 the ANTADVDT changed to April 2022.]; [on 2022.02.22 PHONENUM changed.]; [on 2022.02.22 PROJMAN changed.]; [on 2022.04.15 the ANTADVDT changed to May 2022.]; [on 2022.04.15 PHONENUM changed.]; [on 2022.05.16 the ANTADVDT changed to July 2022.]; [on 2022.09.13 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the ANTADVDT changed to July 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to October 2023.]; [on 2023.10.25 the ANTADVDT changed to February 2024.]; [on 2024.02.14 the ANTADVDT changed to March 2024.]; [on 2024.04.15 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to June 2024.]; [on 2024.07.24 the ANTADVDT changed to July 2024.] | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | Ketchikan | 2024-08-01 | SFHWY00186
Southcoast Region | ANTADVDT | 2024-10-01 | 2025-06-01 | (5) [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.02.14 the ANTADVDT changed to July 2024.]; [on 2024.04.15 the ANTADVDT changed to September 2024.]; [on 2024.07.24 the ANTADVDT changed to October 2024.] | (18) [on 2022.01.18 project was added.]; [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 the project was removed.]; [on 2023.01.17 project was added.]; [on 2023.02.24 the project was removed.]; [on 2023.03.15 project was added.]; [on 2023.05.15 the project was removed.]; [on 2023.06.15 project was added.]; [on 2023.07.14 the ANTADVDT changed to February 2024.]; [on 2023.07.14 DESCRIPTION changed.]; [on 2024.01.16 the ANTADVDT changed to June 2024.]; [on 2024.01.16 PHONENUM changed.]; [on 2024.01.16 PROJMAN changed.]; [on 2024.02.14 the ANTADVDT changed to July 2024.]; [on 2024.04.15 the ANTADVDT changed to September 2024.]; [on 2024.07.24 the ANTADVDT changed to October 2024.] | UNALASKA TAXIWAY AND APRON REHABILITATION | Unalaska | 2025-06-01 | SFAPT00178
Southcoast Region | PHONENUM | (907)465-1215 | None | (5) [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.] | (11) [on 2022.03.15 DESCRIPTION changed.]; [on 2022.04.15 the project was removed.]; [on 2022.06.15 project was added.]; [on 2022.09.13 ADDLINFO changed.]; [on 2022.09.13 the ANTADVDT changed to August 2023.]; [on 2023.07.14 FEDNUM changed.]; [on 2023.08.21 the ANTADVDT changed to December 2023.]; [on 2023.10.25 the ANTADVDT changed to March 2024.]; [on 2024.02.14 the ANTADVDT changed to May 2024.]; [on 2024.05.16 the ANTADVDT changed to August 2024.]; [on 2024.05.16 ENGEST changed.] | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | Ketchikan | 2024-08-01 | SFHWY00070