## Tentative Award Schedule
PROJID | PROJNAME | STATENUM | FEDNUM | REGION | LOCATION | PROJMAN | PHONENUM | ANTADVDT | DESCRIPTION | ADDLINFO | ENGEST
CFHWY00732 | AMATS: VFW ROAD - EAGLE RIVER LP TO EAGLE RIVER RD PP | CFHWY00732 | 0001695 | Central Region | Eagle River | Christina A Huber | (907)269-0572 | April 2025 | This pavement preservation project includes resurfacing, roadside hardware, drainage improvements, bridge improvements, ADA improvements, and utilities as necessary. |  | Between $5,000,000 and $10,000,000
CFHWY00601 | ANCHOR POINT ROAD MP 0-1.3 PAVEMENT PRESERVATION | CFHWY00601 | 0001699 | Central Region | Anchor Point | Steven J Rzepka | (907)269-0592 | April 2025 | Resurface Anchor Point Road from Old Sterling Highway to end of road at beach parking lot. This project will include: Pavement Preservation, Roadside Hardware, Drainage improvements, and Utilities. |  | Pending
CFHWY00286 | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | CFHWY00286 | 0510007 | Central Region | Anchorage | Jon W Knowles | (907)269-0643 | April 2025 | Pavement Preservation of DeArmoun Rd. from East 140th Avenue to Hillside Drive including improvements to drainage, intersections, ADA, roadside hardware, and utilities. High Friction Surface Treatment may be reapplied. |  | Between $2,500,000 and $5,000,000
NFAPT00600 | Kotzebue Airport Crosswind Runway Improvements | NFAPT00600 | 3-02-0160-___-____ | Northern Region | Kotzebue | Jonathan J Hutchinson | (907)451-5479 | April 2025 | Rehabilitate and construct safety improvements to the Kotzebue Airport crosswind runway 18-36 and taxiway G, replace airfield lighting, apply dust palliative, and construct a new general aviation apron. |  | Between $10,000,000 and $20,000,000
CFAPT00854 | TUNUNAK AIRPORT REHABILITATION | CFAPT00854 | 3-02-0486-003-2024 | Central Region | Tununak | Kim D Satterfield | (907)269-0623 | April 2025 | This project proposes to rehabilitate and resurface the operational surfaces at the Tununak Airport to correct cracks, ruts, uneven surfaces, dips (over 6"), soft spots, and ponding. Dust palliative will be applied for fines preservation to bind aggregate and prevent loss of fines. Drainage improvements may include special ditching and culvert realignment where needed. Lighting and visual aids will be repaired or replaced where they have been damaged or displaced by subsidence. |  | Between $10,000,000 and $20,000,000
CFAPT00930 | ANC VISUAL PAGING SYSTEM INSTALLATION DESIGN-BUILD | CFAPT00930 | N/A | Central Region | Anchorage | Bonnie G Allen | (907)266-2510 | August 2024 | Install an estimated 70 monitors and 70 input stations with associated hardware, software, and accessories to provide visual paging throughout the South Terminal, Connector, and North Terminal Lobby to meet Americans with Disabilities Act (ADA) requirements. |  | Between $1,000,000 and $2,500,000
CFAPT01021 | CHENEGA BAY AIRPORT LIGHTING IMPROVEMENTS | CFAPT01021 | 3-02-0419-006-2024 | Central Region | Chenega Bay | Kim D Satterfield | (907)269-0623 | August 2024 | Replace runway and taxiway lighting systems, the segmented circle and lighted primary wind cone, the rotating beacon, and the lighted supplemental wind cone. |  | Between $2,500,000 and $5,000,000
HSHWY00018 | Glenn/Richardson Highway Right of Way Reconciliation | HSHWY00018 | N/A | Northern Region | Glennallen | Carl F Heim | (907)451-5359 | August 2024 | Reconcile right of way and encroachment conflicts along the Glenn and Richardson Highways near Glennallen Alaska, to allow for completion of future federal projects. This work may include right of way research, appraisals, purchases and other activities necessary to eliminate conflicts. Completion of a highway wayside as part of the conflict elimination will also be included as part of this effort. |  | Between $500,000 and $1,000,000
Z686060000 | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Z686060000 | 0956028 | Southcoast Region | Haines | Gregory K Lockwood | (907)465-2393 | August 2024 | Reconstruction of Haines Highway from Milepost 20 to 25 including the Chilkat River bridge. | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise. New draft plans were posted on 11-22-2023 | Between $40,000,000 and $50,000,000
SFHWY00186 | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | SFHWY00186 | 0003244 | Southcoast Region | Ketchikan | Nathan A Purves | (907)465-4521 | August 2024 | Provide additional illumination at the Stedman/Deermount intersection to achieve a level of luminance that meets current DOT&PF standards. Construct a concrete sidewalk bulbout on the Stedman side of the marked crosswalk. The bulbout will extend from the existing sidewalk to the edge of the traveled way. |  | Between $500,000 and $1,000,000
SFHWY00359 | JNU BRIDGET COVE CREEK CULVERT REPLACEMENT | SFHWY00359 | 0003267 | Southcoast Region | Juneau | Brett M Wells | (907)465-1607 | August 2024 | The work includes excavation, grading, chip seal, culvert replacement, seeding, rock armoring, and stream channel restoration. |  | Between $500,000 and $1,000,000
SFHWY00070 | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | SFHWY00070 | 0003225 | Southcoast Region | Ketchikan | Kirk D Miller | None | August 2024 | This project will replace or rehabilitate the Sayles/Gorge Street Viaduct (#1841). | Remove and replace existing bridge structure. | Between $5,000,000 and $10,000,000
NFAPT0094A | Northern Region Preservation Maintenance FFY2024 | NFAPT0094A | N/A | Northern Region | Yukon River | Daniel A Phillips | (907)451-2926 | August 2024 | Complete surface preservation maintenance work at the following airports: Allakaket, Fort Yukon, Huslia, Nulato, and Tanana |  | Pending
CSHWY01203 | Seward Highway MP 98.5 – 118 Signage Project | CSHWY01203 | N/A | Central Region | Anchorage | Sean M Baski | (907)269-0566 | August 2024 | This project will replace existing signs that do not meet ATM standards, install signs in advance of pullouts and recreation sites, and install additional mile points to help with wayfinding and reduce crashes. |  | Pending
25RC013613 | 7 Mile Asbestos Mitigation and HVAC Upgrades | 25RC013613 | N/A | Central Region | Juneau | None | None | December 2024 | Project to address remaining Asbestos ad HVac Issues within the Dot 7mi complex's main building within Juneau Alaska |  | Pending
SFHWY00440 | HNS HIGHWAY MPT1-9- DEC 20 SE PR | SFHWY00440 | 0093006 | Southcoast Region | Haines | Joel D Osburn | (907)465-4409 | December 2024 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS00l, AK 2021 01 HNS002, AK 2021 01 HNS003, and AK 2021 01 HNS004. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway. |  | Between $200,000 and $500,000
SFHWY00481 | JNU GLACIER HWY. CHIP SEAL - INDUSTRIAL TO ROUNDABOUT | SFHWY00481 | 0933051 | Southcoast Region | Juneau | Joel D Osburn | (907)465-4409 | December 2024 | This project will design and construct a chip seal overlay on Glacier Highway, between Brotherhood Bridge & the AMHS Ferry Terminal in Auke Bay. |  | Between $1,000,000 and $2,500,000
SFAPT00558 | KDK ADQ AIRPORT TAXIWAYS C AND D RECNSTN | SFAPT00558 | N/A | Southcoast Region | Kodiak | David B Epstein | (907)465-4483 | December 2024 | Reconstruct Taxiways C and D at Kodiak Airport, Kodiak, AK. This new project replaces stages 2 and 3 of Kodiak Airport apron and Taxiways C, D, and F reconstruction. |  | Between $20,000,000 and $30,000,000
SFAPT00361 | KOKHANOK AIRPORT RESURFACING AND FENCING | SFAPT00361 | N/A | Southcoast Region | Kokhanok | David B Epstein | (907)465-4483 | December 2024 | Resurfacing and grading the runway, regrading ditches and safety areas, replacement of inoperative culverts and drainage repairs. Installation of new AWOS. CC 24300447 LC 33008462 Phase: T02FA1 LC & CC Description: SFAPT00361-2P-Resurf. |  | Between $10,000,000 and $20,000,000
CFHWY00622 | WASILLA FISHHOOK RD: E SELDON RD TO TEX-AL DR PAVEMENT PRESERVATION | CFHWY00622 | 0001700 | Central Region | Wasilla | Chris L Bentz | (907)707-1912 | December 2024 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. |  | Between $5,000,000 and $10,000,000
SAMHS00419 | AMHS AUKE BAY EAST BERTH TERMINAL IMPROVEMENTS | SAMHS00419 | 0933048 | Marine Highways | Juneau | Misty L Butler | (907)465-4546 | February 2025 | Work includes: Removal of 5 mooring/berthing dolphins and replacing with 6 new mooring/berthing dolphins, removal and replacement of 5 catwalks, removal and replacement of 2 gangways, and electrical upgrades to dolphin and walkway lighting systems. |  | Between $10,000,000 and $20,000,000
CFAPT01002 | ANC TAXILANE E IMPROVEMENTS | CFAPT01002 | N/A | Central Region | Anchorage | Kim D Satterfield | (907)269-0623 | February 2025 | Rehabilitate Taxiway Echo from Taxiway Victor to Taxiway Lima. Improvements include: provide adequate typical section; evaluate taxiway safety area; replace lighting, markings, and signs; remove, replace, or modify existing storm drainage as needed; and adjust utilities as needed. |  | Between $40,000,000 and $50,000,000
NFHWY00764 | DALTON HIGHWAY MP 245-274 RESURFACING | NFHWY00764 | 0655016 | Northern Region | Coldfoot | David K Fischer | (907)451-5357 | February 2025 | Resurface the Dalton Highway between MP 245-274. Project includes bridge work (#1333, #1439, #1519, #1520, #4042, #4043, #4050, #7098, and #7099), drainage improvements, roadside hardware, spot repairs, and utilities. |  | Pending
CDRER01160 | PETERS CREEK BRIDGE (1367) EMERGENCY REPAIRS | CDRER01160 | N/A | Central Region | Peters Creek | Steven J Rzepka | (907)269-0592 | February 2025 | This state funded emergency project will remove and replace the damaged girder on the Peters Creek Undercrossing (NBI 1367) on the Glenn Highway. Work also includes cast in place concrete, bridge rail, pavement striping, and traffic control. |  | Between $1,000,000 and $2,500,000
Z600770000 | WASILLA-FISHHOOK - MAIN STREET REHABILITATION | Z600770000 | 0001408 | Central Region | Wasilla | Clint J Adler | (907)707-1911 | February 2025 | Construct a one-way couplet in downtown Wasilla bounded by Bogard Road, KGB/Main Street, Yenlo/Talkeetna Street and the Palmer Wasilla Highway. The exact location of the couplet will be determined during the environmental and preliminary design phase. Improvements to Bogard Road will be necessary to make the couplet functional. Work will consist of new road construction, lane reconfigurations, signals, new pavement, signing and striping, and sidewalks. |  | Between $40,000,000 and $50,000,000
NFHWY00139 | Yankovich-Miller Hill Road Reconstruction and Multi-Use Path | NFHWY00139 | 0002378 | Northern Region | Fairbanks | Ivet Hall | (907)451-5386 | February 2025 | Reconstruct Miller Hill Road and Yankovich Road, and improve existing separated multi-use path as needed. Project work will include roadside hardware, drainage improvements, and utilities. |  | Between $5,000,000 and $10,000,000
CSAPT01196 | ANC C Concourse Plaza Renovation Design | CSAPT01196 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | January 2025 | Provide a design to improve the function, utilization, and maintenance of the C Concourse Plaza area. |  | Between $1,000,000 and $2,500,000
CFAPT01205 | ANC GATES N2 &N4 REHABILITATION | CFAPT01205 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | January 2025 | Rehabilitate and extend the life of the aprons at Gates N2 and N4 to include joint seal replacement and concrete rehabilitation |  | Between $500,000 and $1,000,000
CFAPT01192 | ANC RON 12-14 Rehabilitation | CFAPT01192 | 3-02-0016-XXX-2025 | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | January 2025 | Rehabilitate and extend the life of aprons RON 12, 13, and 14 to include joint seal replacement and concrete rehabilitation. |  | Between $1,000,000 and $2,500,000
CSAPT01183 | ANC South Terminal Employee Entrance Improvements | CSAPT01183 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | January 2025 | Adjust drive lanes at the entrance to provide enough width for maintenance equipment to plow in the vicinity of the access points. Project could include pavement removal and replacement, curb removal and replacement, landscaping, and utility relocations. |  | Between $1,000,000 and $2,500,000
CFAPT00992 | ANC TAXIWAY KILO TUG ROAD REHABILITATION | CFAPT00992 | 3-02-0016-XXX-2024 | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | January 2025 | Rehabilitate approximately 5,000 feet of the Tug Road from Taxiway Alpha to A Concourse. Project includes, pavement rehabilitation, drainage improvements and pavement markings. |  | Between $5,000,000 and $10,000,000
NFHWY00570 | Chena Ridge Road and Chena Pump Road Resurfacing | NFHWY00570 | 0645015 | Northern Region | Fairbanks | John J Netardus | (907)451-5448 | January 2025 | Resurface Chena Ridge Road and Chena Pump Road. Project will include bridge work, drainage improvements, embankment stabilization, and roadside hardware. | Single chip seal overlay proposed. | Between $5,000,000 and $10,000,000
SFHWY00326 | COLD BAY TROUT CREEK CULVERTS WFL | SFHWY00326 | 0003265 | Southcoast Region | Cold Bay | Brett M Wells | (907)465-1607 | January 2025 | Replace two damaged culverts with new Aquatic Organism Passage structures across Trout Creek and Little Trout Creek in Cold Bay, AK. |  | Between $2,500,000 and $5,000,000
NFHWY00835 | Fairbanks Bike Lane Striping and Signing (TAP) | NFHWY00835 | TA23001 | Northern Region | Fairbanks | Ivet Hall | (907)451-5386 | January 2025 | Signing and striping on paved Fairbanks city streets to designate space for seasonal bicycle use. Project will include ADA improvements. |  | Between $200,000 and $500,000
CFHWY00394 | GLENN HIGHWAY MILEPOST 66.5 TO 92 PAVEMENT PRESERVATION | CFHWY00394 | 0A15039 | Central Region | Statewide | Kristina H Busch | (907)269-0567 | January 2025 | Resurface the Glenn Highway from Kings River bridge to Cascade. Additional improvements may include bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities as necessary. Project construction may be phased. |  | Between $10,000,000 and $20,000,000
SDRER00436 | HNS ANADROMOUS CULVERTS 189479 - DEC 20 SE PR | SDRER00436 | N/A | Southcoast Region | Haines | Joel D Osburn | (907)465-4409 | January 2025 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Disaster Inventory Numbers 461219, 461641, 548035, and 461258. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Mud Bay Road, Sawmill Road, and at the DOT&PF Maintenance Yard. This project is funded by FEMA. |  | Between $2,500,000 and $5,000,000
SFHWY00446 | HNS HWY / LUTAK ROAD - DEC 20 SE PR | SFHWY00446 | 0093007 | Southcoast Region | Haines | Joel D Osburn | (907)465-4409 | January 2025 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIRs AK 2021 01 HNS005, AK 2021 01 HNS006, AK 2021 01 HNS007, AK 2021 01 HNS008, AK 2021 01 HNS009, AK 2021 01 HNS010, AK 2021 01 HNS011, and AK 2021 01 HNS012. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Haines Highway & Lutak Road. |  | Between $1,000,000 and $2,500,000
SDRER00445 | HNS ROADWAY & CULVERTS 189485 - DEC 20 SE PR | SDRER00445 | N/A | Southcoast Region | Haines | Joel D Osburn | (907)465-4409 | January 2025 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Damage Inventory Numbers 461220 - 461221, 461229, 461231 - 461236, 461253, 461255 - 461257, 461652, 784622, and 918887 - 918890. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Beach Road, Front Street, Allen-Menaker Road, Comstock Road, Piedad Road and Mud Bay Road. This project is funded by FEMA. |  | Between $1,000,000 and $2,500,000
CFHWY00829 | HSIP: PALMER-FISHHOOK RD & TRUNK RD ROUNDABOUT | CFHWY00829 | 0441010 | Central Region | Palmer | Galen K Jones | (907)269-0550 | January 2025 | The project will reconstruct the three-leg intersection of Palmer-Fishhook Rd and Trunk Rd. This project may also include roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. | PIH 75% review estimate. | Between $2,500,000 and $5,000,000
SFHWY00438 | JNU ROADWAYS AND CULVERTS - DEC 20 SE PR | SFHWY00438 | 0093005 | Southcoast Region | Juneau | Joel D Osburn | (907)465-4409 | January 2025 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK 2021 01 JNU002, AK 2021 01 JNU004, AK 2021 01 JNU005, and AK 2021 01 JNU006. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Glacier Highway/Lemon Road, Egan Drive/Glacier Highway, and Glacier Highway/Twin Lakes Drive. This project is funded by FHWA. |  | Between $1,000,000 and $2,500,000
CFAPT00882 | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | CFAPT00882 | 3-02-0013-XXX-2024 | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | January 2025 | Rehabilitate the pavement of Aircraft and Lakeshore Dr from Voight Cir to the Lake Hood East property boundary south of runway 14/32. Project includes roadway reconditioning, structural section repairs, drainage improvements, and striping. | Rehabilitate Aircraft and Lakeshore Drive pavement. Includes drainage and safety improvements. | Between $2,500,000 and $5,000,000
CFHWY00887 | OLD GLENN HWY OUTER SPRINGER LP & INNER SPRINGER LP PAVEMENT | CFHWY00887 | 0001748 | Central Region | Palmer | Kristina H Busch | (907)269-0567 | January 2025 | This pavement preservation project will resurface Old Glenn Hwy, Outer Springer Loop and Inner Springer Loop. Additional improvements may also include: utility relocation, roadsidehardward, vegetation clearing, dig-outs, drainage, signs, striping, bridge repairs, ADA improvements, and safety improvements. |  | Between $2,500,000 and $5,000,000
CFHWY00405 | PALMER-FISHHOOK ROAD MILEPOSTS 7-17 | CFHWY00405 | 0580020 | Central Region | Matanuska-Susitna Borough | Aaron L Hunting | (907)269-0546 | January 2025 | Pavement Preservation of Palmer-Fishhook Road Mileposts 7-17 and may include, as necessary: Bridge Work, Roadside Hardware, Drainage Improvements, and Utilities. |  | Pending
Z631860000 | Richardson Highway MP 148-173 (CONST MP 167-173) | Z631860000 | 0713010 | Northern Region | Paxson | Russell M Johnson | (907)451-5059 | January 2025 | Reconstruct the Richardson Highway between MP 167 and 173. Project includes roadside hardware, drainage improvements and utility relocations. | Reconstruct the Richardson Highway between mileposts 167-173. | Between $30,000,000 and $40,000,000
CFAPT00835 | ANC TAXIWAY Z IMPROVEMENTS EAST | CFAPT00835 | N/A | Central Region | Anchorage | Philip W Cheasebro | (907)269-0606 | July 2025 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron. |  | Pending
CFHWY00852 | KENAI SPUR HIGHWAY MP 29-38 PAVEMENT PRESERVATION | CFHWY00852 | 0490017 | Central Region | Kenai | Aaron L Hunting | (907)269-0546 | July 2025 | This project will resurface the Kenai Spur Highway between mileposts 29 and 38. Improvements to roadside hardware, safety, drainage, signs, and minor structural section improvements may also be included. |  | Between $5,000,000 and $10,000,000
SFAPT00362 | KING SALMON AIRPORT RWY 18-36 AND GA APRON PVMNT REHAB PROJ | SFAPT00362 | N/A | Southcoast Region | King Salmon | Peter J Jackson | (907)465-4439 | July 2025 | Repave Runway 18-36 and Taxiways C,D,M, Terminal and GA Apron. Remove aligned taxiway on runway 36 |  | Between $5,000,000 and $10,000,000
NFAPT00604 | Buckland Airport Improvements | NFAPT00604 | 3-02-0399-___-____ | Northern Region | Buckland | Jonathan J Hutchinson | (907)451-5479 | June 2025 | Rehabilitate the runway and taxiway, stabilize the embankments, resurface the airport access road, apply dust palliative, and replace the airport lighting system. | Pushed due to funding availability | Between $10,000,000 and $20,000,000
NFHWY00947 | DALTON HWY MP 247-289 AND MP 305-362 DELINEATOR RPLMT (HSIP) | NFHWY00947 | 0656007 | Northern Region | Northern Region | Ethan E Graetz | (907)451-2281 | June 2025 | Install and replace roadside delineators along the Dalton Highway from MP 247 - 289 and MP 305 - 362. |  | Pending
SDRER00448 | HNS LUTAK ROAD 437114 - DEC 20 SE PR | SDRER00448 | N/A | Southcoast Region | Haines | Joel D Osburn | (907)465-4409 | June 2025 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for Damage Inventory Numbers 461224, 461227, 461237 - 461239, 461243 - 461250, 784625 - 784632, and 786036. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. This project will repair sites on Lutak Road. This project is funded by FEMA. |  | Between $2,500,000 and $5,000,000
CFHWY00502 | HSIP GAMBELL ST. UTILITY POLE REMOVAL AND INCREASED LIGHTING | CFHWY00502 | 0A31063 | Central Region | Anchorage | Noah C King | (907)269-0657 | June 2025 | This project will remove the utility poles and underground the utilities. New light poles will be installed at locations further from the traveled way to reduce the risk of impact by errant vehicles. New light poles will be installed meeting current standards. |  | Pending
CFHWY00503 | HSIP:GAMBELL AND INGRA STREET--OVERHEADSIGNAL INDICATION U/G | CFHWY00503 | 0001644 | Central Region | Anchorage | Noah C King | (907)269-0657 | June 2025 | This project will install new signal poles and mast arms to bring signals into conformance with current minimum signal indication requirements. |  | Between $10,000,000 and $20,000,000
SFAPT00178 | UNALASKA TAXIWAY AND APRON REHABILITATION | SFAPT00178 | N/A | Southcoast Region | Unalaska | Bran P Pollard | (907)465-4526 | June 2025 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
SAMHS00147_C | M/V Columbia CPP System Replacement | SAMHS00147_C | 9500143 | Marine Highways | Statewide | Troy J Sherrill | None | March 2024 | The scope of work for this federally funded contract includes the installation of a new Owner-Furnished Controlled Pitch Propeller (CPP) System on the M/V Columbia, including Alarm and Monitoring systems installation, Fire Detection system, testing, and demonstration of acceptable operation to regulatory agencies and the owner. Work includes necessary remediation of contaminated materials, limited engineering, documentation, and State funded annual overhaul work as outlined in the plans and specifications. |  | Pending
CSAPT01228 | ANC PFAS Remediation | CSAPT01228 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | March 2025 | Perform PFAS Remediation measures at ANC. Remediation includes installing permeable reactive barriers using an activated carbon mixture within the Postmark Bog and ARFF building. Project also includes replacement of two manholes within the Postmark Bog. |  | Between $500,000 and $1,000,000
CFHWY00260 | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | CFHWY00260 | AKBLM AFO 2014(1) | Central Region | Anchorage | Noah C King | (907)269-0657 | March 2025 | Relocate the BLM Road to the Cambell Tract Facility 260 feet to align East 68th Avenue with intersection improvements to include bus stop and integration to existing signalized intersection. |  | Between $5,000,000 and $10,000,000
NFAPT00249 | Deering Airport Improvements | NFAPT00249 | 3-02-0400-XX-202X | Northern Region | Deering | Jonathan J Hutchinson | (907)451-5479 | March 2025 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $20,000,000 and $30,000,000
CFHWY00928 | HOPE HWY MP 7.9 & MP 12.9 PIPE REPLACEMENTS | CFHWY00928 | 0498002 | Central Region | Hope | Travis W Holmes | (907)269-0543 | March 2025 | Replace failing culverts on the Hope Highway at MP 7.9 and MP 12.9. Additional improvements may include, as necessary, resurfacing, erosion protection, guardrail, signs, and striping. |  | Between $5,000,000 and $10,000,000
CFHWY00944 | HSIP: ANCHORAGE FLASHING YLW ARROW & SIGNAL HEAD DISPLAY IMP | CFHWY00944 | 0001750 | Central Region | Anchorage | Galen K Jones | (907)269-0550 | March 2025 | This project will install FYA signal heads for existing protected-permissive and permissive left turning movements (opposing left turns will both be upgraded, where identified); install new signal poles, mast arms, and foundations as required to complete FYA upgrades; upgrade existing TS-1 traffic controller cabinets and electrical load centers to support FYA operation; relocate mast arm signage and reconstruct existing sidewalk, roadway, curb and gutter, and curb ramps as required to modify the required traffic signal to FYA operation. | Two PS&Es will be advertised on year apart with roughly equal amounts in 2025 and 2026. The amount shown is for the first contract. | Pending
NFHWY00699 | HSIP: CHENA SMALL TRACTS ROUNDABOUT | NFHWY00699 | 0645016 | Northern Region | Fairbanks North Star Borough | Ethan E Graetz | (907)451-2281 | March 2025 | Construct a roundabout at the intersection of Chena Pump Road, Old Chena Ridge Road, and Chena Small Tracts Road. Project will include intersection improvements, roadside hardware, and utilities. |  | Pending
SFHWY00403 | JNU LOOP RD-VALLEY BLVD INTERSECTION SAFETY IMP HSIP | SFHWY00403 | 0966030 | Southcoast Region | Juneau | Nathan A Purves | (907)465-4521 | March 2025 | Construct a single-lane roundabout at the Loop Road - Mendenhall Boulevard - Valley Boulevard intersection. |  | Between $5,000,000 and $10,000,000
CFHWY00850 | SEWARD HWY MP 90-99 PAVEMENT PRESERVATION | CFHWY00850 | 0A31066 | Central Region | Regionwide | Julia R Hanson | (907)269-0753 | March 2025 | Pavement preservation, which may include improvements to roadside hardware, drainage, intersections, automated traffic recorders, pedestrian facilities, bridge work, striping, and utilities. |  | Between $10,000,000 and $20,000,000
CFAPT00805 | TAKOTNA AIRPORT REHABILITATION | CFAPT00805 | N/A | Central Region | Central | Aaron C Hughes | (907)269-0523 | March 2025 | Resurface the runway, taxiway, apron, and access road to correct deep cracks, uneven surfaces, soft spots, and areas where subbase is exposed. Replace lighting, NAVAIDS, and improve drainage. |  | Pending
CFHWY00587 | AMATS: FISH CREEK TRAIL CONNECTION | CFHWY00587 | 0001696 | Central Region | Anchorage | Noah C King | (907)269-0657 | May 2025 | This project will construct a multi-use path between Northern Lights Boulevard and the Tony Knowles Coastal Trail in the vicinity of Fish Creek. Work may include roadside hardware, ADA improvements, utilities, lighting, bridge work, and drainage improvements. |  | Pending
CRMBS00831 | ANC ATCT REPLACEMENT PARKING | CRMBS00831 | 697DCK-22-T-00001 | Central Region | Anchorage | Philip W Cheasebro | (907)269-0606 | May 2025 | This project will construct additional aircraft parking at LHD Echo Parking to replace parking impacted by FAA's new ATCT. | Pre PS&E review documents are located at the link below: <a class=linkcopy href="https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/00831%20ANC%20ATCT%20Replacement%20Parking%20PSE%20Review%20Plans_TAL.pdf">Preliminary Plans (~14 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $5,000,000 and $10,000,000
CFHWY00392 | Hollywood Rd. : Vine Rd. to Big Lake Rd. Pavement Preservation | CFHWY00392 | 0001686 | Central Region | Big Lake | Alex L Read | (907)269-0641 | May 2025 | Pavement preservation, roadside hardware, structural improvement in limited areas, minor drainage and/or safety improvements, utility adjustment/relocation, signing and striping. |  | Between $5,000,000 and $10,000,000
NFHWY00592 | HSIP: City of Fairbanks Systemic Signal Upgrades | NFHWY00592 | 0002495 | Northern Region | Fairbanks | Ethan E Graetz | (907)451-2281 | May 2025 | Reconstruct 22 signalized intersections at multiple locations in the City of Fairbanks. Work includes roadside hardware and intersection improvements. | This project will be advertised with HSIP: Northern Region Systemic Signal Upgrades (NFHWY00531) | Between $5,000,000 and $10,000,000
SFHWY00524 | HSIP: JNU VANDERBILT CONTINUOUS GREEN T | SFHWY00524 | 0932054 | Southcoast Region | Juneau | Joel D Osburn | (907)465-4409 | May 2025 | This project will convert the southbound Egan lanes to continuous green movements at the Vanderbilt intersection by adding a left turn acceleration lane for vehicles turning south from Vanderbilt onto Egan. |  | Between $1,000,000 and $2,500,000
NFHWY00531 | HSIP: Northern Region Systemic Signal Upgrades | NFHWY00531 | 0002474 | Northern Region | Fairbanks North Star Borough | Ethan E Graetz | (907)451-2281 | May 2025 | Reconstruct eight signalized intersections at multiple locations in the Fairbanks and Parks Highway Nenana Canyon area. Work includes roadside hardware and intersection improvements. | This project will be constructed with HSIP: City of Fairbanks Systemic Signal Upgrades (NFHWY00592) | Between $2,500,000 and $5,000,000
CFHWY00463 | HSIP: VINE RD AT HOLLYWOOD INTERSECTION IMPROVEMENTS | CFHWY00463 | 0001627 | Central Region | Wasilla | Alex L Read | (907)269-0641 | May 2025 | Project will construct either a single lane roundabout or a traffic signal to mitigate crashes at the intersection of Vine and Hollywood. Project is included in the HSIP program. |  | Pending
SFHWY00514 | KDK AREAWIDE ROCKFALL TREATMENT PRESERVATION | SFHWY00514 | 0011051 | Southcoast Region | Kodiak | Travis W Eckhoff | (907)465-1171 | May 2025 | This project is to remove rockfall debris from existing rockfall catchment ditches to restore functionality. |  | Between $500,000 and $1,000,000
SFHWY00591 | KTN N.Tongass HWY Resurface: A/P F.T. To Ward Creek Bridge Stage 2 | SFHWY00591 | 0920031 | Southcoast Region | Ketchikan | Brett M Wells | (907)465-1607 | May 2025 | Resurface North Tongass from the Airport Ferry Terminal (milepoint 0.717) to (and including) the Ward Cove (milepoint 4.485). Replace culverts and guardrail at the end of useful life. Correct erosion and clear brush at Cannery Creek Bridge No. 746. |  | Between $10,000,000 and $20,000,000
Z548570000 | SEWARD AIRPORT IMPROVEMENTS | Z548570000 | N/A | Central Region | Seward | Joy A Vaughn | None | May 2025 | Shift, raise and reconstruct R/W 16/34. Construct Armor protection. Rehabilitate aprons, replace airport lighting, and construct pads for NAVAIDS. Close R/W 13/31, Taxiways A, D, and E. Miscellaneous fencing, signing, etc... |  | Between $20,000,000 and $30,000,000
CFHWY00586 | AMATS: DOWNTOWN TRAIL CONNECTION | CFHWY00586 | 0001662 | Central Region | Anchorage | Kristina H Busch | (907)269-0567 | November 2024 | Project will construct a connection between the Tony Knowles Coastal Trail to the Ship Creek Trail in downtown Anchorage. Major Project Elements include Bridge Work (Pedestrian), Roadside Hardware, Drainage Improvements, Intersection Improvements and ADA Improvements. |  | Between $10,000,000 and $20,000,000
NFHWY00883 | Cowles Street Reconstruction - Airport Way to East Cowles | NFHWY00883 | Pending | Northern Region | Fairbanks | Ivet Hall | (907)451-5386 | November 2024 | Reconstruct Cowles Street from Airport Way through East Cowles Street. Project work will include roadside hardware, drainage improvements, intersection improvements, ADA improvements and utilities. |  | Between $5,000,000 and $10,000,000
NFHWY00719 | GLENN HIGHWAY MP 143-154 RESURFACING | NFHWY00719 | 0A14008 | Northern Region | Northern Region | Ivet Hall | (907)451-5386 | November 2024 | Resurface the Glenn Highway between MP 143-154. Project includes bridge work, drainage improvements, pavement preservation, roadside hardware, and utilities. |  | Pending
2501000065A | Nenana Station Shop Roof Improvements | 2501000065A | N/A | Central Region | Nenana | Lauren A Staft | (907)451-5424 | November 2024 | Perform structural upgrades and replace Nenana DOT Maintenance Station shop roof. |  | Between $500,000 and $1,000,000
Z620030000 | Seppala Drive Upgrade | Z620030000 | 000S828 | Northern Region | Nome | Christopher F Johnston | (907)451-2322 | November 2024 | Realign and rehabilitate Seppala Drive in Nome. Work includes pavement rehabilitation, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. |  | Between $10,000,000 and $20,000,000
SFHWY00312 | SIT SEAWALK PHASE II WFLHD RASPS | SFHWY00312 | AK SIT 2017(1) | Southcoast Region | Sitka | Gregory K Lockwood | (907)465-2393 | November 2024 | This project is for Sitka Seawalk Stage II, which will continue the Sea Walk from the Sitka Public Library to the O¿Connell Lightering Facility. This project would improve pedestrian and ADA accessibility to the existing facilities. | Construct Section 2 of the Sitka Seawalk Phase II Project. Project would construct approximately 750 lineal feet of seawalk including: armored embankment along the existing Sitka Harbor Channel Bridge approach, concrete sidewalk, pedestrian lighting, landscaping and interpretive signage. | Between $2,500,000 and $5,000,000
CFHWY01210 | STERLING HWY: MP 157-169 RECON - PHASE I | CFHWY01210 | N/A | Central Region | Kenai Peninsula | Aaron L Hunting | (907)269-0546 | November 2024 | This project reconstructs and upgrades a 12-mile segment of the Sterling Highway. It includes widening the highway, creating passing lanes, resurfacing, improving drainage, minor realignments, upgrading to current geometric standards, and replacing the North Fork Anchor River and Anchor River Bridges. This first phase will construct from MP 157 through 161 and include both bridges. |  | Between $60,000,000 and $70,000,000
CFAPT01136 | ANC WEST PERIMETER ROAD | CFAPT01136 | 3-02-0016-XXX-2025 | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | October 2024 | Construct a perimeter road along the northwest edge of the security fence. The road will begin just south of the fuel farm and continue around northwest to follow the existing security fence. Project includes structural section, paving, and security fencing. |  | Between $1,000,000 and $2,500,000
CFHWY00883 | HSIP: CHURCH RD AND SPRUCE AVE INTERSECTION FLASHING BEACON | CFHWY00883 | 0001727 | Central Region | Wasilla | Noah C King | (907)269-0657 | October 2024 | This HSIP project will construct a flashing beacon and load center at the intersection of Church Road and Spruce Ave. Work may include drainage improvements, roadside hardware, ADA improvements (curb ramp & pathway), and utilities. |  | Between $200,000 and $500,000
CFHWY00253 | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | CFHWY00253 | 0221019 | Central Region | Kenai | Alex L Read | (907)269-0641 | October 2024 | This project will rehabilitate the Kenai Spur Highway between Soldotna and Kenai. A 5-lane highway will be constructed between the Sports Lake Road and Robin Drive intersections to increase capacity and improve safety. This is the second of two phases to construct the project. | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/00253/00253.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $40,000,000 and $50,000,000
CFAPT00572 | NIGHTMUTE AIRPORT IMPROVEMENTS | CFAPT00572 | 3-02-0195-002-2024 | Central Region | Nightmute | Philip W Cheasebro | (907)269-0606 | October 2024 | Rehabilitate the runway, taxiway, safety areas, apron, and access road. Widen and extend RSA to meet ADG II standards. Place and compact CASC, apply dust palliative. Reconstruct the airfield lighting system, primary wind cone, and supplemental wind cone. Replace rotating beacon on a tip-down pole. Relevel SREB. Construct barge landing. |  | Between $10,000,000 and $20,000,000
NFHWY00712 | Pearl Creek Elementary School Access Improvements and Plug-ins (CMAQ) | NFHWY00712 | 0002519 | Northern Region | Fairbanks | John J Netardus | (907)451-5448 | October 2024 | Reconfigure existing parking lot and access roads at Pearl Creek Elementary School in Fairbanks in order to improve vehicle circulation and reduce vehicle idling. Parking lot work includes installation of new vehicle electrical plug-ins, ADA improvements, drainage improvements, paving, and roadside hardware. | 2-year construction, 2025-2026 | Between $2,500,000 and $5,000,000
NFHWY00630 | Ruby Slough Road Rehabilitation | NFHWY00630 | 0002509 | Northern Region | Ruby | Jonathan J Hutchinson | (907)451-5479 | October 2024 | Rehabilitate Ruby Slough Road from Ruby Slough to the landfill. Project will include drainage improvements and roadside hardware. |  | Between $5,000,000 and $10,000,000
SFHWY00103 | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | SFHWY00103 | 0003214 | Southcoast Region | Sitka | Nathan A Purves | (907)465-4521 | October 2024 | Provide additional illumination at the Halibut Point Road/Peterson Avenue Intersection to achieve a level of luminance that meets current DOT&PF standards. Modify adjacent roadway lighting as needed to maintain satisfactory continuous illumination. Establish a pass-through crossing to facilitate less challenging pedestrian movements. Improve intersection sight distance by removing utility equipment located in the southeast quadrant of the intersection, acquiring property to remove parking spaces that, when occupied, create sight line obstructions, and modifying access to an apartment building adjacent to the intersection (shorten curb cut). Replace existing S1-1 School signs with W11-2 advance pedestrian warning signs. |  | Between $1,000,000 and $2,500,000
CSAPT00931 | ANC ACCESS GATE AND HEADBOLT OUTLET INSTALLATION | CSAPT00931 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | September 2024 | Project will include constructing a new vehicle access control gate at AFM West and install head bolt outlets (HBO) at the TW A and DeHavilland Avenue snow disposal sites. |  | Between $500,000 and $1,000,000
CSAPT01152 | ANC FIRING RANGE MAINTENANCE | CSAPT01152 | N/A | Central Region | Anchorage | Jennifer M Lombardo | (907)266-2731 | September 2024 | Perform deferred maintenance on the active firing/shooting range at ANC by removing lead bullets and bullet fragments. Amend remaining affected soil with a heavy metal fixation reagent to prevent leaching of lead. |  | Between $200,000 and $500,000
CFHWY00723 | BOGARD RD PAV PRESERVATION: TRUNK RD TO WASILLA-FISHHOOK RD | CFHWY00723 | 0001703 | Central Region | Wasilla | Chris L Bentz | (907)707-1912 | September 2024 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. |  | Between $10,000,000 and $20,000,000
NFHWY00905 | City of Fairbanks Systemic Signal Upgrades - Stage 1 (HSIP) | NFHWY00905 | N/A | Northern Region | Fairbanks | Ethan E Graetz | (907)451-2281 | September 2024 | Reconstruct eleven signalized intersections at multiple locations in the City of Fairbanks. Work includes intersection improvements and roadside hardware. | This project will advertise with NFHWY00904. | Less than $200,000
SFHWY00536 | KTN N. Tongass Hwy Resurface: A/P F.T. to Ward Creek Bridge Stage 1 | SFHWY00536 | 0920031 | Southcoast Region | Ketchikan | Brett M Wells | (907)465-1607 | September 2024 | The project includes highway milling and paving, guardrail replacement, culvert replacement and lining, grading, and striping. |  | Between $5,000,000 and $10,000,000
NFHWY00904 | Northern Region Systemic Signal Upgrades - Stage 1 (HSIP) | NFHWY00904 | N/A | Northern Region | Regionwide | Ethan E Graetz | (907)451-2281 | September 2024 | Reconstruct seven signalized intersections at multiple locations in the Fairbanks and Parks Highway Nenana Canyon area. Work includes intersection improvements and roadside hardware. | This project will advertise with NFHWY00905. | Between $5,000,000 and $10,000,000
CFHWY01083 | PARKS HIGHWAY PHASE I, CULVERT REPLACEMENT | CFHWY01083 | N/A | Central Region | Wasilla | Aaron L Hunting | (907)269-0546 | September 2024 | Culvert replacement, drainage improvements, ditch grading, guardrail, signage, utility relocations, clearing and grubbing. This Child Project will construct the first phase of improvements included in the Parent Project CFHWY00592. . | <a class=linkcopy href="https://dot.alaska.gov/creg/design/highways/Projects/01083/CFHWY01083_Plans.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $5,000,000 and $10,000,000
CFHWY01084 | PARKS HIGHWAY PHASE II - RAILROAD CREEK BRIDGE | CFHWY01084 | N/A | Central Region | Wasilla | Aaron L Hunting | (907)269-0546 | September 2024 | New bridge, drainage improvements, ditch grading, guardrail, signage, utility relocations, clearing and grubbing. This Child Project will construct the second phase of improvements included in the Parent Project CFHWY00592. | Construct a bridge at Railroad Creek at MP128.5 along the Parks Highway. | Between $10,000,000 and $20,000,000