## Tentative Award Schedule
PROJID | PROJNAME | STATENUM | FEDNUM | REGION | LOCATION | PROJMAN | PHONENUM | ANTADVDT | DESCRIPTION | ADDLINFO | ENGEST
SFAPT00289 | SR Airport Pavement Markings FFY22 | SFAPT00289 | 3-02-0000-027-2020 | Southcoast Region | Regionwide | David B Epstein | (907)465-4446 | 2022-01-01 | Perform SPM at various primary and non-primary airports in SR. Planned maintenance activities include: maintaining pavement markings on runways, taxiways, and aprons at Gustavus, Ketchikan, Petersburg, Wrangell, and Yakutat. |  | Between $500,000 and $1,000,000
SFAPT00174 | FFY18 VARIOUS PRIMARY/NON-PRIMARY EAS A/P VISUAL AID REPLCMN | SFAPT00174 | 3-02-0200-121-2018 | Southcoast Region | Regionwide | Peter J Jackson | (907)465-4439 | 2022-02-01 | Replace lighted beacon at Yakutat Airport. | To be advertised with project SFAPT00203 (relocate Segmented Circle and Lighted Wind Cone). | Between $200,000 and $500,000
SFAPT00203 | FFY19 VARIOUS PRIMARY/NON PRIMARY EAS AIRPORTS VISUAL AID RE | SFAPT00203 | 3-02-0200-126-2019 | Southcoast Region | Regionwide | Peter J Jackson | (907)465-4439 | 2022-02-01 | Remove and relocate primary wind cone and segmented circle at Yakutat Airport including gravel pad and access road work. | To be advertised with Project SFAPT00174 | Between $200,000 and $500,000
NFHWY00447 | Airport Way West Bicycle/Pedestrian Facility | NFHWY00447 | 2449 | Northern Region | Fairbanks | David K Fischer | (907)451-5357 | 2022-03-01 | Construct a bicycle/pedestrian connection on Airport Way West from the Fairbanks International Airport terminal to Dale Road. Work will include drainage and intersection improvements, and roadside hardware. |  | Between $500,000 and $1,000,000
NFHWY00589 | Alaska Highway MP 1222-1227 Resurfacing | NFHWY00589 | 0A22007 | Northern Region | Alcan Border | Ivet Hall | (907)451-5386 | 2022-03-01 | Resurface the Alaska Highway from MP 1222-1227. Project will include bridge work, drainage improvements, roadside hardware, and utilities. | will be combined with NFHWY00624 Alaska Highway 1235-1252 Rehabilitation | Between $2,500,000 and $5,000,000
NFHWY00624 | Alaska Highway MP 1235-1252 Rehabilitation | NFHWY00624 | PENDING | Northern Region | Northway | David K Fischer | (907)451-5357 | 2022-03-01 | Rehabilitate the Alaska Highway between Milepost 1235-1252 and construct new passing lanes. Project work will include bridge work, roadside hardware, drainage improvements, intersection improvements, utilities and wayside repairs. |  | Between $20,000,000 and $30,000,000
CFAPT00718 | ANC GATES B4, B6, B7, B8, & B9 IMPROVEMENTS | CFAPT00718 | 3-02-0016-214-2022 | Central Region | Anchorage | Philip W Cheasebro | (907)269-0606 | 2022-03-01 | This project will re-seal joints and repair cracks in concrete handstands at Gate B4, B6, B7, B8, & B9 and perform drainage repairs as required. Expected funding FFY 2022. | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/5_00718%20-%20ANC%20Gates%20B4,%20B6,%20B7,%20B8%20&%20B9%20Improvements%20Pre%20PSE-TAS.pdf ">Preliminary Plans (~7.5 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $1,000,000 and $2,500,000
SAMHS00279 | AUKE BAY TERMINAL BUILDING AND ELECTRICAL IMPROVEMENTS | SAMHS00279 | 9500150 | Marine Highways | Juneau | Loren K Gehring | (907)465-8189 | 2022-03-01 | Make improvements to the Auke Bay Ferry Terminal Building, including: ticket counter modifications, bathroom modifications, door replacement, roof and gutter replacement, and drainage improvements. This project would also provide a new East Berth vessel shore tie electrical connection. |  | Between $1,000,000 and $2,500,000
NSHWY00479 | Burma Pit Road Little Tonsina Bridge Replacement | NSHWY00479 | N/A | Northern Region | Tonsina | David M Arvey | (907)451-2621 | 2022-03-01 | Replace the Little Tonsina River culverts with a new bridge; Little Tonsina River Bridge #568, on Burma Pit Road near MP 74.2 of the Richardson Highway. |  | Between $1,000,000 and $2,500,000
NFAPT00354 | Eagle Airport Electrical Equipment Building Replacement | NFAPT00354 | 3-02-0083-___-____ | Northern Region | Eagle | Christopher F Johnston | (907)451-2322 | 2022-03-01 | Replace the electrical equipment building at the Eagle Airport. | This project will advertise with the Tok Airport Electrical Equipment Building Replacement, NFAPT00684. | Between $200,000 and $500,000
SFAPT00212 | FFY18 ST. PAUL AIRPORT VISUAL AID REPLACEMENT | SFAPT00212 | 3-02-0200-120-2018 | Southcoast Region | Regionwide | Peter J Jackson | (907)465-4439 | 2022-03-01 | Remove and replace secondary wind cone and install new conduit and wire. Remove and replace primary wind cone and install new conduit and wire. Remove and replace rotating Airport Beacon. Phase 4 - CC 24300206 LC 33004012 |  | Between $200,000 and $500,000
SDRER00408 | HNS MOSQUITO LAKE ROAD #550474 - DEC 20 SE PR | SDRER00408 | PENDING FEMA RSA -DMV | Southcoast Region | Haines | Joel D Osburn | (907)465-4409 | 2022-03-01 | This project will permanently repair damage on Mosquito Lake Road caused by the December 2020 storm event in Southeast Alaska. The project includes repairing an embankment failure and replacing a damaged culvert. This is a FEMA funded project which will be reimbursed thru RSA with DMVA |  | Between $200,000 and $500,000
21-25-1-031 | Kalskag Airport (KLG) Surface Preservation Maintenance (SPM) | 21-25-1-031 | CFAPT00823 / AIP 3-02-0136-XXX-2022 | Central Region | Kalskag | Vernon S Vreeland | (907)269-0778 | 2022-03-01 | Scarify, reshape and recompact surfacing material at runway, taxiway, and apron to proper profile. Apply dust palliative to retain the critical fine particles now present in the crushed surface and to bind aggregate to prevent loss of fines from the runway, taxiway, and apron surfaces. Apply dust palliative for RWY 6/24 (3,200 LF), TWY (208 LF) and apron (11,250 SY). Work shall consist of spot treatments for all areas within the limits designated on the drawings or as required by the Project Manager. All work shall be in accordance with the Alaska Department of Transportation & Public Facilities “Standard Specifications for Airport Construction, revised 01/01/20” and attachments. Payment shall be made at the contract unit price. This payment shall be full compensation for all requirements of this contract. |  | Between $200,000 and $500,000
21-25-1-029 | Koliganek Airport (JZZ) Surface Preservation Maintenance (SPM) | 21-25-1-029 | CFAPT00820 / AIP 3-02-0424-XXX-2022 | Central Region | Koliganek | Vernon S Vreeland | (907)269-0778 | 2022-03-01 | Purchase, haul, place and compact crushed aggregate surface course (CASC) for RWY 9/27 (3,300 LF), TWY (175 LF) and Apron (66,667 SY (as needed)). All work shall be in accordance with the Alaska Department of Transportation & Public Facilities “Standard Specifications for Airport Construction, revised 01/01/20” and attachments. Payment shall be made at the contract unit price. This payment shall be full compensation for all requirements of this contract. |  | Between $200,000 and $500,000
NFAPT00650 | Kotzebue Airport Runway Settlement Repair | NFAPT00650 | Pending | Northern Region | Kotzebue | Jonathan J Hutchinson | (907)451-5479 | 2022-03-01 | Repair significant depressions on Runway 9/27 that are causing large ponds to form between Taxiways C and D. | 22E | Between $2,500,000 and $5,000,000
Z674660000 | KTN FERRY TERMINAL IMPROVEMENTS (X-REF#SAMHS00015) | Z674660000 | 000S855 | Marine Highways | Ketchikan | Loren K Gehring | (907)465-8189 | 2022-03-01 | This project encompasses the replacement of an existing vessel berthing and turning dolphin structure at the west end of Berth 1; placement of a new turning dolphin between Berths 1 and 3, refurbishment of fendering and platform components at the Berth 3 float; construction of a new pedestrian cover structure over the existing sidewalk from the terminal building to the Berth 3 approach; and the placement of cathodic protection anodes on all existing offshore pile supported structures at Berths 1 and 3. | Refurbish fender system at Berth 3 and conduct minor improvements to utilities at Berth 1. | Between $2,500,000 and $5,000,000
CFHWY00428 | Mchugh RWIS Tower Upgrade | CFHWY00428 | 0106(094) | Central Region | Municipality Of Anchorage | John W Turley | (907)266-2171 | 2022-03-01 | RWIS facilities must be migrated off of the existing tower at McHugh MP 111.8 of the Seward Highway. The existing tower will be demolished and a new tower will be installed within DOT ROW. |  | Between $200,000 and $500,000
SFHWY00306 | POW HOLLIS HWY GUARDRAIL SAFETY IMPROVEMENTS HSIP | SFHWY00306 | 3260 | Southcoast Region | Prince Of Wales Island | Nathan A Purves | (907)465-4483 | 2022-03-01 | Determine the extent of the zone where we can expect a driver to recover control of there vehicle and remove/replace downstream guardrail end anchors that fall in that zone with guardrail parallel end terminals that are compliant with the Manual for Assessing Safety Hardware 16 (MASH16). |  | Between $200,000 and $500,000
SFHWY00379 | PSG Mitkof Hwy MPt 10.8 Culvert Replacement - DEC 20 SE PR | SFHWY00379 | AK2021-1 | Southcoast Region | Petersburg | Joel D Osburn | (907)465-4409 | 2022-03-01 | This project is a Permanent Repair (PR) due to flooding that occurred during the December, 2020 storm event in the Southcoast Region of Alaska. The project need is to replace the existing 5.5' diameter culvert at Mitkof Highway milepoint (MPt) 10.8 to current standards and provide slope and road stability with a new 7' diameter culvert. Repairs may include, but are not limited to, asphalt, embankment, riprap, and drainage. This project repairs sites corresponding to Detailed Damage Inspection Report DDIR AK 2020 01 PTG001. |  | Between $200,000 and $500,000
21-25-1-032 | Red Devil Airport (RDV) Surface Preservation Maintenance (SPM) | 21-25-1-032 | CFAPT00824 / AIP 3-02-0246-XXX-2022 | Central Region | Red Devil | Vernon S Vreeland | (907)269-0778 | 2022-03-01 | Scarify, reshape and recompact surfacing material at runway, taxiway, and apron to proper profile. Apply dust palliative to retain the critical fine particles now present in the crushed surface and to bind aggregate to prevent loss of fines from the runway, taxiway, and apron surfaces. Apply dust palliative for RWY 10/28 (4,800 LF), TWYs A (325 LF), B (220 LF) and Apron (13,333 SY). Work shall consist of spot treatments for all areas within the limits designated on the drawings or as required by the Project Manager. All work shall be in accordance with the Alaska Department of Transportation & Public Facilities “Standard Specifications for Airport Construction, revised 01/01/20” and attachments. Payment shall be made at the contract unit price. This payment shall be full compensation for all requirements of this contract. |  | Between $200,000 and $500,000
SFHWY00401 | SE DISTRICT HIGHWAY PAINTING FFY22 | SFHWY00401 | 3273 | Southcoast Region | Regionwide | Marcus G Zimmerman | (907)465-4655 | 2022-03-01 | SR M&O SE DISTRICT HWY PAINTING 22
Z637720000 | Selawik Barge Landing Access Road & Boardwalk Improvements | Z637720000 | 2280 | Northern Region | Selawik | Christopher F Johnston | (907)451-2322 | 2022-03-01 | Rehabilitate the Barge Landing Access Road and Boardwalk in Selawik, Alaska. Project will include construction of a new barge staging pad, and associated access points, roadside hardware, and utilities. |  | Between $5,000,000 and $10,000,000
NFHWY00631 | Taylor Highway MP 54 Culvert Replacement | NFHWY00631 | Pending | Northern Region | Tok | John J Netardus | (907)451-5448 | 2022-03-01 | Replace a fish passage culvert on the Taylor Highway at MP 54. Project includes drainage improvements and roadside hardware. | DOT&PF's ability to upload pdfs is currently having issues. If you would like a copy of the preliminary plans, please contact john.netardus@alaska.gov | Between $500,000 and $1,000,000
NFAPT00684 | Tok Airport Electrical Equipment Building Replacement | NFAPT00684 | 3-02-0412-___-____ | Northern Region | Tok | Christopher F Johnston | (907)451-2322 | 2022-03-01 | Replace the electrical equipment building at the Tok Airport. | This project will advertise with the Eagle Airport Electrical Equipment Building Replacement, NFAPT00354. | Between $200,000 and $500,000
Z618720000 | Airport Way (West) Improvements | Z618720000 | 610004 | Northern Region | Fairbanks | David K Fischer | (907)451-5357 | 2022-04-01 | Reconstruct Airport Way, Hoselton Road, Dale Road, Old Airport Way and Wien Lake Road. Work includes roadside hardware, drainage improvements, intersection improvements, utilities and ADA improvements such as curb ramps and sidewalks. |  | Between $10,000,000 and $20,000,000
NFAPT00500 | Brevig Mission Airport Lighting and Resurfacing | NFAPT00500 | 3-02-0400-XX-202X | Northern Region | Brevig Mission | Jonathan J Hutchinson | (907)451-5479 | 2022-04-01 | Resurface the runways, taxiway, apron. Stabilize slopes, rehabilitate shoulders, and apply a dust palliative. Rehabilitate airport lighting. | EE is Construction Estimate | Between $10,000,000 and $20,000,000
CFAPT00501 | CHEFORNAK AIRPORT REHAB | CFAPT00501 | 3-02-0054-XXX-202X | Central Region | Chefornak | Aaron C Hughes | (907)269-0523 | 2022-04-01 | Rehabilitate the runway, taxiway, apron, and airport access road surfaces and replace airport lighting. |  | Between $10,000,000 and $20,000,000
Z609110000 | DALTON HWY MP 0-9 RECONSTRUCTION | Z609110000 | 652016 | Northern Region | Regionwide | Carl F Heim | (907)451-5359 | 2022-04-01 | Reconstruct the Dalton Highway between MP 0-9. Work includes bridge work, drainage improvements, utilities, and roadside hardware. | Reconstruct the Dalton Highway from MP 0-9. Work includes re-routing the highway approximately 7.5 miles, constructing a new bridge over Lost Creek, new culverts, and an application of dust palliative. Project will be advertised as CMGC RFP. Project website: https://dot.alaska.gov/nreg/dalton/ | Between $40,000,000 and $50,000,000
NFHWY00603 | FAST Area Surface Upgrades FFY2022 | NFHWY00603 | Pending | Northern Region | Fairbanks North Star Borough | John J Netardus | (907)451-5448 | 2022-04-01 | Resurface pavement, resurface unpaved roadway, and install protective driveway aprons on various streets in Fairbanks and North Pole. |  | Between $500,000 and $1,000,000
CFHWY00300 | Homer: West Hill Road Sterling Highway to Skyline Drive | CFHWY00300 | 1599 | Central Region | Homer | Matthew H Hansen | (907)269-0602 | 2022-04-01 | Resurface the West Hill Road from the Sterling Highway to Skyline Dr. Improvements may include signing, striping, drainage, pavement, dig-outs, curb ramps, guardrail, lighting, and utility relocation. | Resurface West Hill Road in Homer, Alaska from the Sterling Highway to Skyline Dr. | Between $2,500,000 and $5,000,000
SFHWY00186 | HSIP KTN STEDMAN & DEERMOUNT ST INTERSECTION SAFETY IMP | SFHWY00186 | 3244 | Southcoast Region | Ketchikan | Nathan A Purves | (907)465-4483 | 2022-04-01 | Provide additional illumination at the Stedman/Deermount intersection to achieve a level of luminance that meets current DOT&PF standards. Construct a concrete sidewalk bulbout on the Stedman side of the marked crosswalk. The bulbout will extend from the existing sidewalk to the edge of the traveled way. |  | Between $500,000 and $1,000,000
SDRER00409 | JNU THANE ROAD 189449 - DEC 20 SE PR | SDRER00409 | WILL BE FEMA RSA -DMV | Southcoast Region | Juneau | Joel D Osburn | (907)465-4409 | 2022-04-01 | This project is a Permanent Repair (PR) due to flooding that occurred during the December, 2020 storm event in Southcoast Region of Alaska. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, and drainage. This project repairs a site on Thane Road at MPt 4.4. This is a FEMA funded project which will be reimbursed thru RSA with DMVA |  | Between $500,000 and $1,000,000
CFHWY00599 | KNIK-GOOSE BAY RD RECONST, PHASE 1 - FAIRVIEW LOOP TO CENTAUR AVENUE | CFHWY00599 | 525019 | Central Region | Wasilla | Tom J Schmid | (907)269-0543 | 2022-04-01 | Project consists of reconstructing Knik Goose Bay Road to a divided 4 lane facility from Centaur Ave (near Palmer-Wasilla Hwy) to Fairview Loop. Scope includes roadside hardware, drainage improvements, intersection improvements, ADA improvements, utilities and access management. Project will be constructed in two phases. The first phase of construction (Fairview Loop Road to Centaur Ave., approx. 4mi) will be advertised under project CFHWY00599. The 2nd phase (Settlers Bay to Fairview Loop Road, approx. 4mi) will be constructed under project Z524640000 and project 51717. | <a class=linkcopy href="http://www.dot.state.ak.us/creg/design/highways/Projects/00599/00599.pdf">Preliminary Plans (~74 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $40,000,000 and $50,000,000
25RC182609 | NOR REG DYNAMIC MESSAGING SIGNS - TARGETED AIRSHED GRANT | 25RC182609 | N/A | Northern Region | Fairbanks North Star Borough | Ethan E Graetz | (907)451-2281 | 2022-04-01 | Install and operate digital messaging signs on the Parks Highway MP 357 and Richardson Highway MP 359. |  | Between $1,000,000 and $2,500,000
CFAPT00293 | SLEETMUTE AIRPORT RESURFACING | CFAPT00293 | 3-02-0272-00X-20XX | Central Region | Sleetmute | Aaron C Hughes | (907)269-0523 | 2022-04-01 | The project proposes to resurface the runway, taxiway, apron, and access roads at the Sleetmute Airport. Improvements may also include snow removal equipment buildings, lighting, markings, signs, navigational aids, drainage, and a dust palliative. | The project proposes to resurface the runway, taxiway, apron, and access road at the Sleetmute Airport. Improvements may also include snow removal equipment buildings, lighting, markings, signs, navigational aids, drainage, a dust palliative, vegetation clearing, and utilities. This project is expected to be ready to advertise but federal funding is not currently expected to be available this federal fiscal year. | Between $10,000,000 and $20,000,000
Z686560000 | SR REGIONWIDE NHS SLOPE STABILIZATION | Z686560000 | 3188 | Southcoast Region | Regionwide | Darryl Lester | (907)465-4421 | 2022-04-01 | This project will construct a maintenance access to a location on the Haines mile 19 debris flow. Construction activities include clearing, grubbing, excavation, grading, signage, fabrication of a vehicle access gate, and implementation of BMPs. |  | Between $500,000 and $1,000,000
NFHWY00550 | Tetlin National Wildlife Refuge Visitor Center (WFL) | NFHWY00550 | 27563001 | Northern Region | Tetlin | David K Fischer | (907)451-5357 | 2022-04-01 | Paving of a parking area at the Tetlin National Wildlife Refuge Visitor Center at MP 1229.0, a new vault toilet at the Hidden Lake Trail Head at MP 1240.0, and paving the driveway at the Tetlin National Wildlife Refuge Headquarters in Tok at MP 1314.0. | Anticipate advertising with Alaska Highway MP 1235-1252, NFHWY00624 | Between $200,000 and $500,000
CFHWY00223 | A STREET, NORTHERN LIGHTS TO 40TH AVE PAVEMENT PRESERVATION | CFHWY00223 | 527030 | Central Region | Anchorage | Kevin L Jackson | (907)269-0610 | 2022-05-01 | Pavement preservation of A Street from Northern Lights Blvd to 40th Ave including improvements to drainage, intersections, ADA, roadside hardware, and utilities. |  | Between $2,500,000 and $5,000,000
CSAPT00915 | ANC RUNWAY 7R/25L JOINT REPAIR | CSAPT00915 | N/A | Central Region | Anchorage | Jennifer M Carle | (907)602-2511 | 2022-05-01 | Project will include repairing longitudinal joints and asphalt in the structural section of Runway 7R/25L. There is approximately 160,000 linear feet of joints to repair. | Project will repair joints and asphalt on Runway 7R/25L. | Between $2,500,000 and $5,000,000
CFHWY00551 | ANCHORAGE AREA DRAINAGE IMPROVEMENTS FY2019 | CFHWY00551 | 1651 | Central Region | Anchorage | Galen K Jones | (907)269-0550 | 2022-05-01 | Drainage infrastructure maintenance/repair and erosion mitigation to eliminate threats to the State's transportation system within the Anchorage area. Infrastructure including culverts, drainage basins, storm drain systems, ditches, swales, bridge embankments and abutments, side slopes, erosion protection features (such as dikes and rip rap), and other pertinent drainage and erosion protection infrastructure will be repaired, replaced, or improved as necessary. Roadways, pathways, sidewalks, and roadside appurtenances affected by drainage improvements are included. |  | Between $2,500,000 and $5,000,000
NFHWY00290 | COLLEGE ROAD BUS PULLOUTS | NFHWY00290 | 640012 | Northern Region | Fairbanks | John J Netardus | (907)451-5448 | 2022-05-01 | Construct new bus stop facilities along College Road. Work includes roadside hardware, drainage improvements, ADA improvements and utilities. |  | Between $500,000 and $1,000,000
NFHWY00539 | Copper River Boat Launch Facilities Improvements (FLAP) | NFHWY00539 | 851072 | Northern Region | Mccarthy | Daniel S Adamczak | (907)451-2294 | 2022-05-01 | Improve the Copper River Boat Launch facilities located at MP 1.5 on the McCarthy Road. Work includes roadside hardware and drainage improvements.
CFHWY00260 | CTF ALTERNATE ENTRANCE ALIGNMENT (WFL) | CFHWY00260 | AKBLM AFO 2014(1) | Central Region | Anchorage | Christopher L Post | (907)269-7885 | 2022-05-01 | Relocate the BLM Road to the Cambell Tract Facility 260 feet to align East 68th Avenue with intersection improvements to include bus stop and integration to existing signalized intersection. |  | Between $2,500,000 and $5,000,000
Z607350000 | Dalton Hwy MP 18-37 Reconstruction | Z607350000 | 652017 | Northern Region | Northern Region | Carl F Heim | (907)451-5359 | 2022-05-01 | Reconstruct the Dalton Highway from Milepost 18 to 37. The project work includes bridge work, roadside hardware and drainage improvements. Bridge work includes Hess Creek Bridge #1213 replacement. |  | Between $50,000,000 and $60,000,000
CFHWY00395 | ELMORE ROAD PAVEMENT PRESERVATION: ABBOTT RD TO PROVIDENCE | CFHWY00395 | 1642 | Central Region | Anchorage | Christopher L Post | (907)269-7885 | 2022-05-01 | Pavement Preservation project for Elmore Road: Abbott Rd. to Providence Dr. This project includes resurfacing, roadside hardware, drainage improvements, intersection improvements, and ADA improvements as necessary. |  | Between $10,000,000 and $20,000,000
NFHWY00627 | FAIRBANKS AREA PM 2.5 PLUG-INS: BIRCH HILL, CHENA LAKES, UAF | NFHWY00627 | N/A | Northern Region | Fairbanks North Star Borough | Ethan E Graetz | (907)451-2281 | 2022-05-01 | Provide electrical motor vehicle plug-ins at the following locations in the Fairbanks PM 2.5 non-attainment area: Birch Hill, Chena Lakes, and the UAF U-Park Building. Project includes utilities and drainage improvements. |  | Between $1,000,000 and $2,500,000
NFHWY00269 | FMATS North Pole Streetlight Standardization & Improvements | NFHWY00269 | 2403 | Northern Region | North Pole | Ethan E Graetz | (907)451-2281 | 2022-05-01 | Replace the lighting system with more energy efficient technologies and install new LED luminaires. Work will include roadside hardware and utilities. |  | Between $2,500,000 and $5,000,000
CFHWY00677 | HSIP: A ST. MIDTOWN COUPLET OVERHEAD SIGNAL INDICATION U/G | CFHWY00677 | 1684 | Central Region | Anchorage | Kevin L Jackson | (907)269-0610 | 2022-05-01 | Upgrade roadside hardware on A Street between Benson Boulevard and Northern Lights Boulevard. Work incudes removing and replacing the traffic signals at the intersection of Benson Boulevard and A Street and Northern Lights Boulevard and A Street and lighting system replacment adjacent to intersections. |  | Between $1,000,000 and $2,500,000
CFHWY00366 | HSIP: ANCHORAGE PEDESTRIAN LIGHTING | CFHWY00366 | 1607 | Central Region | Anchorage | Christopher L Post | (907)269-7885 | 2022-05-01 | This HSIP Funded Project will increase visibility, reduce pedestrian/bicycle crashes and other traffic incidences by installing lighting. The proposed improvements are consistent with the Alaska Strategic Highway Safety Plan, Special Users Strategies to identify and implement appropriate engineering to address high-crash locations involving bicyclists and pedestrians. This project is also inline with MOA Vision Zero Safety Goals. | <a class=linkcopy href="http://www.dot.state.ak.us/creg/design/highways/Projects/00366/00366.pdf">Preliminary Plans (~38 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $1,000,000 and $2,500,000
SFHWY00163 | JNU DOUGLAS HIGHWAY SLOPE STABILIZATION | SFHWY00163 | 959021 | Southcoast Region | Juneau | David A Pyeatt | (907)465-4490 | 2022-05-01 | Repair a recent slope failure adjacent to a soldier pile and lagging retaining wall along the Juneau-Douglas Highway, in Douglas, Alaska. The slope failure impacted adjacent property and exposed the solider pile and lagging wall supporting the Juneau-Douglas Highway and pedestrian pathway. The purpose of the project is to protect the highway slope from failure due to down slope landslide activity out of the ROW by constructing a soldier pile wall. | Project to be advertised with SFHWY00315. | Between $1,000,000 and $2,500,000
SFHWY00315 | JNU DOUGLAS HWY STAGE 2 CONSTRUCTION | SFHWY00315 | 958032 | Southcoast Region | Juneau | David A Pyeatt | (907)465-4490 | 2022-05-01 | Work required for this project includes reconstructing and resurfacing Douglas Highway from about 700 feet south of Cordova Street to F Street. Other work includes ADA improvements, storm drain system repairs, signing and striping improvements, and bridge joint repairs. A list of anticipated work items are listed below: • Pavement removal and roadway excavation • Pavement cold planing • Removal and installation of concrete gutter and curb & gutters • Removal and installation of asphalt and concrete sidewalks • Reconstruction of existing accessible sidewalk ramps • Replacement and lining of existing culverts and storm drains • Construction of riprap aprons • Installation of new curb inlets • Removal and installation of storm drain manholes • Replacement of existing signs • Addition of new signs • New pavement markings • Replacement of existing guardrail and bridge transition rail • Repairs to existing Lawson Creek Bridge joints • Replacement of wood planter box and steps with concrete retaining wall and wood stairs at Villa Gastineau Condos |  | Between $5,000,000 and $10,000,000
SFHWY00263 | JNU FRANKLIN AND THANE RESURFACING: TRAM PARKING LOT TO MT. ROBERTS ST | SFHWY00263 | 3250 | Southcoast Region | Juneau | Darryl Lester | (907)465-4421 | 2022-05-01 | Resurface Franklin Street from the Tram parking lot to the intersection of Thane Road and Mt. Roberts Street. Associated preventive maintenance activities may include minor structural section improvements, drainage repairs, striping, signs, and ADA improvements. | Pending funding availability. Advertisement may be delayed. | Between $1,000,000 and $2,500,000
CFAPT00433 | KONGIGANAK AIRPORT IMPROVEMENTS | CFAPT00433 | 3-02-0380-004-2022 | Central Region | Kongiganak | Philip W Cheasebro | (907)269-0606 | 2022-05-01 | This project will rehabilitate airport surfaces, expand the apron and runway safety areas (RSA), install a Snow Removal Equipment Building (SREB) and relocate the existing SREB. Install a rotating beacon on a tip-down pole, tie-downs, and replace airfield lighting at the Kongiganak Airport. Expected FFY 2022 funding. | Pre PS&E review documents are located at the link below: <a class=linkcopy href="http://www.dot.state.ak.us/creg/design/aviation/Tentative_Advertising_List_Docs/4_00433%20Kongiganak%20Pre%20PSE%20Plans_TAL.pdf">Preliminary Plans (~13 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
SFHWY00069 | KTN - WATER ST TRESTLE #1 IMPRVMNT | SFHWY00069 | 3224 | Southcoast Region | Ketchikan | Kirk D Miller | (907)465-1215 | 2022-05-01 | This project will replace or rehabilitate the Water Street Trestle No. 1 (No. 389). |  | Between $1,000,000 and $2,500,000
CFHWY00132 | MINNESOTA DR: TUDOR TO 15TH AVE PAVEMENT PRESERVATION | CFHWY00132 | 421099 | Central Region | Anchorage | Steven J Rzepka | (907)269-0592 | 2022-05-01 | This is a Preventive Maintenance (PM) project for resurfacing Minnesota Drive in Anchorage, Alaska from Tudor Road to 15th Avenue. It will also include, as necessary: guardrail, drainage, signalization, ADA curb ramp improvements, signs and striping. | Resurface Minnesota Drive in Anchorage, Alaska from Tudor Road to 15th Avenue. It will also include, roadside hardware, drainage, signalization, ADA curb ramp improvements. | Between $10,000,000 and $20,000,000
CFHWY00406 | MULDOON RD - DEBARR RD TO E 36TH AVE PAVEMENT PRESERVATION | CFHWY00406 | 544022 | Central Region | Anchorage | Sean M Baski | (907)269-0566 | 2022-05-01 | This is a preventative maintenance project for resurfacing Muldoon Road from Debarr Road to East 36th Avenue. This project includes resurfacing, roadside hardware, drainage improvements, intersection improvements, and ADA improvements as necessary. |  | Between $5,000,000 and $10,000,000
NFHWY00551 | Northern Region ADA Improvements - Fairbanks: 6th Avenue | NFHWY00551 | N/A | Northern Region | Northern Region | Ivet Hall | (907)451-5386 | 2022-05-01 | This project proposes to reconstruct ADA improvements and potentially widen the north sidewalk on the 6th Avenue in Fairbanks, Alaska. The project may also include reconstruction, roadside-hardware, drainage improvements, intersection improvements and utilities. | Anticipated to advertise with NFHWY00504 project. | Between $500,000 and $1,000,000
NFHWY00504 | Northern Region ADA Improvements - Fairbanks: Geist Road | NFHWY00504 | Pending | Northern Region | Fairbanks | Ivet Hall | (907)451-5386 | 2022-05-01 | This project proposes to reconstruct ADA improvements and potentially widen sidewalks on both sides of Geist Road within the project area in Fairbanks, Alaska. The project may also include reconstruction, roadside-hardware, drainage improvements, intersection improvements and utilities. | Anticipated to advertise with NFHWY00551 project. | Between $500,000 and $1,000,000
Z638420000 | Point Hope Airport Realignment | Z638420000 | 3-02-0226-___-____ | Northern Region | Point Hope | Jonathan J Hutchinson | (907)451-5479 | 2022-05-01 | Realign the runway at the Point Hope Airport. | CY21 and CY22 | Between $20,000,000 and $30,000,000
NFHWY00583 | Richardson Highway MP 329-340 Pavement Preservation | NFHWY00583 | 714027 | Northern Region | Eielson Afb | Ivet Hall | (907)451-5386 | 2022-05-01 | Resurface the Richardson Highway between MP 329-340. Work will include pavement preservation, roadside hardware, drainage improvements, and utilities. |  | Between $2,500,000 and $5,000,000
NFHWY00694 | Richardson Highway MP 40-51 Resurfacing | NFHWY00694 | 711082 | Northern Region | Valdez | Colleen M Ackiss | (907)451-5179 | 2022-05-01 | Resurface the Richardson Highway between MP 40-51. Improvements include bridge work, roadside hardware, drainage, and utility relocations. |  | Between $10,000,000 and $20,000,000
CFHWY00109 | SEWARD HWY: MP 0 TO 8 PAVEMENT PRESERVATION | CFHWY00109 | 311034 | Central Region | Seward | Chris L Bentz | (907)269-0652 | 2022-05-01 | Resurface the Seward Highway from Milepoint 0-8. The project will also include, as necessary, improvements to pedestrian curb ramps, guardrail, guardrail end treatments, dig-outs, drainage repair, sign replacement, replacement striping, and utility adjustments as needed. | Resurface the Seward Highway from MP 0-8. Project also includes markings, signage, pedestrian curb ramps, guardrail, guardrail end sections, brush clearing, drainage improvements, and utility adjustments. | Between $5,000,000 and $10,000,000
Z680850000 | SGY STATE STREET PAVEMENT REHABILITATION | Z680850000 | 972018 | Southcoast Region | Skagway | David A Pyeatt | (907)465-4490 | 2022-05-01 | Rehabilitate the pavement, replace curb and gutter in select areas, upgrade curb ramps and vehicular curb cuts to meet ADA standards, repair and/or replace drainage facilities as needed, and replace all signs within the project limits. | Rehabilitate the pavement from 1st Avenue to the Skagway River Bridge. Repair and/or replace existing drainage infrastructure. Replace existing sidewalk, curb ramps, and driveways to meet current ADA requirements. | Between $10,000,000 and $20,000,000
SSAPT00093 | SR DM AIRPOR GATE/FENCE REPAIRS/REPLACEMENT | SSAPT00093 | N/A | Southcoast Region | Gustavus | Bran P Pollard | (907)465-4526 | 2022-05-01 | Replace an existing electric cantilever gate with a new 24’ electric vertical pivot gate on a new concrete foundation at the Gustavus Airport. Project gate will connect to the existing Airport Access Control System, existing automatic vehicle gate controllers, and existing auxiliary automatic vehicle gate safety control systems. Includes removal of existing 20' cantilever gate, removal of existing concrete foundation, and removal of existing fencing. |  | Less than $200,000
CFHWY00568 | AMATS: HILAND RD MP 0 TO MP 3.2 PAVEMENT PRESERVATION | CFHWY00568 | 1663 | Central Region | Eagle River | Galen K Jones | (907)269-0550 | 2022-06-01 | Resurface Hiland Road, including milling, paving, minor subgrade rehabilitation, drainage improvements, updating guardrail and sign posts to meet current safety standards, replacing striping and select signage, curb and gutter, lighting, and roadside signal and or traffic data hardware. |  | Between $2,500,000 and $5,000,000
CFAPT00465 | ANC TAXIWAY Z WEST IMPROVEMENTS | CFAPT00465 | N/A | Central Region | Anchorage | Philip W Cheasebro | (907)269-0606 | 2022-06-01 | This Federally Funded contract provides geometric upgrades as necessary to accommodate larger ADG VI, TDG 6 aircraft. The proposed geometric upgrades include widening Taxiway's Z & E, constructing a new entrance Taxiway R, and rehabilitating Taxilane's R & E. Additional work includes: • Rehabilitate or relocate existing private taxilane approaches as needed • Remove TW F entrance taxiway • Relocate existing service road • Drainage improvements • Replace taxiway lighting and sign and install new lights and signs as needed • Relocate/adjust utilities as needed • Relocate/adjust FAA NAVAIDS as needed | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/CFAPT00465 ANC Taxiway Z Improvements West - Phase 1 - PrePSE.pdf ">Preliminary Plans (~46 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
SFAPT00236 | HNH SEAPLANE FACILITY DREDGING AND CREEK RELOCATION | SFAPT00236 | N/A | Southcoast Region | Hoonah | Loren K Gehring | (907)465-8189 | 2022-06-01 | Relocation of an existing stream bed and conduct dredging under the seaplane mooring float to restore sufficient water depths and/or relocation of the seaplane float structure to deeper water at the same location. Phase: T02000 - Par - All Costs |  | Between $500,000 and $1,000,000
CFHWY00253 | KENAI SPUR RD REHAB: SPORTS LAKE RD TO SWIRES RD PH 2 | CFHWY00253 | 221019 | Central Region | Kenai | Christina A Huber | (907)269-0572 | 2022-06-01 | This project will rehabilitate the Kenai Spur Highway between Soldotna and Kenai. A 5-lane highway will be constructed between the Sports Lake Road and Robin Drive intersections to increase capacity and improve safety. This is the second of two phases to construct the project. |  | Between $20,000,000 and $30,000,000
Z680910000 | KTN TONGASS AVE IMPROVEMENTS | Z680910000 | 902042 | Southcoast Region | Ketchikan | Peter J Jackson | (907)465-4439 | 2022-06-01 | Refurbish Tongass Avenue, from MP 0.2000 to 1.2798 including rehabilitation of asphalt and concert pavement surfaces, curb and gutter, sidewalk, and correct ADA deficiencies, making improvements to the lane configurations and to the pedestrian and bike facilities to improve safety and level of service. |  | Between $5,000,000 and $10,000,000
CFHWY00648 | MAT-SU BOROUGH ROAD REPAIRS - NOV 2018 EQ PERM REPAIRS (MSB) | CFHWY00648 | 92010 | Central Region | Matanuska-Susitna Borough | Steven J Rzepka | (907)269-0592 | 2022-06-01 | This project will design and construct repairs for the November 30, 2018 earthquake in the Central Region of Alaska on Point MacKenzie Road, Vine Road, and South Settlers Bay Drive. Repairs may include, but are not limited to, asphalt, embankment, roadside hardware, retaining walls, utilities, and drainage. |  | Between $5,000,000 and $10,000,000
Z605630000 | Saint Mary's Airport Improvements | Z605630000 | PENDING | Northern Region | St Mary's | Christopher F Johnston | (907)451-2322 | 2022-06-01 | Rehabilitate and resurface runways, taxiways, and apron. Project will include replacing airport lighting and runway safety area improvements. |  | Between $20,000,000 and $30,000,000
SFHWY00103 | SIT HALIBUT POINT RD & PETERSON AVE INTERSECTION SAFETY IMPR | SFHWY00103 | 3214 | Southcoast Region | Sitka | Nathan A Purves | (907)465-4483 | 2022-06-01 | Provide additional illumination at the Halibut Point Road/Peterson Avenue Intersection to achieve a level of luminance that meets current DOT&PF standards. Modify adjacent roadway lighting as needed to maintain satisfactory continuous illumination. Establish a pass-through crossing to facilitate less challenging pedestrian movements. Improve intersection sight distance by removing utility equipment located in the southeast quadrant of the intersection, acquiring property to remove parking spaces that, when occupied, create sight line obstructions, and modifying access to an apartment building adjacent to the intersection (shorten curb cut). Replace existing S1-1 School signs with W11-2 advance pedestrian warning signs. |  | Between $500,000 and $1,000,000
CSAPT00566 | ANC Parking Garage PG111 Repairs and Improvement | CSAPT00566 | N/A | Central Region | Anchorage | John W Turley | (907)266-2171 | 2022-07-01 | This project will replace the roof membrane on the roof level of PG-111. Parking Garage and will make repairs to floor deck spalling and electric lighting that have resulted from water infiltration.
CFHWY00006 | Colleen Street Intersection and Frontage Road | CFHWY00006 | 0A15033 | Central Region | Palmer | Sean M Baski | (907)269-0566 | 2022-07-01 | Construct improvements to the Glenn Highway and South Colleen Street intersection, and improve connectivity and access. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00431/00431_Plans.pdf">Preliminary Plans (~37 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $2,500,000 and $5,000,000
NFAPT00249 | Deering Airport Improvements | NFAPT00249 | 3-02-0400-XX-202X | Northern Region | Deering | Jonathan J Hutchinson | (907)451-5479 | 2022-07-01 | Resurface the existing runway, taxiway and apron and provide drainage improvements. Upgrade lighting system and electrical building. Provide erosion protection for the runway safety area at Runway 29. Replace segmented circle. Upgrade and armor the airport access road to reduce flooding and provide cross drainage. Apply dust palliative to all airport operational surfaces and access road. |  | Between $10,000,000 and $20,000,000
CFHWY00431 | Glenn Hwy: Parks Hwy to S. Inner Springer Lp. (Phase II) | CFHWY00431 | 0A15037 | Central Region | Palmer | Sean M Baski | (907)269-0566 | 2022-07-01 | This project will reconstruct the Glenn Highway from the Parks Highway to S. Inner Springer Loop as a four-lane divided highway. Project work will add lanes, widen shoulders, add turn lanes and frontage roads, signals, illumination, other traffic safety related improvements. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00431/00431_Plans.pdf">Preliminary Plans (~54 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
CFHWY00432 | Glenn Hwy: Parks to S. Inner Springer Lp. Pathway (Phase II) | CFHWY00432 | 0A15038 | Central Region | Palmer | Sean M Baski | (907)269-0566 | 2022-07-01 | This project will construct a pathway along the Glenn Highway and other roads. It also includes roadside hardware and drainage, intersection, and ADA improvements. This project will construct the second phase of the Glenn Hwy: Mile Post 34-42 Parks to Old Glenn Pathway project. | <a class=linkcopy href="http://dot.state.ak.us/creg/design/highways/Projects/00431/00431_Plans.pdf">Preliminary Plans (~54 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> Please note, this project will be advertising with project number CFHWY00431. | Between $1,000,000 and $2,500,000
CFAPT00491 | HOMER AIRPORT IMPROVEMENTS | CFAPT00491 | AIP 3-02-0122-020-2022 | Central Region | Homer | Matthew H Hansen | (907)269-0602 | 2022-07-01 | The project proposes to rehabilitate the runway and runway safety area; remove obstructions; rehabilitate Taxiways A & B; rehabilitate and expand the General Aviation apron toward the east; replace airfield lighting, remove Taxiway D; install a new turnaround taxiway at the east end of the runway, and install a new taxiway connecting the east end of the General Aviation apron to the runway. |  | Between $20,000,000 and $30,000,000
SFHWY00307 | JNU EGAN YANDUKIN INTERSECTION IMPROVEMENTS HSIP | SFHWY00307 | 3261 | Southcoast Region | Juneau | Nathan A Purves | (907)465-4483 | 2022-08-01 | Set seasonal speed limit reduction on Egan in the vicinity of the Egan Yandukin intersection. Improve delineation for both left turns on Egan to improve line of sight and reduce travel distance to clear opposing traffic. Improve delineation for the northbound right turn movement from Egan to make it easier for southbound left turn drivers to determine if opposing traffic is executing the right turn or continuing through the intersection. |  | Between $1,000,000 and $2,500,000
SFHWY00111 | KDK CHINIAK HIGHWAY REHABILITATION: MILE POST 15 TO 31 | SFHWY00111 | 391015 | Southcoast Region | Kodiak | James L Brown | (907)465-1796 | 2022-08-01 | Rehabilitate the Chiniak Highway from Milepost 15 to just past 31 to improve and preserve the roadway subgrade and surface. Address lighting, guardrails, drainage, culverts and other highway appurtenances as needed. |  | Between $10,000,000 and $20,000,000
SFAPT00124 | KING SALMON AIRPORT PERIMETER FENCING UPGRADES | SFAPT00124 | N/A | Southcoast Region | King Salmon | Loren K Gehring | (907)465-8189 | 2022-08-01 | Replace/upgrade access controls/gates to meet 49 CFR 1542 requirements. Replace existing fencing as needed. | Construct perimeter fencing and gate upgrades. Upgrades include providing new automatic vehicle gates and pedestrian gates with electric lock gate systems. | Between $1,000,000 and $2,500,000
SFAPT00327 | KTN AIRPORT SEAPLANE RAMP AND HAUL OUT REFURBISHMENT | SFAPT00327 | N/A | Southcoast Region | Ketchikan | Loren K Gehring | (907)465-8189 | 2022-08-01 | Refurbish and/or replace existing seaplane float and haul-out ramp facility at the Ketchikan Airport. Investigate replacement at a new location. |  | Between $1,000,000 and $2,500,000
Z581060000 | STERLING HWY: MP 157-169 RECON-ANCHOR PT TO BAYCREST HILL | Z581060000 | 211052 | Central Region | Kenai Peninsula | Kelly L Summers | (907)269-0546 | 2022-08-01 | Reconstruction and upgrading of 12 miles of Sterling Highway along existing corridor. Project upgrades include widening, construction of passing lanes, resurfacing, scenic turnouts, drainage improvements, minor realignment, and configuration to current AASHTO geometric standards. Also, rehabilitation/replacement of the North Fork Anchor River and Anchor River Bridges. | Reconstruct and upgrade 12 miles of the Sterling Hwy along the existing corridor from Anchor Pt to Baycrest Hill. Replacement of North Fork Anchor River and Anchor River Bridges. Project upgrades include widening, construction of passing lanes, resurfacing, drainage improvements, minor realignment, and configuration to current AASHTO geometric standards. | Between $80,000,000 and $90,000,000
Z516210000 | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT | Z516210000 | 000S783 | Central Region | Takotna | Clint J Adler | (907)269-0544 | 2022-08-01 | The Alaska Department of Transportation and Public Facilities (DOT&PF) in cooperation with the Federal Highway Administration (FHWA) proposes to replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge #462. | Replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge. | Between $2,500,000 and $5,000,000
CSAPT00931 | ANC ACCESS GATE, HEADBOLT OUTLETS, AND DITCH GRADING | CSAPT00931 | N/A | Central Region | Anchorage | Jennifer M Carle | (907)602-2511 | 2022-09-01 | Project will include: 1) constructing a new vehicle access control gate at AFM West; 2) install head bolt outlets (HBO) at the TW A and DeHavilland Avenue snow disposal sites; and 3) re-grade the tug road ditch south of the Trans-northern lease lot. |  | Between $500,000 and $1,000,000
CFAPT00855 | ANC TW K and TL E Apron Rehabilitation | CFAPT00855 | N/A | Central Region | Anchorage | Jennifer M Carle | (907)602-2511 | 2022-09-01 | Rehabilitate the apron surface. Project will include striping. | Rehabilitate Apron Surface | Between $500,000 and $1,000,000
SFHWY00259 | JNU KAXDIGOOWU HEEN DEI IMP (BROTHERHOOD BRIDGE TRAIL IMP) | SFHWY00259 | TA18010 | Southcoast Region | Juneau | Peter J Jackson | (907)465-4439 | 2022-09-01 | This project will design and improve the Kaxdigoowu Heen Dei (Kax) Trail from River Road to the edge of Brotherhood Meadow, where a re-route planned for construction in 2019 would end, and create a new segment of paved trail that connects from the edge of Brotherhood Meadow to the Wildmeadow Neighborhood and the newly constructed trail from Pederson Hill neighborhood. Work will primarily consist of selected areas of subgrade repair, repave the 8 foot wide trail, replace and add new culverts as needed, and build approximately 1,500 feet of new trail section. The new trail will be composed of fill, D-1, and 8 foot wide asphalt with 1 foot shoulders. the pedestrian bridge at Montana Creek will be replaced or modified to provide a larger span that allows for some natural stream movement and can withstand emergency and maintenance vehicle use once again, and the banks armored to increase the expected useful life of the bridge. Additional improvements include adding bike racks, installing interpretive signs, and increasing site distance along the trail. |  | Between $1,000,000 and $2,500,000
CFHWY00129 | TAKOTNA RIVER BRIDGE REPLACEMENT | CFHWY00129 | 1569 | Central Region | Takotna | Julia R Hanson | (907)269-0753 | 2022-09-01 | Reconstruction (replacement) of the Takotna River Bridge (bridge #0463). Reconstruction may include bridge work, roadside hardware, drainage improvements, and utilities. | Replacement of the Takotna River Bridge (bridge #0463). May include bridge work, roadside hardware, drainage improvements, and utilities. | Between $5,000,000 and $10,000,000
SAMHS00300 | AMHS SYSTEM WIDE BRIDGE IMPROVEMENTS (FHWA) | SAMHS00300 | 9500154 | Southcoast Region | Regionwide | Loren K Gehring | (907)465-8189 | 2022-10-01 | Make improvements to AMHS ferry terminal transfer bridges at various locations Statewide to extend their service life and maintain functionality. AMHS relies on 25 different vehicle transfer bridges for its operations. Improvements would include: bridge and float blast cleaning and repainting, weld crack repairs, floor beam strengthening, girder redundancy modifications, utility improvements, bridge and apron lift system improvements, and bridge transition improvements. Design work anticipated to be accomplished under this program and separate projects will be established for the construction phase. |  | Between $1,000,000 and $2,500,000
SAMHS00302 | AMHS SYSTEM WIDE UPLANDS IMPROVEMENTS | SAMHS00302 | 9500156 | Southcoast Region | Regionwide | Loren K Gehring | (907)465-8189 | 2022-10-01 | Make improvements to AMHS owned and operated ferry terminal buildings and upland facilities to extend their service life and maintain functionality. There are 21 State owned and operated AMHS terminals and 16 terminal buildings in the system. Building improvements would include: interior and exterior improvements, roof replacements, exterior door replacements, bathroom renovations, and heating system improvements. Uplands improvements would include: Electrical system improvements for uplands lighting and marine terminal power, lighting improvements, and pedestrian and parking improvements. Design work anticipated to be accomplished under this program and separate projects will be established for the construction phase.
CFHWY00286 | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | CFHWY00286 | 510007 | Central Region | Anchorage | Jon W Knowles | (907)269-0643 | 2022-10-01 | Pavement Preservation of DeArmoun Rd. from East 140th Avenue to Hillside Drive including improvements to drainage, intersections, ADA, roadside hardware, and utilities. High Friction Surface Treatment may be reapplied. |  | Between $2,500,000 and $5,000,000
NFHWY00587 | EDGERTON HWY MP 24 - 29 RESURFACING | NFHWY00587 | 850030 | Northern Region | Mccarthy | John J Netardus | (907)451-5448 | 2022-10-01 | Resurface the Edgerton Highway from MP 24 - 29. Project will include drainage improvements, roadside hardware, and utilities.
CFHWY00493 | FUNNY RIVER RD PAVEMENT PRESERVATION | CFHWY00493 | 485002 | Central Region | Kenai | Steven J Rzepka | (907)269-0592 | 2022-10-01 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements and utilities. | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements and utilities. | Between $10,000,000 and $20,000,000
SFHWY00070 | KTN SAYLES/GORGE ST VIADUCT (#1841) IMPRVMT | SFHWY00070 | 3225 | Southcoast Region | Ketchikan | Kirk D Miller | (907)465-1215 | 2022-10-01 | This project will replace or rehabilitate the Sayles/Gorge Street Viaduct (#1841). |  | Between $2,500,000 and $5,000,000
CFAPT00882 | LHD AIRCRAFT AND LAKESHORE DRIVE REHABILITATION | CFAPT00882 | N/A | Central Region | Anchorage | Jennifer M Carle | (907)602-2511 | 2022-10-01 | Rehabilitate 9,600 ft of Aircraft and Lakeshore Dr from Voight Cir to the Lake Hood East property boundary south of runway 14/32. Project includes roadway reconditioning, structural section repairs, drainage improvements, and striping. | Rehabilitate Aircraft and Lakeshore Drive pavement. Includes drainage improvements. | Between $1,000,000 and $2,500,000
Z621230000 | Nome Port Road Reconstruction | Z621230000 | 2278 | Northern Region | Nome | Lauren M Little | (907)378-5911 | 2022-10-01 | Reconstruct and realign Port Road in Nome, including drainage improvements and construction of sidewalks. |  | Between $2,500,000 and $5,000,000
NFHWY00588 | ELLIOTT HIGHWAY MP 18 - 29 RESURFACING | NFHWY00588 | 650035 | Northern Region | Livengood | John J Netardus | (907)451-5448 | 2022-11-01 | Resurface the Elliott Highway from MP 18 - 29. Project will include selected areas of roadway rehabilitation, bridge work, drainage improvements, roadside hardware, and utilities.
SFAPT00234 | HNS AIRPORT RESURFACING | SFAPT00234 | N/A | Southcoast Region | Haines | David A Pyeatt | (907)465-4490 | 2022-11-01 | The project will rehabilitate the Haines Airport runway and taxiways. Construction activities include, reclimation of paved surfaced, construction of a new taxilane, drainage modification, electrical and lighting replacement, constructing a new access point for the public helipad, and constructing a SREB foundation pad, | The project schedule and budget are being re-developed as the scope has changed. A SREB building is being added to the project. Also, a white paper may be required to justify keeping the 100' width of the runway. | Between $20,000,000 and $30,000,000
Z681370000 | HNS AIRPORT SRE BUILDING | Z681370000 | N/A | Southcoast Region | Haines | David A Pyeatt | (907)465-4490 | 2022-11-01 | This is an FAA funded project which involves the construction of a new 50' x 90' sand, chemical, and snow removal equipment storage building with adjacent parking lot at the location shown in the Haines Airport Master Plan. The work required would include but not limited to site prep, drainage, lighting, building construction, and surfacing.
CFHWY00564 | HSIP: CR GUARDRAIL INVENTORY AND UPGRADE | CFHWY00564 | 1665 | Central Region | Central | Chris L Bentz | (907)269-0652 | 2022-11-01 | Prepare inventory by evaluating existing guardrail segments, end terminals, and associated hardware along several routes in Central Region for damage and adherence to current AKDOT&PF and FHWY standards. Use results of inventory to design and construct installation or updates to guardrail segments found in non- conformance with State and Federal standards. |  | Between $20,000,000 and $30,000,000
CFHWY00939 | HSIP:CR Guardrail Inventory and Upgrade (North) | CFHWY00939 | N/A | Central Region | Central Region | Chris L Bentz | (907)269-0652 | 2022-11-01 | Prepare inventory by evaluating existing guardrail segments, end terminals, and associated hardware along several routes in Central Region for damage and adherence to current AKDOT&PF and FHWA standards. Use results of inventory to design and construct installation or updates to guardrail segments found in non-conformance with State and Federal standards.
CFHWY00938 | HSIP:CR Guardrail Inventory and Upgrade (South) | CFHWY00938 | N/A | Central Region | Central Region | Chris L Bentz | (907)269-0652 | 2022-11-01 | Prepare inventory by evaluating existing guardrail segments, end terminals, and associated hardware along several routes in Central Region for damage and adherence to current AKDOT&PF and FHWY standards. Use results of inventory to design and construct installation or updates to guardrail segments found in non- conformance with State and Federal standards.
2501000083 | Ketchikan Pioneer Home Structural Upgrades | 2501000083 | N/A | Central Region | Central Region | Alyson K Wardell | (907)269-0869 | 2022-11-01 | Seismic upgrades for roof and building structure | Advertise contingent upon funds by User Agency | Between $500,000 and $1,000,000
NFHWY00265 | RICHARDSON HWY MP 128-138 REHABILITATION | NFHWY00265 | N/A | Northern Region | Tazlina | Russell M Johnson | (907)451-5059 | 2022-11-01 | Rehabilitate the Richardson Highway and bridges between MP 128 and MP 138. Project work will include road realignment at MP 134, drainage improvements, intersection improvements, roadside hardware, and utilities.
SFHWY00308 | WRG ZIMOVIA HWY ROCK FALL MITIGATION HSIP | SFHWY00308 | 3262 | Southcoast Region | Wrangell | Nathan A Purves | (907)465-4483 | 2022-11-01 | Analyze and identify areas within the three targeted rockfall zones and apply the proscribed mitigation techniques to stabilize slopes to reduce hazards falling into the road. |  | Between $200,000 and $500,000
SAMHS00301 | AMHS SYSTEM WIDE MOORING STRUCTURE IMPROVEMENTS | SAMHS00301 | 9500155 | Southcoast Region | Regionwide | Loren K Gehring | (907)465-8189 | 2022-12-01 | Make improvements to AMHS ferry terminal transfer bridges at various locations Statewide to extend their service life and maintain functionality. AMHS relies on 25 different vehicle transfer bridges for its operations. Improvements would include: bridge and float blast cleaning and repainting, weld crack repairs, floor beam strengthening, girder redundancy modifications, utility improvements, bridge and apron lift system improvements, and bridge transition improvements. Design work anticipated to be accomplished under this program and separate projects will be established for the construction phase. |  | Between $5,000,000 and $10,000,000
Z686060000 | HNS HWY RECONSTRUCTION MILEPOST 20-25.0 | Z686060000 | 956028 | Southcoast Region | Haines | Gregory K Lockwood | (907)465-2393 | 2022-12-01 | Reconstruction of Haines Highway from Milepost 20 to 25 including the Chilkat River bridge. | Reconstruct the Haines Highway from milepost 20.0 to 25.0 including the Chilkat River Bridge is the next and final phase to advertise | Between $30,000,000 and $40,000,000
CFAPT00288 | MEKORYUK AIRPORT REHABILITATION | CFAPT00288 | 3-02-0176-003-2022 | Central Region | Mekoryuk | Philip W Cheasebro | (907)269-0606 | 2022-12-01 | Rehabilitate/reconstruct runway, taxiway, and access road. Install new lighting. Install new heated two-bay SREB and install dust palliative. | Pre PS&E review documents are located at the link: <a class=linkcopy href=" https://dot.alaska.gov/creg/design/aviation/Tentative_Advertising_List_Docs/6_00288%20-%20Mekoryuk%20Airport%20Rehabilitation%20Pre%20PSE-TAS.pdf ">Preliminary Plans (~20 Mb) </a><img name="pdf_icon" src="/images/styls/pdf_icon.gif" width="18" height="18" border="0"> | Between $20,000,000 and $30,000,000
NFAPT00537 | NOR REG VARIOUS AIRPORTS VISUAL AID REPLACEMENT FFY2020 | NFAPT00537 | N/A | Northern Region | Regionwide | Daniel A Phillips | (907)451-2926 | 2022-12-01 | Replace visual aids at the following airports: Beaver, Birch Creek, Elim, and Koyuk.
Z631860000 | RICHARDSON HWY MP 167-173 | Z631860000 | 713010 | Northern Region | Regionwide | Russell M Johnson | (907)451-5059 | 2022-12-01 | Reconstruct the Richardson Highway between MP 167 and 173. Project includes roadside hardware, drainage improvements and utility relocations. | Reconstruct the Richardson Highway between mileposts 167-173. | Between $20,000,000 and $30,000,000
Z607150000 | RICHARDSON HWY MP 266-341 PASSING LANES | Z607150000 | 0A23021 | Northern Region | Fairbanks North Star Borough | Carl F Heim | (907)451-5359 | 2022-12-01 | Construct passing lanes at multiple locations between Milepost 266 and 341 on the Richardson Highway. Work includes roadside hardware, drainage improvements, intersection improvements and utilities. |  | Between $30,000,000 and $40,000,000
SFAPT00178 | UNALASKA TAXIWAY AND APRON REHABILITATION | SFAPT00178 | N/A | Southcoast Region | Unalaska | Gregory K Lockwood | (907)465-2393 | 2022-12-01 | Begin preliminary design for the Unalaska airport apron and taxiway rehabilitation. For the terminal apron: mill 2 inches of the existing AC pavement and repair underlying PCC. Repave with 2 inches hot mix asphalt. For the hanger apron: repair PCC surface and joints and overlay with 2 inches of hot mix asphalt. | Rehabilitate the airport apron and taxiway apron. | Between $5,000,000 and $10,000,000
SFAPT00412 | WRG GATES AND SECURITY UPGRADES | SFAPT00412 | N/A | Southcoast Region | Wrangell | David B Epstein | (907)465-4446 | 2022-12-01 | (1) Replace the electric vehicle gates, Gate #3 and Gate #9. Install up-to-date security systems on vehicle gates, Gate #3 and Gate #9; and (2) Install compatible/compliant security entry systems on pedestrian gates, Gate #4, #8, #11 and #13. |  | Between $1,000,000 and $2,500,000
CSAPT00754 | ANC RON 3 AND 4 JOINT REPAIRS | CSAPT00754 | N/A | Central Region | Anchorage | Jennifer M Carle | (907)602-2511 | 2023-01-01 | Remove and replace approximately 15,000 feet of liquid joint seal and perform approximately 300 square feet of elastomeric concrete repairs on hardstands RON 3 and 4. | Repair joints and concrete on hardstands 3 & 4. | Between $1,000,000 and $2,500,000
CFAPT00758 | ANC TAXIWAY R SOUTH SURFACE SEAL | CFAPT00758 | N/A | Central Region | Anchorage | Jennifer M Carle | (907)602-2511 | 2023-01-01 | Apply a seal coat to the taxiway surface, select joint repairs and restripe. | Surface seal taxiway | Between $200,000 and $500,000
NFHWY00570 | CHENA RIDGE ROAD AND CHENA PUMP ROAD RESURFACING | NFHWY00570 | 645015 | Northern Region | Fairbanks North Star Borough | John J Netardus | (907)451-5448 | 2023-01-01 | Resurface Chena Ridge Road and Chena Pump Road. Project will include bridge work, drainage improvements, embankment stabilization, and roadside hardware.
SFHWY00377 | CRAIG ADA IMPROVEMENTS | SFHWY00377 | 3274 | Southcoast Region | Craig | Bran P Pollard | (907)465-4526 | 2023-01-01 | ADA Improvements to Craig segments 1 & 2 of the Southcoast ADA Audit. Approximately 1.8 miles of Water st./Craig/Klawock Hwy between Third Street and Craig High School. Scope of work to include sidewalk, curb ramp, driveway and street crossing improvements consistent with findings in the 2017 Southcoast ADA Audit.
NFHWY00133 | Richardson Highway MP 35-65 Resurfacing (Construction 35-40) | NFHWY00133 | 711074 | Northern Region | Valdez | Colleen M Ackiss | (907)451-5179 | 2023-01-01 | Resurface the Richardson Highway between MP 35-40. Improvements include bridge work, retaining wall repair, roadside hardware, drainage, and utility relocations. |  | Between $10,000,000 and $20,000,000
SFAPT00371 | SIT AIRPORT UTILITY IMPROVEMENT | SFAPT00371 | N/A | Southcoast Region | Sitka | Bran P Pollard | (907)465-4526 | 2023-01-01 | Replace and relocate the water and sewer lines serving the Sitka Rocky Gutierrez Airport and along airport road where infrastructure serves lease lots. The water and sewer lines have reached their useful life and are at failure.
CFAPT00835 | ANC TAXIWAY Z IMPROVEMENTS EAST | CFAPT00835 | N/A | Central Region | Anchorage | Philip W Cheasebro | (907)269-0606 | 2023-02-01 | Extend the southern parallel taxiway from Taxiway F to Taxiway C, reconstruct the Taxiway C interlink, reconstruct Kulis Taxiway, and tie into the Kulis Apron.
Z560200000 | FAIRVIEW LOOP PATHWAY AND SAFETY IMPROVEMENTS (GF/GO) | Z560200000 | N/A | Central Region | Wasilla | Sean M Baski | (907)269-0566 | 2023-02-01 | Revised scope 3/14: This project will construct a separated pathway along Fairview Loop Road from Top of the World Circle to Edlund Road. Construction of the pathway may be extended further east depending on the available funding. Safety improvements at selected intersections and drainage improvements not included the Fairview Loop Pavement Preservation project will also be included in the project. |  | Between $10,000,000 and $20,000,000
NFHWY00633 | FAST AREA SURFACE UPGRADES FFY2023 | NFHWY00633 | N/A | Northern Region | Fairbanks North Star Borough | John J Netardus | (907)451-5448 | 2023-02-01 | Resurface pavement, replace pavement markings, replace sidewalk curb with Americans with Disabilities Act (ADA) compliant curb ramps at street corners, improve sidewalks and pedestrian facilities, improve intersections, and install cross culverts on various streets and sidewalks in Fairbanks and North Pole.
SFHWY00278 | HNH HARBOR WAY PEDESTRIAN IMP & PITT ISLAND CEMETERY WALKWY | SFHWY00278 | 3255 | Southcoast Region | Hoonah | Bran P Pollard | (907)465-4526 | 2023-02-01 | The Hoonah Harbor Way Pedestrian Improvements & Pitt Island Cemetery Walkway project is designed to address two major issues for the community: 1) Provide safe and reliable access to the community's cemetery on Pitt Island; and 2) Alleviate tourist-related pedestrian congestion in the harbor area. The City of Hoonah plans to construct a 6-foot wide sidewalk/walkway from the Hoonah city center out to Pitt Island and the community cemetery. This 0.8 mile project will start at the intersection of Front Street and Harbor Way and end on Pitt Island. Approximately 0.5 miles of the sidewalk/walkway will be built atop the US Army Corps of Engineers' breakwater and a 175-foot long gangway will be installed from the shore to the breakwater. |  | Between $2,500,000 and $5,000,000
SFHWY00058-3 | JNU DOUGLAS HWY RESURFACE & SIDEWALK REPAIRS Stage 3 | SFHWY00058-3 | 958032 | Southcoast Region | Juneau | David A Pyeatt | (907)465-4490 | 2023-02-01 | Work required for this project includes reconstructing and resurfacing Douglas Highway from Egan Drive to about 700 feet south of Cordova Street. Other work includes ADA improvements, storm drain system repairs, signing and striping improvements, and bridge joint repairs. A list of anticipated work items are listed below: • Pavement removal and roadway excavation • Pavement cold planing • Removal and installation of concrete gutter and curb & gutters • Removal and installation of asphalt and concrete sidewalks • Reconstruction of existing accessible sidewalk ramps • Replacement and lining of existing culverts and storm drains • Construction of riprap aprons • Installation of new curb inlets • Removal and installation of storm drain manholes • Replacement of existing signs • Addition of new signs • New pavement markings • Replacement of existing guardrail and bridge transition rail |  | Between $2,500,000 and $5,000,000
CFHWY00012 | SEWARD HWY: O'MALLEY TO DIMOND RECONSTRUCTION | CFHWY00012 | 537008 | Central Region | Anchorage | Sean M Baski | (907)269-0566 | 2023-02-01 | This federally funded project will reconstruct the Seward Highway between O'Malley Road and Dimond Blvd. Work may include: new north and south bound lanes and auxiliary lanes, a new interchange connecting 92nd Avenue to Academy Drive, reconstruction of the existing interchanges within the project limits, construction and reconstruction of frontage roads, pathway and sidewalk improvements, noise walls and drainage improvements. |  | Between $90,000,000 and $100,000,000
Z512210000 | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | Z512210000 | 1417 | Central Region | Wasilla | Chris L Bentz | (907)269-0652 | 2023-02-01 | Upgrade Seward Meridian to a four-lane roadway and a multi-use, separated pathway along the west side from the Palmer-Wasilla Highway to Bogard Road and extend SMP one mile from Bogard Road to Seldon Road. Intersection improvements include a new roundabout at the Bogard Road intersection and a new signal at Seldon Road. A new bridge, Cottonwood Creek Bridge #1696, would replace the existing culvert at the Cottonwood Creek crossing. |  | Between $40,000,000 and $50,000,000